## Desired format
| Activity ID | Start | Finish |  | Activity Name | Original Duration
| 962 TB2 Machine Build #2 | 2019-01-07 | 2019-02-08 | 32 | Setup - (Impl Valve, OEAII, NGSC, Pump) | 10
SW | S13 SW Checkout | 2019-03-07 | 2019-03-13 | 6 | Run - Steering Checkout | 5
Machine | Machine Checkout STP64 | 2019-03-14 | 2019-03-18 | 4 | Run | 3
Hydraulics | Steering Tuning #2 | 2019-03-19 | 2019-04-15 | 27 |  | 20
Hydraulics | Steering Tuning- Knotch Filter | 2019-03-19 | 2019-03-21 | 2 |  | 3
Hydraulics | Steering Tuning- Opr Eval Knotch Filter | 2019-03-22 | 2019-03-25 | 3 |  | 2
Hydraulics | Steering Tuning - Perf Tuning | 2019-03-26 | 2019-04-08 | 13 |  | 10
Hydraulics | Steering Tuning- Operator Eval | 2019-04-09 | 2019-04-15 | 6 |  | 5
Hydraulics | Failure Mode Response #1 | 2019-04-09 | 2019-05-15 | 36 |  | 27
SW | STP 230/289 #2 | 2019-05-16 | 2019-05-22 | 6 |  | 6
Transmission | XMSN Development | 2019-05-23 | 2019-06-19 | 27 |  | 19
SW | Implement Valve Tuning | 2019-06-20 | 2019-07-11 | 21 | Run (Cat Electronics - Steve Queen) | 25
SW | S14 SW Update | 2019-06-07 | 2019-06-10 | 3 |  | 2
Performance | L5 Performance Dev/Tuning #1 | 2019-07-12 | 2019-07-25 | 13 | Run | 10
Safety and Regs | ISO 5010 Feasibility | 2019-07-26 | 2019-08-15 | 20 |  | 568
Technology | Cat Detect B Radar | 2019-08-15 | 2019-08-19 | 4 | Run | 3
CAT E | Failure Mode Response #2 | 2019-08-20 | 2019-09-19 | 30 |  | 27
SW | S15 SW Checkout | 2019-09-20 | 2019-10-03 | 13 | Run & Checkout S15 | 10
SW | Implement Valve Tuning #2 | 2019-10-04 | 2019-10-17 | 13 | Run | 20
SW | S16 SW Checkout | 2019-12-06 | 2019-12-19 | 13 | Run & Checkout S16 | 10
Performance | L5 Performance Dev/Tuning #2 | 2020-01-02 | 2020-01-23 | 21 | Run | 15
Safety and Regs | Stg V EMC Test | 2020-01-24 | 2020-03-02 | 38 |  | 77
SW | S17 SW Checkout | 2020-02-20 | 2020-03-04 | 13 | Run & Checkout S17 | 10
SW | S17 SW Endurance - 50 Hrs | 2020-03-05 | 2020-03-08 | 3 | Run Endurance | 4
SW | S18 SW Checkout | 2020-03-02 | 2020-03-13 | 11 | Run & Checkout S18 | 10
SW | S19 SW Checkout | 2020-05-01 | 2020-05-14 | 13 | Run & Checkout S19 | 10
SW | S20 SW Checkout | 2020-08-03 | 2020-08-14 | 11 | Run & Checkout S20 | 10
SW | S20 SW Endurance - 50 Hrs | 2020-08-15 | 2020-08-18 | 3 | Run Endurance | 4
| 950 AU2020 Testbed2 (SN) | 2019-05-07 | 2020-07-15 |  | Aurora Build
Machine | Machine Key On | 2019-05-07 | 2019-05-08 |  |  | 1
Machine | Ship to PPG | 2019-05-09 | 2019-05-09 |  |  | 0
SW | S13 SW Checkout | 2019-05-10 | 2019-05-23 |  | Run - Steering Checkout | 13
Machine | Machine Checkout STP-64 | 2019-05-24 | 2019-05-29 |  |  | 5
Hydraulics | Implement Valve Tuning #1 | 2019-05-30 | 2019-06-19 |  |  | 20
Performance | L5 Performance Dev/Tuning #1 | 2019-06-20 | 2019-07-03 |  |  | 13
SW | S14 SW Update | 2019-06-07 | 2019-06-10 |  | Run & Checkout S14 | 3
Performance | Rimpull/Response | 2019-07-05 | 2019-07-17 |  |  | 12
Cooling | STP-153 (Airflow Testing) | 2019-07-18 | 2019-07-25 |  |  | 7
Cooling | STP-155 (Water Flow Test) | 2019-07-26 | 2019-07-31 |  |  | 5
Cooling | STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT | 2019-08-01 | 2019-08-22 |  |  | 21
Engine Installation | MER Engine Install test | 2019-08-23 | 2019-09-04 |  |  | 12
Hydraulics | Hydraulic Test | 2019-09-05 | 2019-10-03 |  |  | 28
SW | S15 SW Update | 2019-09-06 | 2019-09-09 |  | Run & Checkout S15 | 3
NVH | 950 Stage V Machine Sound Dev | 2019-10-04 | 2019-10-08 |  |  | 4
Performance | Cold Room Test | 2019-10-09 | 2019-12-16 |  |  | 68
SW | S16 SW Update | 2019-12-06 | 2019-12-09 |  | Run & Checkout S16 | 3
Performance | L5 Performance Dev/Tuning #2 | 2020-01-02 | 2020-01-23 |  |  | 21
Engine Installation | MER #2 Engine Install Test | 2020-01-24 | 2020-02-26 |  |  | 33
Safety and Regs | Prelim ISO 5010 Steering | 2020-02-05 | 2020-03-02 |  |  | 26
SW | S17 SW Update | 2020-02-19 | 2020-02-20 |  | Run & Checkout S17 | 1
Transmission | XMSN Auto Cal Dev | 2020-02-28 | 2020-04-01 |  |  | 33
Engine Installation | STP 407 Engine Installation Audit | 2020-04-02 | 2020-04-13 |  |  | 11
Transmission | XMSN Signature | 2020-04-14 | 2020-05-08 |  |  | 24
Performance | L5 Issue Resolution | 2020-05-11 | 2020-05-22 |  |  | 11
NVH | 950 Stage V Machine Sound Dev #2 | 2020-05-26 | 2020-05-28 |  |  | 2
Performance | Productivity | 2020-05-29 | 2020-06-18 |  |  | 20
| 962 Stg V Testbed3 (SN) | 2019-03-21 | 2019-05-17 |  | PPG Build | 42
Machine | PPG Machine Build | 2019-04-15 | 2019-05-17 |  | Rework (Imp valve, pump, Hyd tank, AUX valve, Safim brake valve, NGSC gen 3, OEAII | 17
SW | SW & Electrical Checkout | 2019-05-20 | 2019-06-10 |  |  | 15
Machine | Machine Checkout STP-64 | 2019-06-11 | 2019-06-13 |  |  | 13
Hydraulics | Hydraulic Test | 2019-06-14 | 2019-07-15 |  |  | 58
Light Fab & MER | Light Fab and Engine Install OMSA & MER Test | 2019-07-16 | 2019-08-14 |  |  | 24
SW | S14 SW Update | 2019-08-15 | 2019-08-17 |  | Run & Checkout S14 | 2
Heavy Structures | OMSA Heavy Fab | 2019-08-15 | 2019-09-25 |  |  | 41
SW | S15 SW Update | 2019-09-06 | 2019-09-09 |  | Run & Checkout S15 | 3
Performance | L5 Performance Dev/Tuning #1 | 2019-09-26 | 2019-10-16 |  |  | 20
ELI | Electrical Load Study & Battery Shielded Cable | 2019-11-07 | 2019-11-13 |  |  | 6
Product Support | Servicability Audit | 2019-11-25 | 2019-11-26 |  |  | 1
Safety and Regs | Safety Audit | 2019-11-27 | 2019-12-02 |  |  | 5
SW | S16 SW Update | 2019-12-06 | 2019-12-09 |  | Run & Checkout S16 | 3
Safety and Regs | ISO 3450 Feasibility Checkout | 2020-01-02 | 2020-01-27 |  |  | 25
SW | S17 SW Update | 2020-02-19 | 2020-02-20 |  | Run & Checkout S17 | 2
| 962 T3 HMU Testbed 4 (SN) | 2019-03-28 | 2020-06-02 |  |  | 245
Machine | Machine Update - Built in Aurora | 2019-05-01 | 2019-06-15 |  |  | 3
Machine | Machine Key On | 2019-06-16 | 2019-06-18 |  |  | 2
Machine | Ship to PPG | 2019-06-18 | 2019-06-19 |  |  | 1
Machine | Machine Checkout STP-64 | 2019-06-20 | 2019-06-25 |  | Run | 5
Product Support | Servicability Audit | 2019-06-26 | 2019-06-28 |  |  | 2
NVH | 962 T3 Muffler Sound Validation | 2019-06-29 | 2019-07-01 |  | Run - Sound Bldg | 2
Endurance # 1 | 962 Endurance 0-500 hrs | 2019-07-02 | 2019-09-08 |  |  | 68
SW | S14 SW Update | 2019-09-09 | 2019-09-11 |  | Run & Checkout S14 | 2
Endurance # 2 | 962 Endurance 501-1000 hrs | 2019-09-12 | 2019-10-10 |  |  | 28
Endurance # 3 | 962 Endurance 1001-1500 hrs | 2019-10-11 | 2019-11-09 |  |  | 29
SW | S15 SW Update | 2019-11-10 | 2019-11-12 |  | Run & Checkout S15 | 2
Endurance # 4 | 962 Endurance 1501-2000 hrs | 2019-11-13 | 2019-12-13 |  |  | 30
Engine Installation | BOSCH Fuel System Eval | 2019-12-14 | 2019-12-19 |  | Run | 5
Machine | 962 Final Inspection | 2019-12-20 | 2020-01-02 |  | Rework (Imp valve, OEAII, NGSC, Pump) | 13
Machine | 962 Axle Pinion Bearing Inspection | 2020-01-03 | 2020-01-13 |  |  | 10
SW | S16 SW Update | 2020-01-14 | 2020-01-16 |  | Run & Checkout S16 | 2
NVH | 962 T3 Sound Development | 2020-01-17 | 2020-01-20 |  | Run - Sound Bldg | 3
SW | S17 SW Update | 2020-02-19 | 2020-02-21 |  |  | 2
Performance | 962 Altitude Test | 2020-04-27 | 2020-06-02 |  |  | 36
| 962 HRC AU2020 Pilot #1 (SN) | 2021-01-25 | 2021-08-30 |  |  | 154
Machine | Machine Checkout | 2021-02-08 | 2021-02-10 |  |  | 3
Performance | L5 Checkout | 2021-02-11 | 2021-02-17 |  |  | 5
SW | SW Update | 2021-02-18 | 2021-02-24 |  |  | 5
Safety and Regs | 962 HRC ISO 5010 Steering Certification | 2021-02-25 | 2021-03-19 |  |  | 22
Safety and Regs | ISO 3450 Brake Cert STP24 | 2021-03-22 | 2021-04-15 |  |  | 24
Safety and Regs | 962 HRC EMC Test | 2021-04-16 | 2021-04-27 |  |  | 77
Endurance # 1 | 962 Pilot HRC Endurance 0-500 hrs | 2021-03-03 | 2021-06-08 |  |  | 69
Endurance # 2 | 962 Pilot HRC Endurance 501-1000 hrs | 2021-06-09 | 2021-07-19 |  |  | 28
Endurance # 3 | 962 Pilot HRC Endurance 1001-1500 hrs | 2021-07-20 | 2021-08-30 |  |  | 30
| 950 LRC AU2020 Endurance Pilot #2 (SN) | 2021-02-08 | 2022-06-06 |  |  | 333
Machine | Machine Checkout | 2021-02-22 | 2021-02-24 |  |  | 13
Performance | L5 Checkout | 2021-02-25 | 2021-03-10 |  |  | 10
SW | SW Update | 2021-03-11 | 2021-03-17 |  |  | 5
Safety and Regs | 950 LRC ISO 5010 Steering Certification | 2021-03-18 | 2021-04-09 |  |  | 34
Endurance # 1 | 950 Pilot LRC Endurance 0-500 hrs | 2021-04-10 | 2021-05-24 |  |  | 71
Endurance # 2 | 950 Pilot LRC Endurance 501-1000 hrs | 2021-05-25 | 2021-07-06 |  |  | 29
Endurance # 3 | 950 Pilot LRC Endurance 1001-1500 hrs | 2021-07-07 | 2021-08-16 |  |  | 29
Endurance # 4 | 950 Pilot LRC Endurance 1501-2000 hrs | 2021-08-17 | 2021-09-27 |  |  | 29
Endurance # 5 | 950 Pilot LRC Endurance 2001-2500 hrs | 2021-09-28 | 2021-11-08 |  |  | 30
Endurance # 6 | 950 Pilot LRC Endurance 2501-3000 hrs | 2021-11-09 | 2021-12-20 |  |  | 28
Endurance # 7 | 950 Pilot LRC Endurance 3001-3500 hrs | 2021-12-21 | 2022-01-31 |  |  | 23
Endurance # 8 | 950 Pilot LRC Endurance 3501-4000 hrs | 2022-02-01 | 2022-03-14 |  |  | 30
Endurance # 9 | 950 Pilot LRC Endurance 4001-4500 hrs | 2022-03-15 | 2022-04-25 |  |  | 30
Endurance # 10 | 950 Pilot LRC Endurance 4501-5000 hrs | 2022-04-26 | 2022-06-06 |  |  | 29
Formulas:
Original Duration = DATEDIF([Start],[Finish],"d")
Original Duration = DATEDIF([Start], [Finish],"d")
Start = [Finish, row above]+1
Start = [Finish, row above]
Finish = [Start]+[Original Duration]
Finish = [Start]+13

## Final Format
| Activity ID | Start | Finish
| 962 TB2 Machine Build #2 | 2019-01-07 | 2019-02-08
SW | S13 SW Checkout | 2019-03-07 | 2019-03-13
Machine | Machine Checkout STP64 | 2019-03-14 | 2019-03-18
Hydraulics | Steering Tuning #2 | 2019-03-19 | 2019-04-15
Hydraulics | Steering Tuning- Knotch Filter | 2019-03-19 | 2019-03-21
Hydraulics | Steering Tuning- Opr Eval Knotch Filter | 2019-03-22 | 2019-03-25
Hydraulics | Steering Tuning - Perf Tuning | 2019-03-26 | 2019-04-08
Hydraulics | Steering Tuning- Operator Eval | 2019-04-09 | 2019-04-15
Hydraulics | Failure Mode Response #1 | 2019-04-09 | 2019-05-15
SW | STP 230/289 #2 | 2019-05-16 | 2019-05-22
Transmission | XMSN Development | 2019-05-23 | 2019-06-19
SW | Implement Valve Tuning | 2019-06-20 | 2019-07-11
SW | S14 SW Update | 2019-06-07 | 2019-06-10
Performance | L5 Performance Dev/Tuning #1 | 2019-07-12 | 2019-07-25
Safety and Regs | ISO 5010 Feasibility | 2019-07-26 | 2019-08-15
Technology | Cat Detect B Radar | 2019-08-15 | 2019-08-19
CAT E | Failure Mode Response #2 | 2019-08-20 | 2019-09-19
SW | S15 SW Checkout | 2019-09-20 | 2019-10-03
SW | Implement Valve Tuning #2 | 2019-10-04 | 2019-10-17
SW | S16 SW Checkout | 2019-12-06 | 2019-12-19
Performance | L5 Performance Dev/Tuning #2 | 2020-01-02 | 2020-01-23
Safety and Regs | Stg V EMC Test | 2020-01-24 | 2020-03-02
SW | S17 SW Checkout | 2020-02-20 | 2020-03-04
SW | S17 SW Endurance - 50 Hrs | 2020-03-05 | 2020-03-08
SW | S18 SW Checkout | 2020-03-02 | 2020-03-13
SW | S19 SW Checkout | 2020-05-01 | 2020-05-14
SW | S20 SW Checkout | 2020-08-03 | 2020-08-14
SW | S20 SW Endurance - 50 Hrs | 2020-08-15 | 2020-08-18
| 950 AU2020 Testbed2 (SN) | 2019-05-07 | 2020-07-15
Machine | Machine Key On | 2019-05-07 | 2019-05-08
Machine | Ship to PPG | 2019-05-09 | 2019-05-09
SW | S13 SW Checkout | 2019-05-10 | 2019-05-23
Machine | Machine Checkout STP-64 | 2019-05-24 | 2019-05-29
Hydraulics | Implement Valve Tuning #1 | 2019-05-30 | 2019-06-19
Performance | L5 Performance Dev/Tuning #1 | 2019-06-20 | 2019-07-03
SW | S14 SW Update | 2019-06-07 | 2019-06-10
Performance | Rimpull/Response | 2019-07-05 | 2019-07-17
Cooling | STP-153 (Airflow Testing) | 2019-07-18 | 2019-07-25
Cooling | STP-155 (Water Flow Test) | 2019-07-26 | 2019-07-31
Cooling | STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT | 2019-08-01 | 2019-08-22
Engine Installation | MER Engine Install test | 2019-08-23 | 2019-09-04
Hydraulics | Hydraulic Test | 2019-09-05 | 2019-10-03
SW | S15 SW Update | 2019-09-06 | 2019-09-09
NVH | 950 Stage V Machine Sound Dev | 2019-10-04 | 2019-10-08
Performance | Cold Room Test | 2019-10-09 | 2019-12-16
SW | S16 SW Update | 2019-12-06 | 2019-12-09
Performance | L5 Performance Dev/Tuning #2 | 2020-01-02 | 2020-01-23
Engine Installation | MER #2 Engine Install Test | 2020-01-24 | 2020-02-26
Safety and Regs | Prelim ISO 5010 Steering | 2020-02-05 | 2020-03-02
SW | S17 SW Update | 2020-02-19 | 2020-02-20
Transmission | XMSN Auto Cal Dev | 2020-02-28 | 2020-04-01
Engine Installation | STP 407 Engine Installation Audit | 2020-04-02 | 2020-04-13
Transmission | XMSN Signature | 2020-04-14 | 2020-05-08
Performance | L5 Issue Resolution | 2020-05-11 | 2020-05-22
NVH | 950 Stage V Machine Sound Dev #2 | 2020-05-26 | 2020-05-28
Performance | Productivity | 2020-05-29 | 2020-06-18
| 962 Stg V Testbed3 (SN) | 2019-03-21 | 2019-05-17
Machine | PPG Machine Build | 2019-04-15 | 2019-05-17
SW | SW & Electrical Checkout | 2019-05-20 | 2019-06-10
Machine | Machine Checkout STP-64 | 2019-06-11 | 2019-06-13
Hydraulics | Hydraulic Test | 2019-06-14 | 2019-07-15
Light Fab & MER | Light Fab and Engine Install OMSA & MER Test | 2019-07-16 | 2019-08-14
SW | S14 SW Update | 2019-08-15 | 2019-08-15
Heavy Structures | OMSA Heavy Fab | 2019-08-15 | 2019-09-25
SW | S15 SW Update | 2019-09-06 | 2019-09-09
Performance | L5 Performance Dev/Tuning #1 | 2019-09-26 | 2019-10-16
ELI | Electrical Load Study & Battery Shielded Cable | 2019-11-07 | 2019-11-13
Product Support | Servicability Audit | 2019-11-25 | 2019-11-26
Safety and Regs | Safety Audit | 2019-11-27 | 2019-12-02
SW | S16 SW Update | 2019-12-06 | 2019-12-09
Safety and Regs | ISO 3450 Feasibility Checkout | 2020-01-02 | 2020-01-27
SW | S17 SW Update | 2020-02-19 | 2020-02-20
| 962 T3 HMU Testbed 4 (SN) | 2019-03-28 | 2020-04-27
Machine | Machine Update - Built in Aurora | 2019-05-01 | 2019-06-15
Machine | Machine Key On | 2019-06-16 | 2019-06-16
Machine | Ship to PPG | 2019-06-16 | 2019-06-16
Machine | Machine Checkout STP-64 | 2019-06-17 | 2019-06-17
Product Support | Servicability Audit | 2019-06-18 | 2019-06-18
NVH | 962 T3 Muffler Sound Validation | 2019-06-19 | 2019-06-19
Endurance # 1 | 962 Endurance 0-500 hrs | 2019-06-20 | 2019-06-20
SW | S14 SW Update | 2019-06-21 | 2019-06-21
Endurance # 2 | 962 Endurance 501-1000 hrs | 2019-06-22 | 2019-06-22
Endurance # 3 | 962 Endurance 1001-1500 hrs | 2019-06-23 | 2019-06-23
SW | S15 SW Update | 2019-06-24 | 2019-06-24
Endurance # 4 | 962 Endurance 1501-2000 hrs | 2019-06-25 | 2019-06-25
Engine Installation | BOSCH Fuel System Eval | 2019-06-26 | 2019-06-26
Machine | 962 Final Inspection | 2019-06-27 | 2019-07-10
Machine | 962 Axle Pinion Bearing Inspection | 2019-07-11 | 2019-07-11
SW | S16 SW Update | 2019-07-12 | 2019-07-12
NVH | 962 T3 Sound Development | 2019-07-13 | 2019-07-13
SW | S17 SW Update | 2020-02-19 | 2020-02-19
Performance | 962 Altitude Test | 2020-04-27 | 2020-04-27
| 962 HRC AU2020 Pilot #1 (SN) | 2021-01-25 | 2021-08-30
Machine | Machine Checkout | 2021-02-08 | 2021-02-10
Performance | L5 Checkout | 2021-02-11 | 2021-02-17
SW | SW Update | 2021-02-18 | 2021-02-24
Safety and Regs | ISO 5010 Steering Certification | 2021-02-25 | 2021-03-19
Safety and Regs | ISO 3450 Brake Certification | 2021-03-22 | 2021-04-15
Safety and Regs | 962 HRC EMC Test | 2021-04-16 | 2021-04-27
Endurance # 1 | 962 Pilot HRC Endurance 0-500 hrs | 2021-03-03 | 2021-06-08
Endurance # 2 | 962 Pilot HRC Endurance 501-1000 hrs | 2021-06-09 | 2021-07-19
Endurance # 3 | 962 Pilot HRC Endurance 1001-1500 hrs | 2021-07-20 | 2021-08-30
| 950 LRC AU2020 Endurance Pilot #2 (SN) | 2021-02-08 | 2022-06-06
Machine | Machine Checkout | 2021-02-22 | 2021-02-24
Performance | L5 Checkout | 2021-02-25 | 2021-03-10
SW | SW Update | 2021-03-11 | 2021-03-17
Safety and Regs | 950 LRC ISO 5010 Steering Certification | 2021-03-18 | 2021-04-09
Endurance # 1 | 950 Pilot LRC Endurance 0-500 hrs | 2021-04-10 | 2021-05-24
Endurance # 2 | 950 Pilot LRC Endurance 501-1000 hrs | 2021-05-25 | 2021-07-06
Endurance # 3 | 950 Pilot LRC Endurance 1001-1500 hrs | 2021-07-07 | 2021-08-16
Endurance # 4 | 950 Pilot LRC Endurance 1501-2000 hrs | 2021-08-17 | 2021-09-27
Endurance # 5 | 950 Pilot LRC Endurance 2001-2500 hrs | 2021-09-28 | 2021-11-08
Endurance # 6 | 950 Pilot LRC Endurance 2501-3000 hrs | 2021-11-09 | 2021-12-20
Endurance # 7 | 950 Pilot LRC Endurance 3001-3500 hrs | 2021-12-21 | 2022-01-31
Endurance # 8 | 950 Pilot LRC Endurance 3501-4000 hrs | 2022-02-01 | 2022-03-14
Endurance # 9 | 950 Pilot LRC Endurance 4001-4500 hrs | 2022-03-15 | 2022-04-25
Endurance # 10 | 950 Pilot LRC Endurance 4501-5000 hrs | 2022-04-26 | 2022-06-06
Formulas:
Start = [Finish, row above]+1
Start = [Finish, row above]
Finish = [Start]+I66
Finish = [Start]+13

## Raw
Activity ID | Activity Name | Original Duration | Start | Finish | Budgeted Total Cost | Remaining Total Cost | PDGT GMD Channel Count | Primary Resource | GPM Location
950-962 MWL AU2020 |  | 1873 | 15-Jun-15 A | 2023-01-03 | 3538031.78 | 2881745 | 1039
Project Management |  | 745 | 02-Jan-18 A | 2020-12-23 | 627.48 | 406.4 | 0
950/962 AU20-19595 | Project Management 2018 | 248 | 02-Jan-18 A | 21-Dec-18 A | 207.48 | 0 |  | guppyam.Guppy Amy M | PPG
950/962 AU20-24075 | Project Management 2019 | 248 | 02-Jan-19 A | 2019-12-23 | 210 | 196.4 |  | guppyam.Guppy Amy M | PPG
950/962 AU20-24080 | Project Management 2020 | 249 | 02-Jan-20* | 2020-12-23 | 210 | 210 |  | guppyam.Guppy Amy M | PPG
Management Support |  | 0 | 15-Jun-15 A | 15-Jun-15 A | 0 | 0 | 0
950/962 AU20-1160 | Start PM | 0 | 15-Jun-15 A |  | 0 | 0 |  | guppyam.Guppy Amy M | PPG
Sound Work |  | 216 | 2019-02-15 | 2019-12-20 | 15776 | 15776 | 0
950/962 AU20-26860 | 950 Plate Frame Sound VPD Optimization | 62 | 15-Feb-19* | 2019-05-13 | 13920 | 13920 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-26890 | Sound Validation Engineer Support 950XE - 2019 | 206 | 01-Mar-19* | 2019-12-20 | 1856 | 1856 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
Key Project Milestones |  | 1756 | 30-Nov-15 A | 2023-01-03 | 0 | 0 | 0
950/962 AU20-1100 | Start Project | 0 | 30-Nov-15 A |  | 0 | 0 |  | GREENCD2.Green Christopher D | PPG
950/962 AU20-1040 | NPI Launch | 0 | 16-Dec-15 A |  | 0 | 0 |  | GREENCD2.Green Christopher D | PPG
950/962 AU20-1110 | Testbed Build | 0 | 01-Jun-16 A |  | 0 | 0 |  | GREENCD2.Green Christopher D | PPG
950/962 AU20-1120 | Prototype Build | 0 | 01-Nov-16 A |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-20150 | NPI Gate 1 | 0 | 13-Jun-17 A |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-1320 | Protoype Design Freeze | 0 | 24-Jul-17 A |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-20280 | NPI Gate 2/3 | 0 | 10-Aug-18 A |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-1330 | Pilot Design Freeze | 0 | 13-Mar-20* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-20990 | NPI Gate 4/5 for 950 | 0 | 11-Sep-20* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-21010 | NPI Gate 5.5 for 950 | 0 | 16-Oct-20* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-1130 | Pilot Build | 0 | 16-Oct-20* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-1020 | NPI Gate 6 for 950 | 0 | 14-Jan-22* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-1140 | Production Build | 0 | 11-Feb-22* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-1170 | Finish Project | 0 |  | 2023-01-03 | 0 | 0 |  | shahvb.Shah Viresh B | PPG
950/962 AU20-1060 | NPI Gate 7 | 0 | 03-Jan-23* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
SW Milestones |  | 1341 | 29-Apr-16 A | 2021-09-21 | 0 | 0 | 0
950/962 AU20-11135 | Receive SW Release A | 0 | 29-Apr-16 A |  | 0 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-11145 | Receive TESS 04 | 0 | 11-Jan-17 A |  | 0 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-20170 | Steering DV3.2 SW Release | 0 | 10-Mar-17 A |  | 0 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-20750 | Receive DV3.3 SW Release | 0 | 30-Mar-17 A |  | 0 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-11155 | Receive S05 | 0 | 04-Apr-17 A |  | 0 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-20180 | D6C8 Display Release | 0 | 15-May-17 A |  | 0 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-20160 | Steering DV4 SW Release | 0 | 17-May-17 A |  | 0 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-19185 | Receive S06 | 0 | 19-Jun-17 A |  | 0 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-19205 | Receive S07 | 0 | 22-Aug-17 A |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-19225 | Receive S08 | 0 | 01-Nov-17 A |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-21080 | Receive S13 | 0 | 07-Mar-19* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-21090 | Receive S14 | 0 | 07-Jun-19* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-21100 | Receive S15 | 0 | 06-Sep-19* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-21110 | Receive S16 | 0 | 06-Dec-19* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-21120 | Receive S17 | 0 | 19-Feb-20* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-21130 | Receive S18 | 0 | 02-Mar-20* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-21140 | Receive S19 | 0 | 01-May-20* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU20-21150 | Receive S20 | 0 | 03-Aug-20* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
950/962 AU201000 | Receive Prod SW | 0 | 21-Sep-21* |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
Bundle Planned Work |  | 362 | 15-Jul-16 A | 26-Sep-17 A | 195818.15 | 0 | 16
950/962 Platform |  | 362 | 15-Jul-16 A | 26-Sep-17 A | 195818.15 | 0 | 16
White Noise Alarm Eval |  | 42 | 15-Jul-16 A | 04-Nov-16 A | 53220.15 | 0 | 0
BDL 18-2445 | Run | 3 | 15-Jul-16 A | 18-Jul-16 A | 19681.59 | 0 |  | MylavS1.Mylavarapu Sandeep | PPG.Sound.Bld
BDL 18-2455 | Report | 30 | 01-Aug-16 A | 04-Nov-16 A | 33538.56 | 0 |  | MylavS1.Mylavarapu Sandeep | PPG
Contingency |  | 165 | 01-May-17 A | 31-Aug-17 A | 120000 | 0 | 0
950/962 AU20-19990 | Contingency | 165 | 01-May-17 A | 31-Aug-17 A | 120000 | 0 |  | powelaw.Powell Austin W | PPG
CR 950 PF Aux Attachment (EMB00247) |  | 82 | 06-Jun-17 A | 26-Sep-17 A | 22598 | 0 | 16
BDL AU20-10480 | Setup | 4 | 06-Jun-17 A | 20-Jun-17 A | 7827.2 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10490 | Instrument | 2 | 19-Jul-17 A | 21-Jul-17 A | 3126 | 0 | 16 | powelaw.Powell Austin W | PPG
950/962 AU20-10511 | LOE: Instrumentation Charges - 16c | 5 | 21-Jul-17 A | 26-Sep-17 A | 1490 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10500 | Run | 4 | 24-Jul-17 A | 25-Sep-17 A | 7840 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20--10521 | Teardown | 1 | 26-Sep-17 A | 26-Sep-17 A | 2314.8 | 0 |  | powelaw.Powell Austin W | PPG
Testbed 2 Phase |  | 892 | 23-Jan-17 A | 2020-08-18 | 2386352.98 | 1926105.43 | 980
962 AU2020 Testbed1 (WL900100) |  | 892 | 23-Jan-17 A | 2020-08-18 | 748449.22 | 288201.67 | 183
LOE |  | 872 | 20-Feb-17 A | 2020-08-18 | 0 | 0 | 0
950/962 AU20-1340 | Start Testing 950M Steering Testbed | 0 | 20-Feb-17 A |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-1350 | LOE: 950M Steering Testbed1 | 280 | 20-Feb-17 A | 2020-08-18 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-1370 | Reports Complete 950M Steering Testbed1 | 0 |  | 2020-03-02 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-1360 | Testing Complete 950M Steering Testbed1 | 0 |  | 2020-08-18 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
Machine Build |  | 40 | 23-Jan-17 A | 23-Mar-17 A | 58226 | 0 | 0
950/962 AU20-2550 | Plan | 25 | 23-Jan-17 A | 24-Feb-17 A | 32150 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-2560 | Assemble Machine | 20 | 20-Feb-17 A | 23-Mar-17 A | 26076 | 0 |  | powelaw.Powell Austin W | PPG
STP 230/289 |  | 26 | 27-Feb-17 A | 21-Apr-17 A | 36880 | 0 | 0
950/962 AU20-2570 | Plan | 20 | 27-Feb-17 A | 24-Mar-17 A | 22040 | 0 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU20-2580 | Run | 8 | 27-Mar-17 A | 21-Apr-17 A | 14840 | 0 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
G10 Gauge Display Update |  | 2 | 05-Apr-17 A | 06-Apr-17 A | 4151.44 | 0 | 0
950/962 AU20-20610 | Setup | 1 | 05-Apr-17 A | 05-Apr-17 A | 2359.44 | 0 |  | HagueME.Hague Evan E | PPG
950/962 AU20-20620 | Run - Checkout | 1 | 06-Apr-17 A | 06-Apr-17 A | 1792 | 0 |  | HagueME.Hague Evan E | PPG
S05 SW Updates |  | 5 | 07-Apr-17 A | 13-Apr-17 A | 6660 | 0 | 0
950/962 AU20-20630 | Run & Checkout S05 | 5 | 07-Apr-17 A | 13-Apr-17 A | 6660 | 0 |  | HagueME.Hague Evan E | PPG
Cab Pressurization Test |  | 1 | 27-Apr-17 A | 27-Apr-17 A | 460 | 0 | 0
950/962 AU20-20670 | Run | 1 | 27-Apr-17 A | 27-Apr-17 A | 460 | 0 |  | powelaw.Powell Austin W | PPG
Machine Safety/Servicability Audit |  | 3 | 28-Apr-17 A | 01-May-17 A | 4462.32 | 0 | 0
950/962 AU20-19800 | Setup | 3 | 28-Apr-17 A | 01-May-17 A | 4462.32 | 0 |  | powelaw.Powell Austin W | PPG
Machine Checkout STP-64 |  | 30 | 27-Mar-17 A | 26-Apr-17 A | 25696.72 | 0 | 0
950/962 AU20-14400 | Plan | 10 | 27-Mar-17 A | 26-Apr-17 A | 20935 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-14405 | Setup | 1 | 26-Apr-17 A | 26-Apr-17 A | 973.72 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-14410 | Run | 1 | 26-Apr-17 A | 26-Apr-17 A | 3788 | 0 |  | powelaw.Powell Austin W | PPG
Machine Checkout STP-64 #2 |  | 10 | 22-May-17 A | 07-Jun-17 A | 20935 | 0 | 0
950/962 AU20-23610 | Plan | 10 | 22-May-17 A | 07-Jun-17 A | 20935 | 0 |  | powelaw.Powell Austin W | PPG
Steering Tuning #1 |  | 38 | 19-Jul-17 A | 15-Sep-17 A | 40890 | 0 | 0
950/962 AU20-23690 | Run | 38 | 19-Jul-17 A | 15-Sep-17 A | 40890 | 0 |  | powelaw.Powell Austin W | PPG
S07 SW Update |  | 5 | 25-Aug-17 A | 30-Aug-17 A | 2300 | 0 | 0
950/962 AU20-20640 | Run & Checkout S07 | 5 | 25-Aug-17 A | 30-Aug-17 A | 2300 | 0 |  | egantr.Egan Thomas R | PPG
Steering Operator Eval |  | 1 | 19-Sep-17 A | 19-Sep-17 A | 1673.75 | 0 | 0
950/962 AU20-2590 | Run | 1 | 19-Sep-17 A | 19-Sep-17 A | 1673.75 | 0 |  | powelaw.Powell Austin W | PPG
DV1 Install |  | 1 | 25-Sep-17 A | 25-Sep-17 A | 920 | 0 | 0
950/962 AU20-20680 | Run | 1 | 25-Sep-17 A | 25-Sep-17 A | 920 | 0 |  | egantr.Egan Thomas R | PPG
962 Next Gen Service Center OMSA/MER Light Fabs |  | 239 | 22-May-17 A | 22-Dec-17 A | 157441.61 | 0 | 151
950/962 AU20-12065 | Planning & Procurement | 60 | 22-May-17 A | 20-Sep-17 A | 8586.67 | 0 |  | 01-55710-400.TSD557MGT - SEC10 RES400 LARGE STRUCTURES - Management Labor-Program | PPG
950/962 AU20-12075 | SGL Strain Gage Lab - Instrument Parts | 3 | 18-Sep-17 A | 20-Sep-17 A | 5305 | 0 |  | 01-55710-400.TSD557MGT - SEC10 RES400 LARGE STRUCTURES - Management Labor-Program | PPG
950/962 AU20-12085 | Instrument - Setup Bay | 15 | 25-Sep-17 A | 20-Oct-17 A | 45000 | 0 | 151 | 01-55710-400.TSD557MGT - SEC10 RES400 LARGE STRUCTURES - Management Labor-Program | PPG
950/962 AU20-12135 | Setup - Shop Support Work | 4 | 27-Sep-17 A | 11-Oct-17 A | 11776.43 | 0 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-12145 | Field Prep for OMSA | 2 | 19-Oct-17 A | 20-Oct-17 A | 2203.33 | 0 |  | MorseMP.Morse Mark P | PPG
950/962 AU20-12155 | LOE: Instrumentation Charges - 151c | 8 | 20-Oct-17 A | 27-Oct-17 A | 23728.18 | 0 |  | MorseMP.Morse Mark P | PPG
950/962 AU20-12095 | Run | 7 | 23-Oct-17 A | 26-Oct-17 A | 30842 | 0 |  | MorseMP.Morse Mark P | PPG
950/962 AU20-12105 | Teardown | 2 | 27-Oct-17 A | 30-Oct-17 A | 11740 | 0 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-12115 | Preliminary Analysis/Reporting | 5 | 30-Oct-17 A | 03-Nov-17 A | 5060 | 0 |  | MorseMP.Morse Mark P | PPG
950/962 AU20-12125 | Final Analysis/Reporting | 60 | 06-Nov-17 A | 22-Dec-17 A | 13200 | 0 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
962 TB NVH Sound Eval |  | 38 | 02-Nov-17 A | 08-Nov-18 A | 40579.8 | 0 | 0
950/962 AU20-19365 | Run - Sound Bldg | 7 | 02-Nov-17 A | 13-Nov-17 A | 33390 | 0 |  | bobchij.Bobchik Joe P | PPG.Sound.Bld
950/962 AU20-19375 | Report | 20 | 27-Nov-17 A | 08-Nov-18 A | 7189.8 | 0 |  | bobchij.Bobchik Joe P | PPG
S08 SW Update |  | 5 | 27-Nov-17 A | 28-Nov-17 A | 2300 | 0 | 0
950/962 AU20-20660 | Run & Checkout S08 | 5 | 27-Nov-17 A | 28-Nov-17 A | 2300 | 0 |  | egantr.Egan Thomas R | PPG
L5 Performance Tuning |  | 16 | 13-Nov-17 A | 30-Nov-17 A | 2425.5 | 0 | 0
950/962 AU20-2680 | Plan | 10 | 13-Nov-17 A | 28-Nov-17 A | 1150 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-2710 | Run | 2 | 29-Nov-17 A | 30-Nov-17 A | 1275.5 | 0 |  | powelaw.Powell Austin W | PPG
Instrument Cluster Operator Eval |  | 6 | 27-Nov-17 A | 04-Dec-17 A | 2406.25 | 0 | 0
950/962 AU20-24000 | Plan | 5 | 27-Nov-17 A | 01-Dec-17 A | 920 | 0 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU20-24010 | Run | 1 | 04-Dec-17 A | 04-Dec-17 A | 1486.25 | 0 |  | 01-88180-242.TSD881HRY - SEC80 RES242 PPG TEST OPERATIONS - Vehicle Operator-ABC | PPG
962 TB2 Machine Build #2 |  | 28 | 17-Dec-18 A | 2019-02-08 | 19494 | 9090 | 0
950/962 AU20-21170 | Plan | 10 | 17-Dec-18 A | 08-Jan-19 A | 1314 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-21180 | Setup - (Impl Valve, OEAII, NGSC, Pump) | 20 | 07-Jan-19 A | 2019-02-08 | 18180 | 9090 |  | powelaw.Powell Austin W | PPG
S13 SW Checkout |  | 5 | 2019-03-07 | 2019-03-13 | 2442.5 | 2442.5 | 0
950/962 AU20-21970 | Run - Steering Checkout | 5 | 2019-03-07 | 2019-03-13 | 2442.5 | 2442.5 |  | egantr.Egan Thomas R | PPG
Machine Checkout STP64 |  | 8 | 2019-03-07 | 2019-03-18 | 5459 | 5459 | 0
950/962 AU20-24090 | Plan | 5 | 2019-03-07 | 2019-03-13 | 1635 | 1635 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24100 | Run | 3 | 2019-03-14 | 2019-03-18 | 3824 | 3824 |  | powelaw.Powell Austin W | PPG
Steering Tuning #2 |  | 20 | 2019-03-19 | 2019-04-15 | 10550 | 10550 | 0
950/962 AU20-25380 | Run - Knotch Filter | 3 | 2019-03-19 | 2019-03-21 | 910.5 | 910.5 |  | SULLIPW.Sullivan Patrick W | PPG
950/962 AU20-25390 | Run - Operator Eval Knotch Filter | 2 | 2019-03-22 | 2019-03-25 | 1887 | 1887 |  | SULLIPW.Sullivan Patrick W | PPG
950/962 AU20-25400 | Run - Performance Tuning | 10 | 2019-03-26 | 2019-04-08 | 3035 | 3035 |  | SULLIPW.Sullivan Patrick W | PPG
950/962 AU20-25410 | Run - Operator Eval Peformance Tuning | 5 | 2019-04-09 | 2019-04-15 | 4717.5 | 4717.5 |  | SULLIPW.Sullivan Patrick W | PPG
Failure Mode Response #1 |  | 27 | 2019-04-09 | 2019-05-15 | 46167 | 46167 | 0
950/962 AU20-25360 | Plan | 5 | 2019-04-09 | 2019-04-15 | 3270 | 3270 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU20-25370 | Setup | 1 | 2019-04-16 | 2019-04-16 | 1730 | 1730 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU20-25340 | Run | 20 | 2019-04-17 | 2019-05-14 | 40200 | 40200 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU20-25350 | Teardown | 1 | 2019-05-15 | 2019-05-15 | 967 | 967 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
STP 230/289 #2 |  | 15 | 2019-05-02 | 2019-05-22 | 6750 | 6750 | 0
950/962 AU20-23920 | Plan | 10 | 2019-05-02 | 2019-05-15 | 2180 | 2180 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU20-23930 | Run | 5 | 2019-05-16 | 2019-05-22 | 4570 | 4570 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
XMSN Development |  | 19 | 2019-05-23 | 2019-06-19 | 22656 | 22656 | 16
950/962 AU20-21810 | Setup | 1 | 2019-05-23 | 2019-05-23 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-21820 | Instrument | 2 | 2019-05-24 | 2019-05-28 | 3618 | 3618 | 16 | powelaw.Powell Austin W | PPG
950/962 AU20-21330 | Run | 15 | 2019-05-29 | 2019-06-18 | 16995 | 16995 |  | powelaw.Powell Austin W | PPG
950/962 AU20-21850 | Teardown | 1 | 2019-06-19 | 2019-06-19 | 967 | 967 |  | powelaw.Powell Austin W | PPG
Implement Valve Tuning |  | 25 | 2019-06-06 | 2019-07-11 | 5082.5 | 5082.5 | 0
950/962 AU20-14790 | Plan | 10 | 2019-06-06 | 2019-06-19 | 1090 | 1090 |  | powelaw.Powell Austin W | PPG
950/962 AU20-14800 | Run (Cat Electronics - Steve Queen) | 15 | 2019-06-20 | 2019-07-11 | 3992.5 | 3992.5 |  | powelaw.Powell Austin W | PPG
S14 SW Update |  | 2 | 2019-06-07 | 2019-06-10 | 1744 | 1744 | 0
950/962 AU20-26880 | Run & Checkout S14 | 2 | 2019-06-07 | 2019-06-10 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
L5 Performance Dev/Tuning #1 |  | 10 | 2019-07-12 | 2019-07-25 | 10640 | 10640 | 0
950/962 AU20-21790 | Run | 10 | 2019-07-12 | 2019-07-25 | 10640 | 10640 |  | powelaw.Powell Austin W | PPG
ISO 5010 Feasibility |  | 568 | 08-May-17 A | 2019-08-16 | 72025.83 | 30590.67 | 16
950/962 AU20-19950 | Plan | 10 | 08-May-17 A | 14-Jun-17 A | 1150 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23620 | Setup | 1 | 07-Jun-17 A | 07-Jun-17 A | 973.72 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23630 | Run | 1 | 13-Jun-17 A | 13-Jun-17 A | 2044 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-19960 | Setup | 1 | 14-Jun-17 A | 14-Jun-17 A | 2407.44 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-19970 | Run - Driver Performance | 28 | 15-Jun-17 A | 17-Jul-17 A | 34860 | 0 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25420 | Plan | 15 | 2019-07-05 | 2019-07-25 | 4905 | 4905 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-25430 | Setup | 4 | 2019-07-26 | 2019-07-31 | 8636 | 8636 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-25440 | Instrument | 3 | 2019-08-01 | 2019-08-05 | 3078 | 3078 | 16 | powelaw.Powell Austin W | PPG
950/962 AU20-25450 | Run | 5 | 2019-08-06 | 2019-08-12 | 10511.67 | 10511.67 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-25460 | Teardown | 2 | 2019-08-13 | 2019-08-14 | 1716 | 1716 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25470 | Analyze | 2 | 2019-08-15 | 2019-08-16 | 1744 | 1744 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
Cat Detect B Radar |  | 3 | 2019-08-15 | 2019-08-19 | 2616 | 2616 | 0
950/962 AU20-24020 | Run | 3 | 2019-08-15 | 2019-08-19 | 2616 | 2616 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
Failure Mode Response #2 |  | 27 | 2019-08-13 | 2019-09-19 | 46167 | 46167 | 0
950/962 AU201185 | Plan | 5 | 2019-08-13 | 2019-08-19 | 3270 | 3270 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU201190 | Setup | 1 | 2019-08-20 | 2019-08-20 | 1730 | 1730 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU201065 | Run | 20 | 2019-08-21 | 2019-09-18 | 40200 | 40200 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
950/962 AU201180 | Teardown | 1 | 2019-09-19 | 2019-09-19 | 967 | 967 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
S15 SW Checkout |  | 10 | 2019-09-20 | 2019-10-03 | 4885 | 4885 | 0
950/962 AU20-22010 | Run & Checkout S15 | 10 | 2019-09-20 | 2019-10-03 | 4885 | 4885 |  | egantr.Egan Thomas R | PPG
Implement Valve Tuning #2 |  | 20 | 2019-09-20 | 2019-10-17 | 9565 | 9565 | 0
950/962 AU20-21300 | Plan | 10 | 2019-09-20 | 2019-10-03 | 3270 | 3270 |  | powelaw.Powell Austin W | PPG
950/962 AU20-21800 | Run | 10 | 04-Oct-19* | 2019-10-17 | 6295 | 6295 |  | powelaw.Powell Austin W | PPG
S16 SW Checkout |  | 10 | 2019-12-06 | 2019-12-19 | 4885 | 4885 | 0
950/962 AU20-22030 | Run & Checkout S16 | 10 | 2019-12-06 | 2019-12-19 | 4885 | 4885 |  | egantr.Egan Thomas R | PPG
L5 Performance Dev/Tuning #2 |  | 15 | 2020-01-02 | 2020-01-23 | 15960 | 15960 | 0
950/962 AU20-24110 | Run | 15 | 02-Jan-20* | 2020-01-23 | 15960 | 15960 |  | powelaw.Powell Austin W | PPG
Stg V EMC Test |  | 77 | 2019-11-01 | 2020-03-02 | 23196 | 23196 | 0
950/962 AU20-15310 | Plan | 50 | 2019-11-01 | 2020-01-23 | 4600 | 4600 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
950/962 AU20-15320 | Setup | 2 | 2020-01-24 | 2020-01-27 | 2152 | 2152 |  | powelaw.Powell Austin W | PPG
950/962 AU20-15330 | Run | 5 | 2020-01-28 | 2020-02-03 | 12810 | 12810 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
950/962 AU20-15340 | Teardown | 1 | 2020-02-04 | 2020-02-04 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-15350 | Report | 20 | 2020-02-04 | 2020-03-02 | 2558 | 2558 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
S17 SW Checkout |  | 10 | 2020-02-20 | 2020-03-04 | 4885 | 4885 | 0
950/962 AU20-22050 | Run & Checkout S17 | 10 | 20-Feb-20* | 2020-03-04 | 4885 | 4885 |  | egantr.Egan Thomas R | PPG
S17 SW Endurance - 50 Hrs |  | 4 | 2020-03-05 | 2020-03-08 | 5108 | 5108 | 0
950/962 AU20-22060 | Run Endurance | 4 | 2020-03-05 | 2020-03-08 | 5108 | 5108 |  | powelaw.Powell Austin W | PPG
S18 SW Checkout |  | 10 | 2020-03-02 | 2020-03-13 | 4885 | 4885 | 0
950/962 AU20-22070 | Run & Checkout S18 | 10 | 2020-03-02 | 2020-03-13 | 4885 | 4885 |  | egantr.Egan Thomas R | PPG
S19 SW Checkout |  | 10 | 2020-05-01 | 2020-05-14 | 4885 | 4885 | 0
950/962 AU20-22090 | Run & Checkout S19 | 10 | 2020-05-01 | 2020-05-14 | 4885 | 4885 |  | egantr.Egan Thomas R | PPG
S20 SW Checkout |  | 10 | 2020-08-03 | 2020-08-14 | 4885 | 4885 | 0
950/962 AU20-22110 | Run & Checkout S20 | 10 | 2020-08-03 | 2020-08-14 | 4885 | 4885 |  | egantr.Egan Thomas R | PPG
S20 SW Endurance - 50 Hrs |  | 4 | 2020-08-15 | 2020-08-18 | 5108 | 5108 | 0
950/962 AU20-22120 | Run Endurance | 4 | 2020-08-15 | 2020-08-18 | 5108 | 5108 |  | powelaw.Powell Austin W | PPG
950 AU2020 Testbed2 (SN) |  | 297 | 2019-05-07 | 2020-07-15 | 823045.63 | 823045.63 | 442
LOE |  | 294 | 2019-05-10 | 2020-07-15 | 0 | 0 | 0
950/962 AU20-3670 | Start Testing 950 TB2 | 0 | 2019-05-10 |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-3680 | LOE: 950 TB2 | 276 | 2019-05-10 | 2020-06-18 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-3690 | Testing Complete 950 TB2 | 0 |  | 2020-06-18 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-3700 | Reports Complete 950 TB2 | 0 |  | 2020-07-15 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
Machine Update - Built in Aurora |  | 3 | 2019-05-07 | 2019-05-09 | 1853 | 1853 | 0
950/962 AU201010 | Machine Key On | 2 | 07-May-19* | 2019-05-08 | 1744 | 1744 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | Field
950/962 AU201005 | Ship to PPG | 1 | 2019-05-09 | 2019-05-09 | 109 | 109 |  | layjd.Lay Joe D | Field
S13 SW Checkout |  | 10 | 2019-05-10 | 2019-05-23 | 4885 | 4885 | 0
950/962 AU20-24070 | Run - Steering Checkout | 10 | 2019-05-10 | 2019-05-23 | 4885 | 4885 |  | egantr.Egan Thomas R | PPG
Machine Checkout STP-64 |  | 13 | 2019-05-10 | 2019-05-29 | 7094 | 7094 | 0
950/962 AU20-14385 | Plan | 10 | 2019-05-10 | 2019-05-23 | 3270 | 3270 |  | powelaw.Powell Austin W | PPG
950/962 AU20-14395 | Run | 3 | 2019-05-24 | 2019-05-29 | 3824 | 3824 |  | powelaw.Powell Austin W | PPG
Implement Valve Tuning #1 |  | 25 | 2019-05-15 | 2019-06-19 | 10532.5 | 10532.5 | 0
950/962 AU20-24120 | Plan | 10 | 2019-05-15 | 2019-05-29 | 1090 | 1090 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24130 | Run | 15 | 2019-05-30 | 2019-06-19 | 9442.5 | 9442.5 |  | powelaw.Powell Austin W | PPG
L5 Performance Dev/Tuning #1 |  | 10 | 2019-06-20 | 2019-07-03 | 10640 | 10640 | 0
950/962 AU20-24140 | Run | 10 | 2019-06-20 | 2019-07-03 | 10640 | 10640 |  | powelaw.Powell Austin W | PPG
S14 SW Update |  | 2 | 2019-06-07 | 2019-06-10 | 1744 | 1744 | 0
950/962AU20-1000 | Run & Checkout S14 | 2 | 2019-06-07 | 2019-06-10 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
Rimpull/Response |  | 53 | 2019-05-31 | 2019-08-14 | 30834 | 30834 | 24
950/962 AU20-22420 | Plan | 20 | 2019-05-31 | 2019-06-27 | 4360 | 4360 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22470 | SGL Strain Gage Lab - Instrument Parts | 4 | 2019-06-28 | 2019-07-03 | 3924 | 3924 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22430 | Setup | 2 | 2019-07-05 | 2019-07-08 | 2996 | 2996 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22440 | Instrument | 2 | 2019-07-09 | 2019-07-10 | 4352 | 4352 | 24 | powelaw.Powell Austin W | PPG
950/962 AU20-22410 | Run | 4 | 2019-07-11 | 2019-07-16 | 4984 | 4984 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22450 | Teardown | 1 | 2019-07-17 | 2019-07-17 | 1498 | 1498 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22460 | Analyze | 5 | 2019-07-18 | 2019-07-24 | 2180 | 2180 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22480 | Report | 15 | 2019-07-25 | 2019-08-14 | 6540 | 6540 |  | powelaw.Powell Austin W | PPG
STP-153 (Airflow Testing) |  | 21 | 2019-07-03 | 2019-08-01 | 12543 | 12543 | 0
950/962 AU20-24150 | Plan | 10 | 2019-07-03 | 2019-07-17 | 1160 | 1160 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-24160 | Setup/Run | 5 | 2019-07-18 | 2019-07-24 | 9830 | 9830 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-24210 | Teardown | 1 | 2019-07-25 | 2019-07-25 | 625 | 625 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-24170 | Report | 6 | 2019-07-25 | 2019-08-01 | 928 | 928 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
STP-155 (Water Flow Test) |  | 19 | 2019-07-12 | 2019-08-07 | 7093 | 7093 | 0
950/962 AU20-24180 | Plan | 10 | 2019-07-12 | 2019-07-25 | 1160 | 1160 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-24190 | Setup/Run | 3 | 2019-07-26 | 2019-07-30 | 4380 | 4380 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-24220 | Teardown | 1 | 2019-07-31 | 2019-07-31 | 625 | 625 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-24200 | Report | 6 | 2019-07-31 | 2019-08-07 | 928 | 928 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT |  | 104 | 2019-05-07 | 2019-10-02 | 75983.3 | 75983.3 | 112
950/962 AU20-22720 | Plan | 60 | 2019-05-07 | 2019-07-31 | 3375 | 3375 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-22730 | Setup | 3 | 2019-08-01 | 2019-08-05 | 5358 | 5358 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-22790 | Instrument | 6 | 2019-08-06 | 2019-08-13 | 29060 | 29060 | 112 | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-22780 | Prep Field - MDC | 3 | 2019-08-09 | 2019-08-13 | 2029 | 2029 |  | Field_Prep1.Field Prep 1 | PPG
950/962 AU20-22740 | Run | 5 | 2019-08-14 | 2019-08-20 | 21677.5 | 21677.5 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-22750 | Teardown | 2 | 2019-08-21 | 2019-08-22 | 2862 | 2862 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
950/962 AU20-22760 | Report (Class 3) | 30 | 2019-08-21 | 2019-10-02 | 11621.8 | 11621.8 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
MER Engine Install test |  | 134 | 2019-05-24 | 2019-12-04 | 53518 | 53518 | 48
950/962 AU20-24230 | Planning & Procurement | 60 | 2019-05-24 | 2019-08-19 | 4723.33 | 4723.33 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24240 | SGL Strain Gage Lab - Instrument Parts | 3 | 2019-08-20 | 2019-08-22 | 3161 | 3161 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24300 | Setup - Shop Support Work | 2 | 2019-08-23 | 2019-08-26 | 3314.67 | 3314.67 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-24250 | Instrument - Setup Bay | 3 | 2019-08-27 | 2019-08-29 | 9135 | 9135 | 48 | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24310 | Field Prep for OMSA | 2 | 2019-08-28 | 2019-08-29 | 16216 | 16216 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24260 | Run | 2 | 2019-08-30 | 2019-09-03 | 4120 | 4120 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24270 | Teardown | 1 | 2019-09-04 | 2019-09-04 | 1948 | 1948 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-24280 | Preliminary Analysis/Reporting | 3 | 2019-09-04 | 2019-09-06 | 2180 | 2180 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24290 | TIC Report | 61 | 2019-09-09 | 2019-12-04 | 8720 | 8720 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
Hydraulic Test |  | 58 | 2019-08-21 | 2019-11-11 | 65318 | 65318 | 32
950/962 AU20-22180 | Plan | 10 | 2019-08-21 | 2019-09-04 | 4360 | 4360 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-22190 | Setup | 5 | 2019-09-05 | 2019-09-11 | 8650 | 8650 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-22200 | Instrument | 3 | 2019-09-12 | 2019-09-16 | 9477 | 9477 | 32 | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-22170 | Run | 10 | 2019-09-17 | 2019-09-30 | 25760 | 25760 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-22210 | Teardown | 3 | 2019-10-01 | 2019-10-03 | 4536 | 4536 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-22220 | Report | 30 | 2019-10-01 | 2019-11-11 | 12535 | 12535 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
S15 SW Update |  | 2 | 2019-09-06 | 2019-09-09 | 1744 | 1744 | 0
950/962AU20-1010 | Run & Checkout S15 | 2 | 2019-09-06 | 2019-09-09 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
950 Stage V Machine Sound Dev |  | 16 | 2019-10-04 | 2019-10-25 | 16062 | 16062 | 0
950/962 AU20-21220 | Run - Sound Bldg | 3 | 2019-10-04 | 2019-10-08 | 13278 | 13278 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG.Sound.Bld
950/962 AU20-21230 | Report | 13 | 2019-10-09 | 2019-10-25 | 2784 | 2784 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
Cold Room Test |  | 137 | 2019-07-16 | 2020-02-06 | 249421 | 249421 | 90
950/962 AU20-22550 | Plan | 60 | 2019-07-16 | 2019-10-08 | 10900 | 10900 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-22560 | Setup | 5 | 2019-10-09 | 2019-10-15 | 6470 | 6470 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-22570 | Instrument | 5 | 2019-10-16 | 2019-10-22 | 16550 | 16550 | 90 | powelaw.Powell Austin W | PPG
950/962 AU20-22610 | Ship to test site | 1 | 2019-10-23 | 2019-10-23 | 554.5 | 554.5 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22640 | Machine Install | 2 | 2019-10-24 | 2019-10-25 | 2116 | 2116 |  | powelaw.Powell Austin W | TC-L
950/962 AU20-22580 | Run | 30 | 2019-10-28 | 2019-12-10 | 194460 | 194460 |  | powelaw.Powell Austin W | TC-L.I6Val.UNASSIGN
950/962 AU20-22650 | Machine Removal | 1 | 2019-12-11 | 2019-12-11 | 1058 | 1058 |  | powelaw.Powell Austin W | TC-L.I6Val.UNASSIGN
950/962 AU20-22620 | Ship from test site | 1 | 2019-12-12 | 2019-12-12 | 554.5 | 554.5 |  | powelaw.Powell Austin W | TC-L
950/962 AU20-22590 | Teardown | 2 | 2019-12-13 | 2019-12-16 | 2588 | 2588 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-22600 | Report | 30 | 2019-12-17 | 2020-02-06 | 14170 | 14170 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
S16 SW Update |  | 2 | 2019-12-06 | 2019-12-09 | 1744 | 1744 | 0
950/962AU20-1020 | Run & Checkout S16 | 2 | 2019-12-06 | 2019-12-09 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
L5 Performance Dev/Tuning #2 |  | 15 | 2020-01-02 | 2020-01-23 | 15960 | 15960 | 0
950/962 AU20-24320 | Run | 15 | 02-Jan-20* | 2020-01-23 | 15960 | 15960 |  | powelaw.Powell Austin W | PPG
MER #2 |  | 134 | 2019-10-15 | 2020-05-01 | 50902 | 50902 | 32
950/962 AU20-25500 | Planning & Procurement | 60 | 2019-10-15 | 2020-01-17 | 4723.33 | 4723.33 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-25510 | SGL Strain Gage Lab - Instrument Parts | 3 | 2020-01-21 | 2020-01-23 | 3161 | 3161 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-25570 | Setup - Shop Support Work | 2 | 2020-01-24 | 2020-01-27 | 3314.67 | 3314.67 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-25520 | Instrument - Setup Bay | 3 | 2020-01-28 | 2020-01-30 | 6519 | 6519 | 32 | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-25580 | Field Prep for OMSA | 2 | 2020-01-29 | 2020-01-30 | 16216 | 16216 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-25530 | Run | 2 | 2020-01-31 | 2020-02-03 | 4120 | 4120 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-25540 | Teardown | 1 | 2020-02-04 | 2020-02-04 | 1948 | 1948 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-25550 | Preliminary Analysis/Reporting | 3 | 2020-02-04 | 2020-02-06 | 2180 | 2180 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-25560 | TIC Report | 61 | 2020-02-07 | 2020-05-01 | 8720 | 8720 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
Prelim ISO 5010 Steering |  | 34 | 2020-01-14 | 2020-03-02 | 54748.33 | 54748.33 | 16
950/962 AU20-24340 | Plan | 15 | 2020-01-14 | 2020-02-04 | 4905 | 4905 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-24350 | Setup | 4 | 2020-02-05 | 2020-02-10 | 10732 | 10732 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-24360 | Instrument | 2 | 2020-02-11 | 2020-02-12 | 2964 | 2964 | 16 | powelaw.Powell Austin W | PPG
950/962 AU20-24330 | Run | 10 | 2020-02-13 | 2020-02-26 | 32033.33 | 32033.33 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-24370 | Teardown | 1 | 2020-02-27 | 2020-02-27 | 1498 | 1498 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24380 | Analyze | 2 | 2020-02-28 | 2020-03-02 | 2616 | 2616 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
S17 SW Update |  | 2 | 2020-02-19 | 2020-02-20 | 1744 | 1744 | 0
950/962AU20-1030 | Run & Checkout S17 | 2 | 2020-02-19 | 2020-02-20 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
XMSN Auto Cal Dev |  | 24 | 2020-02-28 | 2020-04-01 | 28961 | 28961 | 16
950/962 AU20-22520 | Setup | 1 | 2020-02-28 | 2020-02-28 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22540 | Instrument | 2 | 2020-03-02 | 2020-03-03 | 3618 | 3618 | 16 | powelaw.Powell Austin W | PPG
950/962 AU20-22500 | Run | 20 | 2020-03-04 | 2020-03-31 | 22660 | 22660 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22510 | Teardown | 1 | 2020-04-01 | 2020-04-01 | 1607 | 1607 |  | powelaw.Powell Austin W | PPG
STP 407 Engine Installation Audit |  | 77 | 2020-03-19 | 2020-07-07 | 21496 | 21496 | 24
950/962 AU20-24440 | Plan | 10 | 2020-03-19 | 2020-04-01 | 2180 | 2180 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24450 | Setup | 3 | 2020-04-02 | 2020-04-06 | 4536 | 4536 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24460 | Instrument | 2 | 2020-04-07 | 2020-04-08 | 5878 | 5878 | 24 | powelaw.Powell Austin W | PPG
950/962 AU20-24470 | Run | 2 | 2020-04-09 | 2020-04-10 | 3248 | 3248 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24480 | Teardown | 1 | 2020-04-13 | 2020-04-13 | 1294 | 1294 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24490 | TIC Report | 60 | 2020-04-13 | 2020-07-07 | 4360 | 4360 |  | powelaw.Powell Austin W | PPG
XMSN Signature |  | 19 | 2020-04-14 | 2020-05-08 | 23296 | 23296 | 16
950/962 AU20-22680 | Setup | 1 | 2020-04-14 | 2020-04-14 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22700 | Instrument | 2 | 2020-04-15 | 2020-04-16 | 3618 | 3618 | 16 | powelaw.Powell Austin W | PPG
950/962 AU20-22660 | Run | 15 | 2020-04-17 | 2020-05-07 | 16995 | 16995 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22670 | Teardown | 1 | 2020-05-08 | 2020-05-08 | 1607 | 1607 |  | powelaw.Powell Austin W | PPG
L5 Issue Resolution |  | 20 | 2020-04-27 | 2020-05-22 | 12345.5 | 12345.5 | 32
950/962 AU20-4840 | Plan | 10 | 2020-04-27 | 2020-05-08 | 1090 | 1090 |  | powelaw.Powell Austin W | PPG
950/962 AU20-4850 | Setup | 1 | 2020-05-11 | 2020-05-11 | 1948 | 1948 |  | powelaw.Powell Austin W | PPG
950/962 AU20-4860 | Instrument | 3 | 2020-05-12 | 2020-05-14 | 5487 | 5487 | 32 | Instrument Tech.Instrumentation Setup Tech | PPG
950/962 AU20-4870 | Run | 5 | 2020-05-15 | 2020-05-21 | 2962.5 | 2962.5 |  | powelaw.Powell Austin W | PPG
950/962 AU20-4880 | Teardown | 1 | 2020-05-22 | 2020-05-22 | 858 | 858 |  | powelaw.Powell Austin W | PPG
950 Stage V Machine Sound Dev #2 |  | 16 | 2020-05-26 | 2020-06-16 | 16062 | 16062 | 0
950/962 AU20-26865 | Run - Sound Bldg | 3 | 2020-05-26 | 2020-05-28 | 13278 | 13278 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG.Sound.Bld
950/962 AU20-26870 | Report | 13 | 2020-05-29 | 2020-06-16 | 2784 | 2784 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
Productivity |  | 43 | 2020-05-14 | 2020-07-15 | 46522 | 46522 | 0
950/962 AU20-22800 | Plan | 10 | 2020-05-14 | 2020-05-28 | 2180 | 2180 |  | powelaw.Powell Austin W | PPG
950/962 AU20-22810 | Setup | 3 | 2020-05-29 | 2020-06-02 | 4536 | 4536 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-22850 | Field Prep | 2 | 2020-06-01 | 2020-06-02 | 1498 | 1498 |  | Field_Prep1.Field Prep 1 | PPG
950/962 AU20-22820 | Run | 10 | 2020-06-03 | 2020-06-16 | 31360 | 31360 |  | 01-88180-242.TSD881HRY - SEC80 RES242 PPG TEST OPERATIONS - Vehicle Operator-ABC | PPG
950/962 AU20-22830 | Teardown | 2 | 2020-06-17 | 2020-06-18 | 2588 | 2588 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-22840 | Report | 20 | 2020-06-17 | 2020-07-15 | 4360 | 4360 |  | powelaw.Powell Austin W | PPG
962 Stg V Testbed3 (SN) |  | 228 | 2019-03-21 | 2020-02-20 | 461535.13 | 461535.13 | 323
LOE |  | 203 | 2019-04-15 | 2020-02-10 | 0 | 0 | 0
950/962 AU20-24500 | Start Testing 962 Stg V TB 3 | 0 | 2019-04-15 |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-24510 | LOE: 962 Stg V TB 3 | 193 | 2019-04-15 | 2020-01-27 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-24520 | Testing Complete: 962 Stg V TB 3 | 0 |  | 2020-01-27 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-24530 | Reports Complete: 962 Stg V TB 3 | 0 |  | 2020-02-10 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
962 Stg V Machine Build |  | 42 | 2019-03-21 | 2019-05-17 | 45506 | 45506 | 0
950/962 AU20-24540 | Plan | 17 | 2019-03-21 | 2019-04-12 | 3706 | 3706 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24550 | Rework (Imp valve, pump, Hyd tank, AUX valve, Safim brake valve, NGSC gen 3, OEAII | 25 | 15-Apr-19* | 2019-05-17 | 41800 | 41800 |  | powelaw.Powell Austin W | PPG
SW & Electrical Checkout |  | 15 | 2019-05-20 | 2019-06-10 | 15502.5 | 15502.5 | 0
950/962 AU20-24880 | Run | 15 | 2019-05-20 | 2019-06-10 | 15502.5 | 15502.5 |  | powelaw.Powell Austin W | PPG
Machine Checkout STP-64 |  | 13 | 2019-05-28 | 2019-06-13 | 7094 | 7094 | 0
950/962 AU20-24620 | Plan | 10 | 2019-05-28 | 2019-06-10 | 3270 | 3270 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24630 | Run | 3 | 2019-06-11 | 2019-06-13 | 3824 | 3824 |  | powelaw.Powell Austin W | PPG
Hydraulic Test |  | 58 | 2019-05-31 | 2019-08-21 | 65318 | 65318 | 32
950/962 AU20-24570 | Plan | 10 | 2019-05-31 | 2019-06-13 | 4360 | 4360 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-24580 | Setup | 5 | 2019-06-14 | 2019-06-20 | 8650 | 8650 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-24590 | Instrument | 3 | 2019-06-21 | 2019-06-25 | 9477 | 9477 | 32 | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-24560 | Run | 10 | 2019-06-26 | 2019-07-10 | 25760 | 25760 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-24600 | Teardown | 3 | 2019-07-11 | 2019-07-15 | 4536 | 4536 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-24610 | Report | 30 | 2019-07-11 | 2019-08-21 | 12535 | 12535 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
Light Fab and Engine Install OMSA & MER Test |  | 164 | 2019-03-27 | 2019-11-14 | 113399.8 | 113399.8 | 120
950/962 AU20-24740 | Planning & Procurement | 74 | 2019-03-27 | 2019-07-10 | 9446.67 | 9446.67 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24750 | SGL Strain Gage Lab - Instrument Parts | 3 | 2019-07-11 | 2019-07-15 | 3379 | 3379 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24810 | Setup - Shop Support Work | 3 | 2019-07-16 | 2019-07-18 | 5190 | 5190 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-24760 | Instrument - Setup Bay | 10 | 2019-07-19 | 2019-08-01 | 30737.33 | 30737.33 | 120 | 01-88102-400.TSD881MGT - SEC02 RES400 INSTRUMENTATION - Management Labor-Program | PPG
950/962 AU20-24820 | Field Prep for OMSA | 2 | 2019-07-31 | 2019-08-01 | 16434 | 16434 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24770 | Run | 8 | 2019-08-02 | 2019-08-13 | 31948.8 | 31948.8 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24780 | Teardown | 1 | 2019-08-14 | 2019-08-14 | 3184 | 3184 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-24790 | Preliminary Analysis/Reporting | 5 | 2019-08-14 | 2019-08-20 | 4360 | 4360 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24800 | TIC Report | 61 | 2019-08-21 | 2019-11-14 | 8720 | 8720 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
S14 SW Update |  | 2 | 2019-06-07 | 2019-06-10 | 1744 | 1744 | 0
950/962AU20-1040 | Run & Checkout S14 | 2 | 2019-06-07 | 2019-06-10 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
OMSA Heavy Fab |  | 215 | 2019-04-05 | 2020-02-18 | 148169.33 | 148169.33 | 160
950/962 AU20-24640 | Planning & Procurement | 89 | 2019-04-05 | 2019-08-09 | 2180 | 2180 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24650 | SGL Strain Gage Lab - Instrument Parts | 3 | 2019-08-12 | 2019-08-14 | 5647 | 5647 |  | PPG SGL Tech.PPG SGL Tech | PPG
950/962 AU20-24710 | Setup - Shop Support Work | 5 | 15-Aug-19* | 2019-08-21 | 7208.33 | 7208.33 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-24660 | Instrument - Setup Bay or Lab | 10 | 2019-08-22 | 2019-09-05 | 44210 | 44210 | 160 | 01-88102-400.TSD881MGT - SEC02 RES400 INSTRUMENTATION - Management Labor-Program | PPG
950/962 AU20-24730 | Field Prep for OMSA | 2 | 2019-09-04 | 2019-09-05 | 16216 | 16216 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24670 | Run | 12 | 2019-09-06 | 2019-09-23 | 59568 | 59568 |  | 01-88180-242.TSD881HRY - SEC80 RES242 PPG TEST OPERATIONS - Vehicle Operator-ABC | PPG
950/962 AU20-24680 | Teardown - Including Channel Verification | 2 | 2019-09-24 | 2019-09-25 | 3548 | 3548 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
950/962 AU20-24690 | Preliminary Results Analysis | 5 | 2019-09-24 | 2019-09-30 | 218 | 218 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24700 | Formal Presentation and Report | 31 | 2019-10-01 | 2019-11-12 | 654 | 654 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
950/962 AU20-24720 | TIC Report | 60 | 2019-11-13 | 2020-02-18 | 8720 | 8720 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
S15 SW Update |  | 2 | 2019-09-06 | 2019-09-09 | 1744 | 1744 | 0
950/962AU20-1050 | Run & Checkout S15 | 2 | 2019-09-06 | 2019-09-09 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
L5 Performance Dev/Tuning #1 |  | 15 | 2019-09-26 | 2019-10-16 | 15960 | 15960 | 0
950/962 AU20-24830 | Run | 15 | 26-Sep-19* | 2019-10-16 | 15960 | 15960 |  | powelaw.Powell Austin W | PPG
Electrical Load Study & Battery Shielded Cable |  | 5 | 2019-11-07 | 2019-11-13 | 4905 | 4905 | 0
950/962 AU20-24860 | Run | 5 | 07-Nov-19* | 2019-11-13 | 4905 | 4905 |  | powelaw.Powell Austin W | PPG
Servicability Audit |  | 2 | 2019-11-25 | 2019-11-26 | 2152 | 2152 | 0
950/962 AU20-24840 | Setup | 2 | 25-Nov-19* | 2019-11-26 | 2152 | 2152 |  | powelaw.Powell Austin W | PPG
Safety Audit |  | 2 | 2019-11-27 | 2019-12-02 | 2152 | 2152 | 0
950/962 AU20-24870 | Setup | 2 | 2019-11-27 | 2019-12-02 | 2152 | 2152 |  | powelaw.Powell Austin W | PPG
S16 SW Update |  | 2 | 2019-12-06 | 2019-12-09 | 1744 | 1744 | 0
950/962AU20-1060 | Run & Checkout S16 | 2 | 2019-12-06 | 2019-12-09 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
ISO 3450 Feasibility Checkout |  | 37 | 2019-12-10 | 2020-02-10 | 34400.5 | 34400.5 | 11
950/962 AU20-23320 | Plan | 10 | 2019-12-10 | 2019-12-23 | 2180 | 2180 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23290 | Setup | 4 | 02-Jan-20* | 2020-01-07 | 4712 | 4712 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23300 | Instrument | 1 | 2020-01-08 | 2020-01-08 | 1992.5 | 1992.5 | 11 | powelaw.Powell Austin W | PPG
950/962 AU20-23340 | Run | 10 | 2020-01-09 | 2020-01-23 | 19440 | 19440 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23310 | Teardown | 2 | 2020-01-24 | 2020-01-27 | 1716 | 1716 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23330 | Report | 10 | 2020-01-28 | 2020-02-10 | 4360 | 4360 |  | powelaw.Powell Austin W | PPG
S17 SW Update |  | 2 | 2020-02-19 | 2020-02-20 | 1744 | 1744 | 0
950/962AU20-1070 | Run & Checkout S17 | 2 | 2020-02-19 | 2020-02-20 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
962 T3 HMU Testbed 4 (SN) |  | 310 | 2019-03-28 | 2020-06-23 | 353323 | 353323 | 32
LOE |  | 279 | 2019-05-10 | 2020-06-23 | 0 | 0 | 0
950/962 AU20-24890 | Start Testing 962 T3 HMU TB 4 | 0 | 2019-05-10 |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-24900 | LOE: 962 T3 HMU TB 4 | 264 | 2019-05-10 | 2020-06-02 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-24910 | Testing Complete: 962 T3 HMU TB 4 | 0 |  | 2020-06-02 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-24920 | Reports Complete: 962 T3 HMU TB 4 | 0 |  | 2020-06-23 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
Machine Update - Built in Aurora |  | 3 | 2019-05-07 | 2019-05-09 | 1853 | 1853 | 0
950/962 AU201020 | Machine Key On | 2 | 07-May-19* | 2019-05-08 | 1744 | 1744 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | Field
950/962 AU201015 | Ship to PPG | 1 | 2019-05-09 | 2019-05-09 | 109 | 109 |  | layjd.Lay Joe D | Field
Machine Checkout STP-64 |  | 15 | 2019-04-26 | 2019-05-16 | 9643.33 | 9643.33 | 0
950/962 AU20-24950 | Plan | 10 | 2019-04-26 | 2019-05-09 | 3270 | 3270 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24960 | Run | 5 | 2019-05-10 | 2019-05-16 | 6373.33 | 6373.33 |  | powelaw.Powell Austin W | PPG
Servicability Audit |  | 2 | 2019-05-17 | 2019-05-20 | 2152 | 2152 | 0
950/962 AU20-24970 | Setup | 2 | 2019-05-17 | 2019-05-20 | 2152 | 2152 |  | powelaw.Powell Austin W | PPG
962 T3 Muffler Sound Validation |  | 32 | 2019-05-21 | 2019-07-05 | 11348 | 11348 | 0
950/962 AU20-25490 | Run - Sound Bldg | 2 | 2019-05-21 | 2019-05-22 | 9492 | 9492 |  | rogerar2.Rogers Adam R | PPG.Sound.Bld
950/962 AU20-25480 | Report | 20 | 2019-06-07 | 2019-07-05 | 1856 | 1856 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
962 Endurance 0-500 hrs |  | 68 | 2019-03-28 | 2019-07-02 | 57440 | 57440 | 0
950/962 AU20-25010 | Plan | 40 | 2019-03-28 | 2019-05-22 | 981 | 981 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25000 | Endurance - 1 shift for 1st week | 3 | 2019-05-23 | 2019-05-25 | 5012 | 5012 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24990 | Endurance (40-250hr) | 16 | 2019-05-26 | 2019-06-11 | 22512 | 22512 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25030 | 250hr Service/Inspect | 1 | 2019-06-12 | 2019-06-12 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25020 | Endurance (251-500hr) | 19 | 2019-06-13 | 2019-07-01 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-24980 | 500hr Service/Inspect/Update | 1 | 2019-07-02 | 2019-07-02 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
S14 SW Update |  | 2 | 2019-06-07 | 2019-06-10 | 1744 | 1744 | 0
950/962AU20-1080 | Run & Checkout S14 | 2 | 2019-06-07 | 2019-06-10 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
962 Endurance 501-1000 hrs |  | 28 | 2019-07-03 | 2019-08-12 | 55718 | 55718 | 0
950/962 AU20-25050 | Endurance (501-750hr) | 19 | 2019-07-03 | 2019-07-22 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25080 | 750hr Service/Inspect | 1 | 2019-07-23 | 2019-07-23 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25070 | Endurance (751-1000hr) | 19 | 2019-07-24 | 2019-08-11 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25040 | 1000hr Service/Inspect/Update | 1 | 2019-08-12 | 2019-08-12 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
962 Endurance 1001-1500 hrs |  | 29 | 2019-08-13 | 2019-09-23 | 55718 | 55718 | 0
950/962 AU20-25100 | Endurance (1001-1250hr) | 19 | 2019-08-13 | 2019-08-31 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25130 | 1250hr Service/Inspect | 1 | 2019-09-03 | 2019-09-03 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25120 | Endurance (1251-1500hr) | 19 | 2019-09-04 | 2019-09-22 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25090 | 1500hr Service/Inspect/Update | 1 | 2019-09-23 | 2019-09-23 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
S15 SW Update |  | 2 | 2019-09-06 | 2019-09-09 | 1744 | 1744 | 0
950/962AU20-1090 | Run & Checkout S15 | 2 | 2019-09-06 | 2019-09-09 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
962 Endurance 1501-2000 hrs |  | 30 | 2019-09-24 | 2019-11-04 | 55718 | 55718 | 0
950/962 AU20-25150 | Endurance (1501-1750hr) | 19 | 2019-09-24 | 2019-10-12 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25180 | 1750hr Service/Inspect | 1 | 2019-10-14 | 2019-10-14 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25170 | Endurance (1750-2000hr) | 19 | 2019-10-15 | 2019-11-02 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25140 | 2000hr Service/Inspect/Update | 1 | 2019-11-04 | 2019-11-04 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
BOSCH Fuel System Eval |  | 10 | 2019-11-05 | 2019-11-18 | 8720 | 8720 | 0
950/962 AU20-25310 | Run | 10 | 2019-11-05 | 2019-11-18 | 8720 | 8720 |  | powelaw.Powell Austin W | PPG
962 Final Inspection |  | 10 | 2019-11-19 | 2019-12-04 | 9090 | 9090 | 0
950/962 AU20-25330 | Rework (Imp valve, OEAII, NGSC, Pump) | 10 | 2019-11-19 | 2019-12-04 | 9090 | 9090 |  | powelaw.Powell Austin W | PPG
962 Axle Pinion Bearing Inspection |  | 10 | 2019-11-26 | 2019-12-11 | 5816 | 5816 | 0
950/962 AU20-21700 | Plan | 5 | 2019-11-26 | 2019-12-04 | 436 | 436 |  | powelaw.Powell Austin W | PPG
950/962 AU20-21720 | Setup | 5 | 2019-12-05 | 2019-12-11 | 5380 | 5380 |  | powelaw.Powell Austin W | PPG
S16 SW Update |  | 2 | 2019-12-06 | 2019-12-09 | 1744 | 1744 | 0
950/962AU20-1100 | Run & Checkout S16 | 2 | 2019-12-06 | 2019-12-09 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
962 T3 Sound Development |  | 33 | 2020-01-13 | 2020-02-27 | 16062 | 16062 | 0
950/962 AU20-25590 | Run - Sound Bldg | 3 | 13-Jan-20* | 2020-01-15 | 13278 | 13278 |  | rogerar2.Rogers Adam R | PPG.Sound.Bld
950/962 AU20-25585 | Report | 20 | 2020-01-31 | 2020-02-27 | 2784 | 2784 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
S17 SW Update |  | 2 | 2020-02-19 | 2020-02-20 | 1744 | 1744 | 0
950/962AU20-1110 | Run & Checkout S17 | 2 | 2020-02-19 | 2020-02-20 | 1744 | 1744 |  | egantr.Egan Thomas R | PPG
962 Altitude Test |  | 81 | 2020-03-02 | 2020-06-23 | 57068.67 | 57068.67 | 32
950/962 AU20-25220 | Plan - 966M Altitude Performance Eval | 40 | 2020-03-02 | 2020-04-24 | 4360 | 4360 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25230 | Setup - 966M Altitude Performance Eval | 2 | 27-Apr-20* | 2020-04-28 | 4076.67 | 4076.67 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25200 | Instrument | 2 | 2020-04-29 | 2020-04-30 | 6354 | 6354 | 32 | powelaw.Powell Austin W | PPG
950/962 AU20-25210 | Run - Machine Checkout | 2 | 2020-05-01 | 2020-05-04 | 1714 | 1714 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25300 | Run Baseline | 2 | 2020-05-05 | 2020-05-06 | 1714 | 1714 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25260 | Ship machine to Denver CO | 3 | 2020-05-07 | 2020-05-11 | 8100 | 8100 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25270 | Run Response at Denver (5000 ft) | 5 | 2020-05-12 | 2020-05-18 | 7555 | 7555 |  | powelaw.Powell Austin W | Field
950/962 AU20-25280 | Ship machine to Leadville CO | 1 | 2020-05-18 | 2020-05-19 | 2872 | 2872 |  | powelaw.Powell Austin W | Field
950/962 AU20-25290 | Run Response at Leadville (10000 ft) | 5 | 2020-05-20 | 2020-05-27 | 7555 | 7555 |  | powelaw.Powell Austin W | Field
950/962 AU20-25190 | Ship machine back to PPG | 3 | 2020-05-28 | 2020-06-01 | 8000 | 8000 |  | powelaw.Powell Austin W | Field
950/962 AU20-25240 | Teardown - 966M Altitude Performance Eval | 1 | 2020-06-02 | 2020-06-02 | 1498 | 1498 |  | powelaw.Powell Austin W | PPG
950/962 AU20-25250 | Report - 966M Altitude Performance Eval | 15 | 2020-06-03 | 2020-06-23 | 3270 | 3270 |  | powelaw.Powell Austin W | PPG
Pilot Phase |  | 343 | 2021-01-25 | 2022-06-06 | 939457.17 | 939457.17 | 43
962 HRC AU2020 Pilot #1 (SN) |  | 154 | 2021-01-25 | 2021-08-30 | 302727.83 | 302727.83 | 27
LOE |  | 144 | 2021-02-08 | 2021-08-30 | 0 | 0 | 0
950/962 AU20-5600 | Start Testing 962 HRC Pilot | 0 | 2021-02-08 |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-5610 | LOE: 962 HRC Pilot | 144 | 2021-02-08 | 2021-08-30 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-5630 | Reports Complete: 962 HRC Pilot | 0 |  | 2021-05-24 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-5620 | Testing Complete: 962 HRC Pilot | 0 |  | 2021-08-30 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
Machine Checkout |  | 13 | 2021-01-25 | 2021-02-10 | 4026 | 4026 | 0
950/962 AU20-18290 | Plan | 10 | 2021-01-25 | 2021-02-05 | 3270 | 3270 |  | powelaw.Powell Austin W | PPG
950/962 AU20-18300 | Setup | 3 | 08-Feb-21* | 2021-02-10 | 756 | 756 |  | powelaw.Powell Austin W | PPG
L5 Checkout |  | 5 | 2021-02-11 | 2021-02-17 | 5320 | 5320 | 0
950/962 AU20-23110 | Run | 5 | 2021-02-11 | 2021-02-17 | 5320 | 5320 |  | powelaw.Powell Austin W | PPG
SW Update |  | 5 | 2021-02-18 | 2021-02-24 | 7205 | 7205 | 0
950/962 AU20-23120 | Run | 5 | 2021-02-18 | 2021-02-24 | 7205 | 7205 |  | powelaw.Powell Austin W | PPG
962 HRC ISO 5010 Steering Certification |  | 34 | 2021-02-04 | 2021-03-23 | 54748.33 | 54748.33 | 16
950/962 AU20-23440 | Plan | 15 | 2021-02-04 | 2021-02-24 | 4905 | 4905 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-23450 | Setup | 4 | 2021-02-25 | 2021-03-02 | 10732 | 10732 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-23460 | Instrument | 2 | 2021-03-03 | 2021-03-04 | 2964 | 2964 | 16 | powelaw.Powell Austin W | PPG
950/962 AU20-23430 | Run | 10 | 2021-03-05 | 2021-03-18 | 32033.33 | 32033.33 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-23470 | Teardown | 1 | 2021-03-19 | 2021-03-19 | 1498 | 1498 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23480 | Analyze | 2 | 2021-03-22 | 2021-03-23 | 2616 | 2616 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
ISO 3450 Brake Cert STP24 |  | 89 | 2021-03-08 | 2021-07-12 | 38288.5 | 38288.5 | 11
950/962 AU201040 | Plan | 10 | 2021-03-08 | 2021-03-19 | 2180 | 2180 |  | powelaw.Powell Austin W | PPG
950/962 AU201025 | Setup | 4 | 2021-03-22 | 2021-03-25 | 4712 | 4712 |  | powelaw.Powell Austin W | PPG
950/962 AU201030 | Instrument | 1 | 2021-03-26 | 2021-03-26 | 1992.5 | 1992.5 | 11 | powelaw.Powell Austin W | PPG
950/962 AU201050 | Run | 12 | 2021-03-29 | 2021-04-13 | 23328 | 23328 |  | powelaw.Powell Austin W | PPG
950/962 AU201035 | Teardown | 2 | 2021-04-14 | 2021-04-15 | 1716 | 1716 |  | powelaw.Powell Austin W | PPG
950/962 AU201045 | TIC Report | 60 | 2021-04-16 | 2021-07-12 | 4360 | 4360 |  | powelaw.Powell Austin W | PPG
962 HRC EMC Test |  | 77 | 2021-02-05 | 2021-05-24 | 23056 | 23056 | 0
950/962 AU20-23240 | Plan | 50 | 2021-02-05 | 2021-04-15 | 4600 | 4600 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
950/962 AU20-23250 | Setup | 2 | 2021-04-16 | 2021-04-19 | 2152 | 2152 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23260 | Run | 5 | 2021-04-20 | 2021-04-26 | 12670 | 12670 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
950/962 AU20-23270 | Teardown | 1 | 2021-04-27 | 2021-04-27 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23280 | Report | 20 | 2021-04-27 | 2021-05-24 | 2558 | 2558 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
962 Pilot HRC Endurance 0-500 hrs |  | 69 | 2021-03-03 | 2021-06-08 | 58648 | 58648 | 0
950/962 AU20-23160 | Plan | 40 | 2021-03-03 | 2021-04-27 | 981 | 981 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23150 | Endurance - 1 shift for 1st week | 5 | 2021-04-28 | 2021-05-02 | 6220 | 6220 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23140 | Endurance (40-250hr) | 16 | 2021-05-03 | 2021-05-18 | 22512 | 22512 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23180 | 250hr Service/Inspect | 1 | 2021-05-19 | 2021-05-19 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23170 | Endurance (251-500hr) | 19 | 2021-05-20 | 2021-06-07 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23130 | 500hr Service/Inspect/Update | 1 | 2021-06-08 | 2021-06-08 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
962 Pilot HRC Endurance 501-1000 hrs |  | 28 | 2021-06-09 | 2021-07-19 | 55718 | 55718 | 0
950/962 AU20-23200 | Endurance (501-750hr) | 19 | 2021-06-09 | 2021-06-27 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23230 | 750hr Service/Inspect | 1 | 2021-06-28 | 2021-06-28 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23220 | Endurance (751-1000hr) | 19 | 2021-06-29 | 2021-07-17 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23190 | 1000hr Service/Inspect/Update | 1 | 2021-07-19 | 2021-07-19 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
962 Pilot HRC Endurance 1001-1500 hrs |  | 30 | 2021-07-20 | 2021-08-30 | 55718 | 55718 | 0
950/962 AU201060 | Endurance (1001-1250hr) | 19 | 2021-07-20 | 2021-08-07 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201075 | 1250hr Service/Inspect | 1 | 2021-08-09 | 2021-08-09 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU201070 | Endurance (1251-1500hr) | 19 | 2021-08-10 | 2021-08-28 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201055 | 1500hr Service/Inspect/Update | 1 | 2021-08-30 | 2021-08-30 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 LRC AU2020 Endurance Pilot #2 (SN) |  | 333 | 2021-02-08 | 2022-06-06 | 636729.33 | 636729.33 | 16
LOE |  | 323 | 2021-02-22 | 2022-06-06 | 0 | 0 | 0
950/962 AU20-10440 | Start Testing 950 LRC Pilot | 0 | 2021-02-22 |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-10470 | LOE: 950 LRC Pilot | 470 | 2021-02-22 | 2022-06-06 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
950/962 AU20-10450 | Testing Complete: 950 LRC Pilot | 0 |  | 2022-06-06 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
Machine Checkout |  | 13 | 2021-02-08 | 2021-02-24 | 4026 | 4026 | 0
950/962 AU20-23590 | Plan | 10 | 2021-02-08 | 2021-02-19 | 3270 | 3270 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23600 | Setup | 3 | 22-Feb-21* | 2021-02-24 | 756 | 756 |  | powelaw.Powell Austin W | PPG
L5 Checkout |  | 10 | 2021-02-25 | 2021-03-10 | 10640 | 10640 | 0
950/962 AU20-23500 | Run | 10 | 2021-02-25 | 2021-03-10 | 10640 | 10640 |  | powelaw.Powell Austin W | PPG
SW Update |  | 5 | 2021-03-11 | 2021-03-17 | 7205 | 7205 | 0
950/962 AU20-23510 | Run | 5 | 2021-03-11 | 2021-03-17 | 7205 | 7205 |  | powelaw.Powell Austin W | PPG
950 LRC ISO 5010 Steering Certification |  | 34 | 2021-02-25 | 2021-04-13 | 54748.33 | 54748.33 | 16
950/962 AU20-23530 | Plan | 15 | 2021-02-25 | 2021-03-17 | 4905 | 4905 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-23540 | Setup | 4 | 18-Mar-21* | 2021-03-23 | 10732 | 10732 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-23550 | Instrument | 2 | 2021-03-24 | 2021-03-25 | 2964 | 2964 | 16 | powelaw.Powell Austin W | PPG
950/962 AU20-23520 | Run | 10 | 2021-03-26 | 2021-04-08 | 32033.33 | 32033.33 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950/962 AU20-23560 | Teardown | 1 | 2021-04-09 | 2021-04-09 | 1498 | 1498 |  | powelaw.Powell Austin W | PPG
950/962 AU20-23570 | Analyze | 2 | 2021-04-12 | 2021-04-13 | 2616 | 2616 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
950 Pilot LRC Endurance 0-500 hrs |  | 71 | 2021-02-15 | 2021-05-24 | 58648 | 58648 | 0
950/962 AU20-10410 | Plan | 40 | 2021-02-15 | 2021-04-09 | 981 | 981 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10400 | Endurance - 1 shift for 1st week | 5 | 2021-04-10 | 2021-04-14 | 6220 | 6220 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10390 | Endurance (40-250hr) | 16 | 2021-04-15 | 2021-04-30 | 22512 | 22512 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10430 | 250hr Service/Inspect | 1 | 2021-05-03 | 2021-05-03 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10420 | Endurance (251-500hr) | 19 | 2021-05-04 | 2021-05-22 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10380 | 500hr Service/Inspect/Update | 1 | 2021-05-24 | 2021-05-24 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 501-1000 hrs |  | 29 | 2021-05-25 | 2021-07-06 | 55718 | 55718 | 0
950/962 AU20-10520 | Endurance (501-750hr) | 19 | 2021-05-25 | 2021-06-12 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10550 | 750hr Service/Inspect | 1 | 2021-06-14 | 2021-06-14 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10540 | Endurance (751-1000hr) | 19 | 2021-06-15 | 2021-07-03 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10510 | 1000hr Service/Inspect/Update | 1 | 2021-07-06 | 2021-07-06 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 1001-1500 hrs |  | 29 | 2021-07-07 | 2021-08-16 | 55718 | 55718 | 0
950/962 AU20-10570 | Endurance (1001-1250hr) | 19 | 2021-07-07 | 2021-07-25 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10600 | 1250hr Service/Inspect | 1 | 2021-07-26 | 2021-07-26 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10590 | Endurance (1251-1500hr) | 19 | 2021-07-27 | 2021-08-14 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10560 | 1500hr Service/Inspect/Update | 1 | 2021-08-16 | 2021-08-16 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 1501-2000 hrs |  | 29 | 2021-08-17 | 2021-09-27 | 55718 | 55718 | 0
950/962 AU20-10620 | Endurance (1501-1750hr) | 19 | 2021-08-17 | 2021-09-04 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10650 | 1750hr Service/Inspect | 1 | 2021-09-07 | 2021-09-07 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10640 | Endurance (1750-2000hr) | 19 | 2021-09-08 | 2021-09-26 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10610 | 2000hr Service/Inspect/Update | 1 | 2021-09-27 | 2021-09-27 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 2001-2500 hrs |  | 30 | 2021-09-28 | 2021-11-08 | 55718 | 55718 | 0
950/962 AU20-10670 | Endurance (2001-2250hr) | 19 | 2021-09-28 | 2021-10-16 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10700 | 2250hr Service/Inspect | 1 | 2021-10-18 | 2021-10-18 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10690 | Endurance (2251-2500hr) | 19 | 2021-10-19 | 2021-11-06 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10660 | 2500hr Service/Inspect/Update | 1 | 2021-11-08 | 2021-11-08 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 2501-3000 hrs |  | 28 | 2021-11-09 | 2021-12-20 | 55718 | 55718 | 0
950/962 AU20-10720 | Endurance (2501-2550hr) | 19 | 2021-11-09 | 2021-11-27 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10750 | 2550hr Service/Inspect | 1 | 2021-11-29 | 2021-11-29 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10740 | Endurance (2551-3000hr) | 19 | 2021-11-30 | 2021-12-18 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU20-10710 | 3000hr Service/Inspect/Update | 1 | 2021-12-20 | 2021-12-20 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 3001-3500 hrs |  | 23 | 2021-12-21 | 2022-01-31 | 55718 | 55718 | 0
950/962 AU201085 | Endurance (3001-3250hr) | 19 | 2021-12-21 | 2022-01-08 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201100 | 3250hr Service/Inspect | 1 | 2022-01-10 | 2022-01-10 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU201095 | Endurance (3251-3500hr) | 19 | 2022-01-11 | 2022-01-29 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201080 | 3500hr Service/Inspect/Update | 1 | 2022-01-31 | 2022-01-31 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 3501-4000 hrs |  | 30 | 2022-02-01 | 2022-03-14 | 55718 | 55718 | 0
950/962 AU201110 | Endurance (3501-3750hr) | 19 | 2022-02-01 | 2022-02-19 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201125 | 3750hr Service/Inspect | 1 | 2022-02-21 | 2022-02-21 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU201120 | Endurance (3751-4000hr) | 19 | 2022-02-22 | 2022-03-12 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201105 | 4000hr Service/Inspect/Update | 1 | 2022-03-14 | 2022-03-14 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 4001-4500 hrs |  | 30 | 2022-03-15 | 2022-04-25 | 55718 | 55718 | 0
950/962 AU201135 | Endurance (4001-4250hr) | 19 | 2022-03-15 | 2022-04-02 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201150 | 4250hr Service/Inspect | 1 | 2022-04-04 | 2022-04-04 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU201145 | Endurance (4250-4500hr) | 19 | 2022-04-05 | 2022-04-23 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201130 | 4500hr Service/Inspect/Update | 1 | 2022-04-25 | 2022-04-25 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950 Pilot LRC Endurance 4501-5000 hrs |  | 29 | 2022-04-26 | 2022-06-06 | 55718 | 55718 | 0
950/962 AU201160 | Endurance (4501-4750hr) | 19 | 2022-04-26 | 2022-05-14 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201175 | 4750hr Service/Inspect | 1 | 2022-05-16 | 2022-05-16 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG
950/962 AU201170 | Endurance (4750-5000hr) | 19 | 2022-05-17 | 2022-06-04 | 26783 | 26783 |  | powelaw.Powell Austin W | PPG
950/962 AU201155 | 5000hr Service/Inspect/Update | 1 | 2022-06-06 | 2022-06-06 | 1076 | 1076 |  | powelaw.Powell Austin W | PPG