## Week Summary
40 hr week
Values
Project | Serial # | Resource Name | Sum of 21-Oct-18 | Sum of 28-Oct-18 | Sum of 4-Nov-18 | Sum of 11-Nov-18 | Sum of 18-Nov-18 | Sum of 25-Nov-18 | Sum of 2-Dec-18 | Sum of 9-Dec-18 | Sum of 16-Dec-18 | Sum of 23-Dec-18
05 950/962 AU2020 | WL900100 | Frederick Chris C
Leaders Royce E
| TB2.41 | Frederick Chris C
Leaders Royce E
| TB2.RP | Frederick Chris C
Leaders Royce E
| TB2.Cold | Leaders Royce E
| TB3.41 | Frederick Chris C
Leaders Royce E
05 950/962 AU2020 Total
05 966/972 AU2020 | MBY00100 | Anderson Kirk E |  |  |  | 24 | 24 | 40 | 24
|  | Goli Suman |  |  |  | 24 | 24 | 40 | 24
Tinker Matt M
| SM200101 | Anderson Kirk E | 32 | [7 empty] | 8
|  | Frederick Chris C | 32
| SM200102 | Anderson Kirk E | 16 | 8 | 40 | 32 |  |  |  | 8 | 16
|  | Frederick Chris C | [7 empty] | 8 | 16
| W9900100 | Anderson Kirk E | 32
|  | Frederick Chris C | 32
| WLW00100 | Anderson Kirk E | [8 empty] | 32
|  | Frederick Chris C | [8 empty] | 32
05 966/972 AU2020 Total |  |  | 144 | 8 | 40 | 80 | 48 | 80 | 48 | 16 | 104
05 966GC | SGW00201 | Frederick Chris C |  |  | 8 | 16
|  | Jensen Cameron |  |  | 8 | 16
05 966GC Total |  |  |  |  | 16 | 32
05 980 XE | XE300100 | Sharp Jeremy T
|  | Tinker Matt M |  |  |  | 8 | 24 | 40 | 8 | 24
| XE400100 | Sharp Jeremy T
05 980 XE Total | [5 empty] | 8 | 24 | 40 | 8 | 24
05 980/982 AU2020 | MK700100 | Sharp Jeremy T
| MK800100 | Frederick Chris C |  |  | 32 |  |  |  |  | 16 | 40
|  | Sharp Jeremy T |  |  | 32 |  |  |  |  | 16 | 40
Tinker Matt M
| MK900100 | Frederick Chris C | [6 empty] | 16 | 16
|  | Sharp Jeremy T | [6 empty] | 16 | 16
| P1.10 | Sharp Jeremy T
| P1.6 | Sharp Jeremy T
05 980/982 AU2020 Total |  |  |  |  | 64 |  |  |  | 32 | 64 | 80
05 BDL 2019 | EMB00251 | Frederick Chris C |  | 40
|  | Leaders Royce E |  | 40
05 BDL 2019 Total |  |  |  | 80
(blank) | (blank) | (blank)
(blank) Total
05 MWL CPI/M | M5T00101 | Frederick Chris C |  | 24
05 MWL CPI/M Total |  |  |  | 24
05 980GC | PD2.20 | Jensen Cameron
| W7K00288 | Jensen Cameron
| PD2.3 | Frederick Chris C
Sharp Jeremy T
| PD2.RP | Frederick Chris C
Sharp Jeremy T
05 980GC Total
05 966GC 2020 | SGW00201 | Frederick Chris C
Jensen Cameron
05 966GC 2020 Total
05 950XE | EJB00166 | Frederick Chris C
Leaders Royce E
05 950XE Total
Grand Total |  |  | 144 | 112 | 120 | 120 | 72 | 120 | 88 | 104 | 184
end line

## Week Detail
Values
Project | Serial # | Start | WBS Name | Resource Name | Activity ID | Activity Name | Original Duration | Budgeted Units | Sum of 21-Oct-18 | Sum of 28-Oct-18 | Sum of 4-Nov-18 | Sum of 11-Nov-18 | Sum of 18-Nov-18 | Sum of 25-Nov-18 | Sum of 2-Dec-18 | Sum of 9-Dec-18 | Sum of 16-Dec-18 | Sum of 23-Dec-18
05 950/962 AU2020 | WL900100 | 2019-07-05 | L5 Performance Dev/Tuning #1 | Frederick Chris C | 950/962 AU20-21790 | Run | 10 | 80
|  |  |  | Leaders Royce E | 950/962 AU20-21790 | Run | 10 | 80
| TB2.41 | 2019-06-20 | L5 Performance Dev/Tuning #1 | Frederick Chris C | 950/962 AU20-24140 | Run | 10 | 80
|  |  |  | Leaders Royce E | 950/962 AU20-24140 | Run | 10 | 80
| TB2.RP | 2019-07-11 | Rimpull/Response | Frederick Chris C | 950/962 AU20-22410 | Run | 4 | 32
|  |  |  | Leaders Royce E | 950/962 AU20-22410 | Run | 4 | 32
| TB2.Cold | 2019-10-28 | Cold Room Test | Leaders Royce E | 950/962 AU20-22580 | Run | 30 | 240
| TB3.41 | 2019-09-26 | L5 Performance Dev/Tuning #1 | Frederick Chris C | 950/962 AU20-24830 | Run | 15 | 120
|  |  |  | Leaders Royce E | 950/962 AU20-24830 | Run | 15 | 120
05 950/962 AU2020 Total
05 966/972 AU2020 | MBY00100 | 2019-11-26 | Altitude Performance C93B | Anderson Kirk E | 966/972 AU20-16210 | Run Response at Denver (5000 ft) | 5 | 40
|  |  |  | Goli Suman | 966/972 AU20-16210 | Run Response at Denver (5000 ft) | 5 | 40
|  | 2019-06-12 | 972XE Productivity Study (XE, LRC, Powershift) | Anderson Kirk E | 966/972 AU20-23817 | Run | 10 | 80
|  |  |  | Goli Suman | 966/972 AU20-23817 | Run | 10 | 80
|  | 2018-11-14 | S11 SW Checkout | Anderson Kirk E | 966/972 AU20-24482 | Run - L5 Checkout | 14 | 112 |  |  |  | 24 | 24 | 40 | 24
|  |  |  | Goli Suman | 966/972 AU20-24482 | Run - L5 Checkout | 14 | 112 |  |  |  | 24 | 24 | 40 | 24
|  | 2019-06-27 | Dig Assist Development | Tinker Matt M | 966/972 AU20-25480 | Run (Tinker) | 10 | 80
|  | 2019-04-30 | 972XE TB Cold System Performance Testing (Baudette Mn) | Anderson Kirk E | 966/972 AU20-8080 | Machine Checkout | 2 | 16
|  |  |  | Goli Suman | 966/972 AU20-8080 | Machine Checkout | 2 | 16
|  | 2019-05-07 | 972XE TB Cold System Performance Testing (Baudette Mn) | Anderson Kirk E | 966/972 AU20-8010 | Run | 15 | 120
|  |  |  | Goli Suman | 966/972 AU20-8010 | Run | 15 | 120
|  | 2019-03-07 | L5 Performance Development/Tuning | Anderson Kirk E | 966/972 AU20-15550 | Run | 13 | 104
|  |  |  | Goli Suman | 966/972 AU20-15550 | Run | 13 | 104
|  | 2019-12-06 | Altitude Performance C93B | Anderson Kirk E | 966/972 AU20-16230 | Run Response at Leadville (10000 ft) | 4 | 32
|  |  |  | Goli Suman | 966/972 AU20-16230 | Run Response at Leadville (10000 ft) | 4 | 32
|  | 2019-11-19 | Altitude Performance C93B | Anderson Kirk E | 966/972 AU20-16240 | Run Baseline | 2 | 16
|  |  |  | Goli Suman | 966/972 AU20-16240 | Run Baseline | 2 | 16
|  | 2019-11-15 | Altitude Performance C93B | Anderson Kirk E | 966/972 AU20-16150 | Run - Machine Checkout | 2 | 16
|  |  |  | Goli Suman | 966/972 AU20-16150 | Run - Machine Checkout | 2 | 16
|  | 2019-07-12 | Dig Assist Operator Eval | Tinker Matt M | 966/972 AU20-25490 | Run | 3 | 24
| SM200101 | 2018-12-21 | Operator Eval #3 | Anderson Kirk E | 966/972 AU20-4140 | Run | 3 | 24 | [8 empty] | 8
|  | 22-Oct-18 A | Altitude Performance - C93B | Anderson Kirk E | 966/972 AU20-13335 | Run Response at Leadville (10000 ft) | 4 | 32 | 32
|  |  |  | Frederick Chris C | 966/972 AU20-13335 | Run Response at Leadville (10000 ft) | 4 | 32 | 32
| SM200102 | 2019-02-19 | Cold Weather Thermal Mgmt | Anderson Kirk E | 966/972 AU20-24692 | Run | 15 | 120
|  | 2019-07-03 | 972 HRC Altitude Test #2 | Anderson Kirk E | 966/972 AU20-26515 | Run - Machine Checkout | 2 | 16
|  |  |  | Frederick Chris C | 966/972 AU20-26515 | Run - Machine Checkout | 2 | 16
|  | 2018-10-25 | 972 HRC Cold System Performance Testing (Eglin) | Anderson Kirk E | 966/972 AU20-24252 | Machine Checkout | 2 | 16 | 16
|  | 2019-07-08 | 972 HRC Altitude Test #2 | Anderson Kirk E | 966/972 AU20-26565 | Run Baseline | 2 | 16
|  |  |  | Frederick Chris C | 966/972 AU20-26565 | Run Baseline | 2 | 16
|  | 2018-12-14 | L5 Performance Development/Tuning #2 | Anderson Kirk E | 966/972 AU20-24182 | Run | 3 | 24 | [7 empty] | 8 | 16
|  |  |  | Frederick Chris C | 966/972 AU20-24182 | Run | 3 | 24 | [7 empty] | 8 | 16
|  | 2019-05-09 | 972 HRC Productivity Study (XE, LRC, Powershift) | Anderson Kirk E | 966/972 AU20-23787 | Run | 10 | 80
|  | 2018-11-02 | 972 HRC Cold System Performance Testing (Eglin) | Anderson Kirk E | 966/972 AU20-24217 | Run (11/2-15) | 10 | 80 |  | 8 | 40 | 32
|  | 2019-07-15 | 972 HRC Altitude Test #2 | Anderson Kirk E | 966/972 AU20-26545 | Run Response at Denver (5000 ft) (7/15-19) | 5 | 40
|  |  |  | Frederick Chris C | 966/972 AU20-26545 | Run Response at Denver (5000 ft) (7/15-19) | 5 | 40
|  | 2019-07-22 | 972 HRC Altitude Test #2 | Anderson Kirk E | 966/972 AU20-26555 | Run Response at Leadville (10000 ft) | 4 | 32
|  |  |  | Frederick Chris C | 966/972 AU20-26555 | Run Response at Leadville (10000 ft) | 4 | 32
| W9900100 | 2019-03-08 | 972 LRC Cold System Performance Testing (Baudette Mn) | Anderson Kirk E | 966/972 AU2020-1035 | Machine Checkout | 2 | 16
|  | 2019-05-09 | 972 Productivity Study (XE, LRC, Powershift) | Anderson Kirk E | 966/972 AU20-23781 | Run | 10 | 80
|  | 2019-03-15 | 972 LRC Cold System Performance Testing (Baudette Mn) | Anderson Kirk E | 966/972 AU2020-1000 | Run | 10 | 80
|  | 22-Oct-18 A | Altitude Performance | Anderson Kirk E | 966/972 AU20-14090 | Run Response at Leadville (10000 ft) | 4 | 32 | 32
|  |  |  | Frederick Chris C | 966/972 AU20-14090 | Run Response at Leadville (10000 ft) | 4 | 32 | 32
| WLW00100 | 2019-01-14 | 966 HRC Rimpull/Response C93B #1 | Anderson Kirk E | 966/972 AU20-26300 | Run | 4 | 32
|  |  |  | Frederick Chris C | 966/972 AU20-26300 | Run | 4 | 32
|  | 2018-12-18 | L5 Performance Development/Tuning | Anderson Kirk E | 966/972 AU20-25152 | Run | 7 | 56 | [8 empty] | 32
|  |  |  | Frederick Chris C | 966/972 AU20-25152 | Run | 7 | 56 | [8 empty] | 32
|  | 2019-04-25 | 966 HRC Rimpull/Response C93B #2 | Anderson Kirk E | 966/972 AU20-23715 | Run | 6 | 48
|  |  |  | Frederick Chris C | 966/972 AU20-23715 | Run | 6 | 48
05 966/972 AU2020 Total | [8 empty] | 144 | 8 | 40 | 80 | 48 | 80 | 48 | 16 | 104
05 966GC | SGW00201 | 2019-02-20 | Cold Room Test | Jensen Cameron | 966GC-105130 | Run (1/14-25) | 9 | 72
|  | 2019-06-05 | Altitude Performance | Frederick Chris C | 966GC-106390 | Run Baseline | 2 | 16
|  |  |  | Jensen Cameron | 966GC-106390 | Run Baseline | 2 | 16
|  | 2019-03-11 | UPT ETCA Steady State Performance Analysis | Jensen Cameron | 966GC-106540 | Run - Cameron Jensen | 5 | 40
|  | 2019-07-11 | SCL Verification Operator Eval | Frederick Chris C | 966GC-1536 | Run | 2 | 16
|  | 2019-04-01 | L5 Tuning #2 | Frederick Chris C | 966GC-1445 | Run | 8 | 64
|  |  |  | Jensen Cameron | 966GC-1445 | Run | 8 | 64
|  | 2019-05-09 | Altitude Performance | Frederick Chris C | 966GC-106290 | Run - Machine Checkout | 2 | 16
|  |  |  | Jensen Cameron | 966GC-106290 | Run - Machine Checkout | 2 | 16
|  | 2019-04-12 | Operator Eval | Jensen Cameron | 966GC-106400 | Run | 3 | 24
|  | 2018-11-09 | L5 Tuning w/ Operator | Frederick Chris C | 966GC-108370 | Run | 3 | 24 |  |  | 8 | 16
|  |  |  | Jensen Cameron | 966GC-108370 | Run | 3 | 24 |  |  | 8 | 16
|  | 2019-05-24 | Altitude Performance | Frederick Chris C | 966GC-106370 | Run Response at Leadville (10000 ft) | 4 | 32
|  |  |  | Jensen Cameron | 966GC-106370 | Run Response at Leadville (10000 ft) | 4 | 32
|  | 2019-05-16 | Altitude Performance | Frederick Chris C | 966GC-106350 | Run Response at Denver (5000 ft) | 5 | 40
|  |  |  | Jensen Cameron | 966GC-106350 | Run Response at Denver (5000 ft) | 5 | 40
05 966GC Total | [10 empty] | 16 | 32
05 980 XE | XE300100 | 2018-12-10 | Dig Assist Operator Eval | Tinker Matt M | 980XE-11360 | Run | 3 | 24 | [7 empty] | 24
|  | 2018-11-16 | Dig Assist Development | Tinker Matt M | 980XE-11350 | Run (Goli) | 10 | 80 |  |  |  | 8 | 24 | 40 | 8
|  | 2019-01-24 | L4/L5 Development | Sharp Jeremy T | 980XE-12460 | Run | 15 | 120
| XE400100 | 2019-03-05 | Cold Room Test (Baudette) | Sharp Jeremy T | 980XE-11460 | Run | 15 | 120
|  | 2019-02-25 | Cold Room Test (Baudette) | Sharp Jeremy T | 980XE-11090 | Machine Checkout - L4/L5 | 2 | 16
05 980 XE Total | [11 empty] | 8 | 24 | 40 | 8 | 24
05 980/982 AU2020 | MK700100 | 2019-10-11 | Productivity | Sharp Jeremy T | 980/982 AU20-24320 | Run | 10 | 80
| MK800100 | 2018-11-05 | Rimpull Test | Frederick Chris C | 980/982 AU20-25125 | Run | 4 | 32 |  |  | 32
|  |  |  | Sharp Jeremy T | 980/982 AU20-25125 | Run | 4 | 32 |  |  | 32
|  | 2018-12-13 | L5 Tuning w/Response Test #2 | Frederick Chris C | 980/982 AU20-24520 | Run | 10 | 80 | [7 empty] | 16 | 40
|  |  |  | Sharp Jeremy T | 980/982 AU20-24520 | Run | 10 | 80 | [7 empty] | 16 | 40
|  | 2019-10-11 | Productivity | Sharp Jeremy T | 980/982 AU20-25485 | Run | 10 | 80
|  | 2019-01-07 | Dig Assist Operator Eval | Tinker Matt M | 980/982 AU20-26440 | Run | 3 | 24
| MK900100 | 2018-12-06 | Rimpull Test | Frederick Chris C | 980/982 AU20-24700 | Run | 4 | 32 | [6 empty] | 16 | 16
|  |  |  | Sharp Jeremy T | 980/982 AU20-24700 | Run | 4 | 32 | [6 empty] | 16 | 16
| P1.10 | 2019-08-05 | Operator Eval | Sharp Jeremy T | 980/982 AU20-6490 | Run | 3 | 24
| P1.6 | 2019-10-31 | Operator Eval #2 | Sharp Jeremy T | 980/982 AU20-7330 | Run | 3 | 24
05 980/982 AU2020 Total | [10 empty] | 64 |  |  |  | 32 | 64 | 80
05 BDL 2019 | EMB00251 | 2019-05-06 | 950M Stage 5 - L5 Checkout - Preprods | Frederick Chris C | BDL19-1850 | Run | 4 | 32
|  |  |  | Leaders Royce E | BDL19-1850 | Run | 4 | 32
|  | 2018-10-29 | 950M Stage 5 - L5 Checkout #2 | Frederick Chris C | BDL19-1780 | Run | 5 | 40 |  | 40
|  |  |  | Leaders Royce E | BDL19-1780 | Run | 5 | 40 |  | 40
05 BDL 2019 Total | [9 empty] | 80
(blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
(blank) Total
05 MWL CPI/M | M5T00101 | 2018-10-29 | L5 Checkout | Frederick Chris C | MWLMaintI-27340 | Run | 3 | 24 |  | 24
05 MWL CPI/M Total | [9 empty] | 24
05 980GC | PD2.20 | 2019-11-14 | Operator Eval | Jensen Cameron | 980GC-106400 | Run | 3 | 24
| W7K00288 | 2019-02-08 | Operator Eval | Jensen Cameron | 980GC-108320 | Run | 3 | 24
| PD2.3 | 2019-11-19 | L5 Tuning and Performance Check #1 | Frederick Chris C | 980GC-110200 | Run | 7 | 56
|  |  |  | Sharp Jeremy T | 980GC-110200 | Run | 7 | 56
| PD2.RP | 2019-12-06 | Rimpull and Response Test | Frederick Chris C | 980GC-110230 | Run | 7 | 56
|  |  |  | Sharp Jeremy T | 980GC-110230 | Run | 7 | 56
05 980GC Total
05 966GC 2020 | SGW00201 | 2019-06-12 | L5 Tuning w/ Operator | Frederick Chris C | 966GC 2020-1590 | Run | 3 | 24
|  |  |  | Jensen Cameron | 966GC 2020-1590 | Run | 3 | 24
|  | 2019-05-29 | Rimpull/Response | Frederick Chris C | 966GC 2020-1525 | Run | 8 | 64
|  |  |  | Jensen Cameron | 966GC 2020-1525 | Run | 8 | 64
05 966GC 2020 Total
05 950XE | EJB00166 | 2019-03-13 | Rimpull/Response | Frederick Chris C | 950 Drive-1455 | Run | 10 | 80
|  |  |  | Leaders Royce E | 950 Drive-1455 | Run | 10 | 80
|  | 2019-04-10 | Productivity | Leaders Royce E | 950 Drive-1490 | Run | 7 | 56
05 950XE Total
Grand Total | [8 empty] | 144 | 112 | 120 | 120 | 72 | 120 | 88 | 104 | 184

## Data by Wk
Serial # | Project | PDGT Charge Number | Division | Section | WBS | WBS Name | WBS Path | Activity ID | Activity Name | Start | Finish | Role | Resource Name | Price / Unit | Original Duration | Budgeted Units | Remaining Units / Time | GPM Location | Spreadsheet Field | time axis 2018-10-21 to 2019-12-15
SM200101 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200101.7 | Operator Eval #3 | Testbed2.SM200101.7 | 966/972 AU20-4140 | Run | 2018-12-21 | 2019-01-03 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2018-12-16: 8; 2018-12-30: 16
SM200101 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200101.Altitude | Altitude Performance - C93B | Testbed2.SM200101.Altitude | 966/972 AU20-13335 | Run Response at Leadville (10000 ft) | 22-Oct-18 A | 2018-10-25 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 4 | 32 | 8/d | Field | Remaining Units | 2018-10-21: 32
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.L5 | L5 Performance Development/Tuning | Testbed2.MBY00100.L5 | 966/972 AU20-15550 | Run | 2019-03-07 | 2019-03-25 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 13 | 104 | 8/d | PPG | Remaining Units | 2019-03-03: 16; 2019-03-10: 40; 2019-03-17: 40; 2019-03-24: 8
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.L5 | L5 Performance Development/Tuning | Testbed2.MBY00100.L5 | 966/972 AU20-15550 | Run | 2019-03-07 | 2019-03-25 | L5 IPS Engineer | Goli Suman | $0.00/h | 13 | 104 | 8/d | PPG | Remaining Units | 2019-03-03: 16; 2019-03-10: 40; 2019-03-17: 40; 2019-03-24: 8
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Prod | 972XE Productivity Study (XE, LRC, Powershift) | Testbed2.MBY00100.Prod | 966/972 AU20-23817 | Run | 2019-06-12 | 2019-06-25 | L5 IPS Engineer | Goli Suman | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-06-09: 24; 2019-06-16: 40; 2019-06-23: 16
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Prod | 972XE Productivity Study (XE, LRC, Powershift) | Testbed2.MBY00100.Prod | 966/972 AU20-23817 | Run | 2019-06-12 | 2019-06-25 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-06-09: 24; 2019-06-16: 40; 2019-06-23: 16
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Altitude | Altitude Performance C93B | Testbed2.MBY00100.Altitude | 966/972 AU20-16150 | Run - Machine Checkout | 2019-11-15 | 2019-11-18 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-11-10: 8; 2019-11-17: 8
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Altitude | Altitude Performance C93B | Testbed2.MBY00100.Altitude | 966/972 AU20-16210 | Run Response at Denver (5000 ft) | 2019-11-26 | 2019-12-04 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 5 | 40 | 8/d | Field | Remaining Units | 2019-11-24: 16; 2019-12-01: 24
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Altitude | Altitude Performance C93B | Testbed2.MBY00100.Altitude | 966/972 AU20-16230 | Run Response at Leadville (10000 ft) | 2019-12-06 | 2019-12-11 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 4 | 32 | 8/d | Field | Remaining Units | 2019-12-01: 8; 2019-12-08: 24
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Altitude | Altitude Performance C93B | Testbed2.MBY00100.Altitude | 966/972 AU20-16240 | Run Baseline | 2019-11-19 | 2019-11-20 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-11-17: 16
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.L51 | L5 Performance Development/Tuning #2 | Testbed2.SM200102.L51 | 966/972 AU20-24182 | Run | 2018-12-14 | 2018-12-18 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2018-12-09: 8; 2018-12-16: 16
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.11-68635 | 972 HRC Cold System Performance Testing (Eglin) | Testbed2.SM200102.11-68635 | 966/972 AU20-24252 | Machine Checkout | 2018-10-25 | 2018-10-26 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2018-10-21: 16
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.11-68635 | 972 HRC Cold System Performance Testing (Eglin) | Testbed2.SM200102.11-68635 | 966/972 AU20-24217 | Run (11/2-15) | 2018-11-02 | 2018-11-15 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 10 | 80 | 8/d | Field | Remaining Units | 2018-10-28: 8; 2018-11-04: 40; 2018-11-11: 32
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Prod | 972 HRC Productivity Study (XE, LRC, Powershift) | Testbed2.SM200102.Prod | 966/972 AU20-23787 | Run | 2019-05-09 | 2019-05-22 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-05-05: 16; 2019-05-12: 40; 2019-05-19: 24
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.6 | Cold Weather Thermal Mgmt | Testbed2.SM200102.6 | 966/972 AU20-24692 | Run | 2019-02-19 | 2019-03-11 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 15 | 120 | 8/d | PPG | Remaining Units | 2019-02-17: 32; 2019-02-24: 40; 2019-03-03: 40; 2019-03-10: 8
W9900100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.W9900100.Altitude | Altitude Performance | Testbed2.W9900100.Altitude | 966/972 AU20-14090 | Run Response at Leadville (10000 ft) | 22-Oct-18 A | 2018-10-25 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 4 | 32 | 8/d | Field | Remaining Units | 2018-10-21: 32
W9900100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.W9900100.11-68635 | 972 LRC Cold System Performance Testing (Baudette Mn) | Testbed2.W9900100.11-68635 | 966/972 AU2020-1035 | Machine Checkout | 2019-03-08 | 2019-03-11 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-03-03: 8; 2019-03-10: 8
W9900100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.W9900100.11-68635 | 972 LRC Cold System Performance Testing (Baudette Mn) | Testbed2.W9900100.11-68635 | 966/972 AU2020-1000 | Run | 2019-03-15 | 2019-03-28 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 10 | 80 | 8/d | Field | Remaining Units | 2019-03-10: 8; 2019-03-17: 40; 2019-03-24: 32
W9900100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.W9900100.Prod | 972 Productivity Study (XE, LRC, Powershift) | Testbed2.W9900100.Prod | 966/972 AU20-23781 | Run | 2019-05-09 | 2019-05-22 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-05-05: 16; 2019-05-12: 40; 2019-05-19: 24
WLW00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.WLW00100.L5 | L5 Performance Development/Tuning | Testbed2.WLW00100.L5 | 966/972 AU20-25152 | Run | 2018-12-18 | 2019-01-04 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 7 | 56 | 8/d | PPG | Remaining Units | 2018-12-16: 32; 2018-12-30: 24
WLW00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.WLW00100.RP | 966 HRC Rimpull/Response C93B #2 | Testbed2.WLW00100.RP | 966/972 AU20-23715 | Run | 2019-04-25 | 2019-05-02 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 6 | 48 | 8/d | PPG | Remaining Units | 2019-04-21: 16; 2019-04-28: 32
XE400100 | 05 980 XE | 92-L5 | 70 | 16 | 05 980 XE.Proto.XE400100.18 | Cold Room Test (Baudette) | Proto.XE400100.18 | 980XE-11460 | Run | 2019-03-05 | 2019-03-25 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 15 | 120 | 8/d | Field | Remaining Units | 2019-03-03: 32; 2019-03-10: 40; 2019-03-17: 40; 2019-03-24: 8
MK700100 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Testbed2.MK700100.49 | Productivity | Testbed2.MK700100.49 | 980/982 AU20-24320 | Run | 2019-10-11 | 2019-10-24 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-10-06: 8; 2019-10-13: 40; 2019-10-20: 32
MK800100 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Testbed2.MK800100.RP | Rimpull Test | Testbed2.MK800100.RP | 980/982 AU20-25125 | Run | 2018-11-05 | 2018-11-08 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2018-11-04: 32
MK800100 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Testbed2.MK800100.3 | L5 Tuning w/Response Test #2 | Testbed2.MK800100.3 | 980/982 AU20-24520 | Run | 2018-12-13 | 2019-01-04 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2018-12-09: 16; 2018-12-16: 40; 2018-12-30: 24
MK800100 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Testbed2.MK800100.49 | Productivity | Testbed2.MK800100.49 | 980/982 AU20-25485 | Run | 2019-10-11 | 2019-10-24 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-10-06: 8; 2019-10-13: 40; 2019-10-20: 32
MK900100 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Testbed2.MK900100.RP | Rimpull Test | Testbed2.MK900100.RP | 980/982 AU20-24700 | Run | 2018-12-06 | 2018-12-11 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2018-12-02: 16; 2018-12-09: 16
P1.10 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Pilot.P1.10 | Operator Eval | Pilot.P1.10 | 980/982 AU20-6490 | Run | 2019-08-05 | 2019-08-07 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-08-04: 24
P1.6 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Pilot.P1.6 | Operator Eval #2 | Pilot.P1.6 | 980/982 AU20-7330 | Run | 2019-10-31 | 2019-11-04 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-10-27: 16; 2019-11-03: 8
EMB00251 | 05 BDL 2019 | 92-L5 | 70 | 16 | 05 BDL 2019.1.EMB00251.23 | 950M Stage 5 - L5 Checkout #2 | 1.EMB00251.23 | BDL19-1780 | Run | 2018-10-29 | 2018-11-02 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 5 | 40 | 8/d | PPG | Remaining Units | 2018-10-28: 40
EMB00251 | 05 BDL 2019 | 92-L5 | 70 | 16 | 05 BDL 2019.1.EMB00251.28 | 950M Stage 5 - L5 Checkout - Preprods | 1.EMB00251.28 | BDL19-1850 | Run | 2019-05-06 | 2019-05-09 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2019-05-05: 32
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.17 | UPT ETCA Steady State Performance Analysis | EP.SGW00201.17 | 966GC-106540 | Run - Cameron Jensen | 2019-03-11 | 2019-03-15 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 5 | 40 | 8/d | PPG | Remaining Units | 2019-03-10: 40
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.9 | L5 Tuning #2 | EP.SGW00201.9 | 966GC-1445 | Run | 2019-04-01 | 2019-04-10 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 8 | 64 | 8/d | PPG | Remaining Units | 2019-03-31: 40; 2019-04-07: 24
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.20 | Operator Eval | EP.SGW00201.20 | 966GC-106400 | Run | 2019-04-12 | 2019-04-16 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-04-07: 8; 2019-04-14: 16
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.34 | Cold Room Test | EP.SGW00201.34 | 966GC-105130 | Run (1/14-25) | 2019-02-20 | 2019-03-04 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 9 | 72 | 8/d | TC-L.I6Val.UNASSIGN | Remaining Units | 2019-02-17: 24; 2019-02-24: 40; 2019-03-03: 8
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.Altitude | Altitude Performance | EP.SGW00201.Altitude | 966GC-106290 | Run - Machine Checkout | 2019-05-09 | 2019-05-10 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-05-05: 16
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.Altitude | Altitude Performance | EP.SGW00201.Altitude | 966GC-106350 | Run Response at Denver (5000 ft) | 2019-05-16 | 2019-05-22 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 5 | 40 | 8/d | PPG | Remaining Units | 2019-05-12: 16; 2019-05-19: 24
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.Altitude | Altitude Performance | EP.SGW00201.Altitude | 966GC-106370 | Run Response at Leadville (10000 ft) | 2019-05-24 | 2019-05-30 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2019-05-19: 8; 2019-05-26: 24
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.Altitude | Altitude Performance | EP.SGW00201.Altitude | 966GC-106390 | Run Baseline | 2019-06-05 | 2019-06-06 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-06-02: 16
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.11-68635 | 972XE TB Cold System Performance Testing (Baudette Mn) | Testbed2.MBY00100.11-68635 | 966/972 AU20-8010 | Run | 2019-05-07 | 2019-05-28 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 15 | 120 | 8/d | Field | Remaining Units | 2019-05-05: 32; 2019-05-12: 40; 2019-05-19: 40; 2019-05-26: 8
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.11-68635 | 972XE TB Cold System Performance Testing (Baudette Mn) | Testbed2.MBY00100.11-68635 | 966/972 AU20-8080 | Machine Checkout | 2019-04-30 | 2019-05-01 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-04-28: 16
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.11-68635 | 972XE TB Cold System Performance Testing (Baudette Mn) | Testbed2.MBY00100.11-68635 | 966/972 AU20-8010 | Run | 2019-05-07 | 2019-05-28 | L5 IPS Engineer | Goli Suman | $0.00/h | 15 | 120 | 8/d | Field | Remaining Units | 2019-05-05: 32; 2019-05-12: 40; 2019-05-19: 40; 2019-05-26: 8
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.11-68635 | 972XE TB Cold System Performance Testing (Baudette Mn) | Testbed2.MBY00100.11-68635 | 966/972 AU20-8080 | Machine Checkout | 2019-04-30 | 2019-05-01 | L5 IPS Engineer | Goli Suman | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-04-28: 16
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.11 | S11 SW Checkout | Testbed2.MBY00100.11 | 966/972 AU20-24482 | Run - L5 Checkout | 2018-11-14 | 2018-12-05 | L5 IPS Engineer | Goli Suman | $0.00/h | 14 | 112 | 8/d | PPG | Remaining Units | 2018-11-11: 24; 2018-11-18: 24; 2018-11-25: 40; 2018-12-02: 24
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.11 | S11 SW Checkout | Testbed2.MBY00100.11 | 966/972 AU20-24482 | Run - L5 Checkout | 2018-11-14 | 2018-12-05 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 14 | 112 | 8/d | PPG | Remaining Units | 2018-11-11: 24; 2018-11-18: 24; 2018-11-25: 40; 2018-12-02: 24
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Altitude | Altitude Performance C93B | Testbed2.MBY00100.Altitude | 966/972 AU20-16150 | Run - Machine Checkout | 2019-11-15 | 2019-11-18 | L5 IPS Engineer | Goli Suman | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-11-10: 8; 2019-11-17: 8
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Altitude | Altitude Performance C93B | Testbed2.MBY00100.Altitude | 966/972 AU20-16240 | Run Baseline | 2019-11-19 | 2019-11-20 | L5 IPS Engineer | Goli Suman | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-11-17: 16
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Altitude | Altitude Performance C93B | Testbed2.MBY00100.Altitude | 966/972 AU20-16210 | Run Response at Denver (5000 ft) | 2019-11-26 | 2019-12-04 | L5 IPS Engineer | Goli Suman | $0.00/h | 5 | 40 | 8/d | Field | Remaining Units | 2019-11-24: 16; 2019-12-01: 24
MBY00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.MBY00100.Altitude | Altitude Performance C93B | Testbed2.MBY00100.Altitude | 966/972 AU20-16230 | Run Response at Leadville (10000 ft) | 2019-12-06 | 2019-12-11 | L5 IPS Engineer | Goli Suman | $0.00/h | 4 | 32 | 8/d | Field | Remaining Units | 2019-12-01: 8; 2019-12-08: 24
WLW00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.WLW00100.RP1 | 966 HRC Rimpull/Response C93B #1 | Testbed2.WLW00100.RP1 | 966/972 AU20-26300 | Run | 2019-01-14 | 2019-01-17 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2019-01-13: 32
WL900100 | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.WL900100.41 | L5 Performance Dev/Tuning #1 | Testbed2.WL900100.41 | 950/962 AU20-21790 | Run | 2019-07-05 | 2019-07-18 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-06-30: 8; 2019-07-07: 40; 2019-07-14: 32
TB2.41 | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.TB2.41 | L5 Performance Dev/Tuning #1 | Testbed2.TB2.41 | 950/962 AU20-24140 | Run | 2019-06-20 | 2019-07-03 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-06-16: 16; 2019-06-23: 40; 2019-06-30: 24
TB2.RP | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.TB2.RP | Rimpull/Response | Testbed2.TB2.RP | 950/962 AU20-22410 | Run | 2019-07-11 | 2019-07-16 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2019-07-07: 16; 2019-07-14: 16
TB2.Cold | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.TB2.ColdRoom | Cold Room Test | Testbed2.TB2.ColdRoom | 950/962 AU20-22580 | Run | 2019-10-28 | 2019-12-10 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 30 | 240 | 8/d | TC-L.I6Val.UNASSIGN | Remaining Units | 2019-10-27: 40; 2019-11-03: 40; 2019-11-10: 40; 2019-11-17: 40; 2019-11-24: 24; 2019-12-01: 40; 2019-12-08: 16
TB3.41 | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.TB3.41 | L5 Performance Dev/Tuning #1 | Testbed2.TB3.41 | 950/962 AU20-24830 | Run | 2019-09-26 | 2019-10-16 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 15 | 120 | 8/d | PPG | Remaining Units | 2019-09-22: 16; 2019-09-29: 40; 2019-10-06: 40; 2019-10-13: 24
EJB00166 | 05 950XE | 92-L5 | 70 | 16 | 05 950XE.TB.EJB00166.RP | Rimpull/Response | TB.EJB00166.RP | 950 Drive-1455 | Run | 2019-03-13 | 2019-03-26 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-03-10: 24; 2019-03-17: 40; 2019-03-24: 16
EJB00166 | 05 950XE | 92-L5 | 70 | 16 | 05 950XE.TB.EJB00166.23 | Productivity | TB.EJB00166.23 | 950 Drive-1490 | Run | 2019-04-10 | 2019-04-18 | Performance/Controls Engineer | Leaders Royce E | $0.00/h | 7 | 56 | 8/d | PPG | Remaining Units | 2019-04-07: 24; 2019-04-14: 32
PD2.20 | 05 980GC | 92-L5 | 70 | 16 | 05 980GC.PD.PD2.20 | Operator Eval | PD.PD2.20 | 980GC-106400 | Run | 2019-11-14 | 2019-11-18 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-11-10: 16; 2019-11-17: 8
W7K00288 | 05 980GC | 92-L5 | 70 | 16 | 05 980GC.TB.W7K00288.20 | Operator Eval | TB.W7K00288.20 | 980GC-108320 | Run | 2019-02-08 | 2019-02-12 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-02-03: 8; 2019-02-10: 16
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.11 | L5 Tuning w/ Operator | EP.SGW00201.11 | 966GC-108370 | Run | 2018-11-09 | 2018-11-13 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2018-11-04: 8; 2018-11-11: 16
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Altitude | 972 HRC Altitude Test #2 | Testbed2.SM200102.Altitude | 966/972 AU20-26515 | Run - Machine Checkout | 2019-07-03 | 2019-07-05 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-06-30: 16
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Altitude | 972 HRC Altitude Test #2 | Testbed2.SM200102.Altitude | 966/972 AU20-26545 | Run Response at Denver (5000 ft) (7/15-19) | 2019-07-15 | 2019-07-19 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 5 | 40 | 8/d | Field | Remaining Units | 2019-07-14: 40
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Altitude | 972 HRC Altitude Test #2 | Testbed2.SM200102.Altitude | 966/972 AU20-26555 | Run Response at Leadville (10000 ft) | 2019-07-22 | 2019-07-25 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 4 | 32 | 8/d | Field | Remaining Units | 2019-07-21: 32
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Altitude | 972 HRC Altitude Test #2 | Testbed2.SM200102.Altitude | 966/972 AU20-26565 | Run Baseline | 2019-07-08 | 2019-07-09 | Performance/Controls Engineer | Anderson Kirk E | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-07-07: 16
PD2.3 | 05 980GC | 92-L5 | 70 | 16 | 05 980GC.PD.PD2.3 | L5 Tuning and Performance Check #1 | PD.PD2.3 | 980GC-110200 | Run | 2019-11-19 | 2019-11-27 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 7 | 56 | 8/d | PPG | Remaining Units | 2019-11-17: 32; 2019-11-24: 24
PD2.RP | 05 980GC | 92-L5 | 70 | 16 | 05 980GC.PD.PD2.RP | Rimpull and Response Test | PD.PD2.RP | 980GC-110230 | Run | 2019-12-06 | 2019-12-16 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 7 | 56 | 8/d | PPG | Remaining Units | 2019-12-01: 8; 2019-12-08: 40; 2019-12-15: 8
SGW00201 | 05 966GC 2020 | 92-L5 | 70 | 16 | 05 966GC 2020.TB.SGW00201.RP | Rimpull/Response | TB.SGW00201.RP | 966GC 2020-1525 | Run | 2019-05-29 | 2019-06-07 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 8 | 64 | 8/d | PPG | Remaining Units | 2019-05-26: 24; 2019-06-02: 40
SGW00201 | 05 966GC 2020 | 92-L5 | 70 | 16 | 05 966GC 2020.TB.SGW00201.11 | L5 Tuning w/ Operator | TB.SGW00201.11 | 966GC 2020-1590 | Run | 2019-06-12 | 2019-06-14 | Performance/Controls Engineer | Jensen Cameron | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-06-09: 24
XE300100 | 05 980 XE | 92-L5 | 70 | 16 | 05 980 XE.Proto.XE300100.25 | L4/L5 Development | Proto.XE300100.25 | 980XE-12460 | Run | 2019-01-24 | 2019-02-13 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 15 | 120 | 8/d | PPG | Remaining Units | 2019-01-20: 16; 2019-01-27: 40; 2019-02-03: 40; 2019-02-10: 24
XE400100 | 05 980 XE | 92-L5 | 70 | 16 | 05 980 XE.Proto.XE400100.18 | Cold Room Test (Baudette) | Proto.XE400100.18 | 980XE-11090 | Machine Checkout - L4/L5 | 2019-02-25 | 2019-02-26 | Performance/Controls Engineer | Sharp Jeremy T | $0.00/h | 2 | 16 | 8/d |  | Remaining Units | 2019-02-24: 16
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.9 | L5 Tuning #2 | EP.SGW00201.9 | 966GC-1445 | Run | 2019-04-01 | 2019-04-10 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 8 | 64 | 8/d | PPG | Remaining Units | 2019-03-31: 40; 2019-04-07: 24
SM200101 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200101.Altitude | Altitude Performance - C93B | Testbed2.SM200101.Altitude | 966/972 AU20-13335 | Run Response at Leadville (10000 ft) | 22-Oct-18 A | 2018-10-25 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | Field | Remaining Units | 2018-10-21: 32
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.L51 | L5 Performance Development/Tuning #2 | Testbed2.SM200102.L51 | 966/972 AU20-24182 | Run | 2018-12-14 | 2018-12-18 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2018-12-09: 8; 2018-12-16: 16
W9900100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.W9900100.Altitude | Altitude Performance | Testbed2.W9900100.Altitude | 966/972 AU20-14090 | Run Response at Leadville (10000 ft) | 22-Oct-18 A | 2018-10-25 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | Field | Remaining Units | 2018-10-21: 32
WLW00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.WLW00100.L5 | L5 Performance Development/Tuning | Testbed2.WLW00100.L5 | 966/972 AU20-25152 | Run | 2018-12-18 | 2019-01-04 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 7 | 56 | 8/d | PPG | Remaining Units | 2018-12-16: 32; 2018-12-30: 24
WLW00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.WLW00100.RP | 966 HRC Rimpull/Response C93B #2 | Testbed2.WLW00100.RP | 966/972 AU20-23715 | Run | 2019-04-25 | 2019-05-02 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 6 | 48 | 8/d | PPG | Remaining Units | 2019-04-21: 16; 2019-04-28: 32
MK800100 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Testbed2.MK800100.3 | L5 Tuning w/Response Test #2 | Testbed2.MK800100.3 | 980/982 AU20-24520 | Run | 2018-12-13 | 2019-01-04 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2018-12-09: 16; 2018-12-16: 40; 2018-12-30: 24
MK900100 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Testbed2.MK900100.RP | Rimpull Test | Testbed2.MK900100.RP | 980/982 AU20-24700 | Run | 2018-12-06 | 2018-12-11 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2018-12-02: 16; 2018-12-09: 16
EMB00251 | 05 BDL 2019 | 92-L5 | 70 | 16 | 05 BDL 2019.1.EMB00251.23 | 950M Stage 5 - L5 Checkout #2 | 1.EMB00251.23 | BDL19-1780 | Run | 2018-10-29 | 2018-11-02 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 5 | 40 | 8/d | PPG | Remaining Units | 2018-10-28: 40
EMB00251 | 05 BDL 2019 | 92-L5 | 70 | 16 | 05 BDL 2019.1.EMB00251.28 | 950M Stage 5 - L5 Checkout - Preprods | 1.EMB00251.28 | BDL19-1850 | Run | 2019-05-06 | 2019-05-09 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2019-05-05: 32
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.4 | SCL Verification Operator Eval | EP.SGW00201.4 | 966GC-1536 | Run | 2019-07-11 | 2019-07-12 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-07-07: 16
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.Altitude | Altitude Performance | EP.SGW00201.Altitude | 966GC-106290 | Run - Machine Checkout | 2019-05-09 | 2019-05-10 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-05-05: 16
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.Altitude | Altitude Performance | EP.SGW00201.Altitude | 966GC-106350 | Run Response at Denver (5000 ft) | 2019-05-16 | 2019-05-22 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 5 | 40 | 8/d | PPG | Remaining Units | 2019-05-12: 16; 2019-05-19: 24
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.Altitude | Altitude Performance | EP.SGW00201.Altitude | 966GC-106370 | Run Response at Leadville (10000 ft) | 2019-05-24 | 2019-05-30 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2019-05-19: 8; 2019-05-26: 24
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.Altitude | Altitude Performance | EP.SGW00201.Altitude | 966GC-106390 | Run Baseline | 2019-06-05 | 2019-06-06 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-06-02: 16
MK800100 | 05 980/982 AU2020 | 92-L5 | 70 | 16 | 05 980/982 AU2020.Testbed2.MK800100.RP | Rimpull Test | Testbed2.MK800100.RP | 980/982 AU20-25125 | Run | 2018-11-05 | 2018-11-08 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2018-11-04: 32
WLW00100 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.WLW00100.RP1 | 966 HRC Rimpull/Response C93B #1 | Testbed2.WLW00100.RP1 | 966/972 AU20-26300 | Run | 2019-01-14 | 2019-01-17 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2019-01-13: 32
M5T00101 | 05 MWL CPI/M | 92-L5 | 70 | 16 | 05 MWL CPI/M.5.M5T00101.6 | L5 Checkout | 5.M5T00101.6 | MWLMaintI-27340 | Run | 2018-10-29 | 2018-10-31 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2018-10-28: 24
WL900100 | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.WL900100.41 | L5 Performance Dev/Tuning #1 | Testbed2.WL900100.41 | 950/962 AU20-21790 | Run | 2019-07-05 | 2019-07-18 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-06-30: 8; 2019-07-07: 40; 2019-07-14: 32
TB2.41 | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.TB2.41 | L5 Performance Dev/Tuning #1 | Testbed2.TB2.41 | 950/962 AU20-24140 | Run | 2019-06-20 | 2019-07-03 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-06-16: 16; 2019-06-23: 40; 2019-06-30: 24
TB2.RP | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.TB2.RP | Rimpull/Response | Testbed2.TB2.RP | 950/962 AU20-22410 | Run | 2019-07-11 | 2019-07-16 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | PPG | Remaining Units | 2019-07-07: 16; 2019-07-14: 16
TB3.41 | 05 950/962 AU2020 | 92-L5 | 70 | 16 | 05 950/962 AU2020.Testbed2.TB3.41 | L5 Performance Dev/Tuning #1 | Testbed2.TB3.41 | 950/962 AU20-24830 | Run | 2019-09-26 | 2019-10-16 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 15 | 120 | 8/d | PPG | Remaining Units | 2019-09-22: 16; 2019-09-29: 40; 2019-10-06: 40; 2019-10-13: 24
EJB00166 | 05 950XE | 92-L5 | 70 | 16 | 05 950XE.TB.EJB00166.RP | Rimpull/Response | TB.EJB00166.RP | 950 Drive-1455 | Run | 2019-03-13 | 2019-03-26 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-03-10: 24; 2019-03-17: 40; 2019-03-24: 16
SGW00201 | 05 966GC | 92-L5 | 70 | 16 | 05 966GC.EP.SGW00201.11 | L5 Tuning w/ Operator | EP.SGW00201.11 | 966GC-108370 | Run | 2018-11-09 | 2018-11-13 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2018-11-04: 8; 2018-11-11: 16
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Altitude | 972 HRC Altitude Test #2 | Testbed2.SM200102.Altitude | 966/972 AU20-26515 | Run - Machine Checkout | 2019-07-03 | 2019-07-05 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-06-30: 16
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Altitude | 972 HRC Altitude Test #2 | Testbed2.SM200102.Altitude | 966/972 AU20-26545 | Run Response at Denver (5000 ft) (7/15-19) | 2019-07-15 | 2019-07-19 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 5 | 40 | 8/d | Field | Remaining Units | 2019-07-14: 40
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Altitude | 972 HRC Altitude Test #2 | Testbed2.SM200102.Altitude | 966/972 AU20-26555 | Run Response at Leadville (10000 ft) | 2019-07-22 | 2019-07-25 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 4 | 32 | 8/d | Field | Remaining Units | 2019-07-21: 32
SM200102 | 05 966/972 AU2020 | 92-L5 | 70 | 16 | 05 966/972 AU2020.Testbed2.SM200102.Altitude | 972 HRC Altitude Test #2 | Testbed2.SM200102.Altitude | 966/972 AU20-26565 | Run Baseline | 2019-07-08 | 2019-07-09 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 2 | 16 | 8/d | PPG | Remaining Units | 2019-07-07: 16
PD2.3 | 05 980GC | 92-L5 | 70 | 16 | 05 980GC.PD.PD2.3 | L5 Tuning and Performance Check #1 | PD.PD2.3 | 980GC-110200 | Run | 2019-11-19 | 2019-11-27 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 7 | 56 | 8/d | PPG | Remaining Units | 2019-11-17: 32; 2019-11-24: 24
PD2.RP | 05 980GC | 92-L5 | 70 | 16 | 05 980GC.PD.PD2.RP | Rimpull and Response Test | PD.PD2.RP | 980GC-110230 | Run | 2019-12-06 | 2019-12-16 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 7 | 56 | 8/d | PPG | Remaining Units | 2019-12-01: 8; 2019-12-08: 40; 2019-12-15: 8
SGW00201 | 05 966GC 2020 | 92-L5 | 70 | 16 | 05 966GC 2020.TB.SGW00201.RP | Rimpull/Response | TB.SGW00201.RP | 966GC 2020-1525 | Run | 2019-05-29 | 2019-06-07 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 8 | 64 | 8/d | PPG | Remaining Units | 2019-05-26: 24; 2019-06-02: 40
SGW00201 | 05 966GC 2020 | 92-L5 | 70 | 16 | 05 966GC 2020.TB.SGW00201.11 | L5 Tuning w/ Operator | TB.SGW00201.11 | 966GC 2020-1590 | Run | 2019-06-12 | 2019-06-14 | L5 IPS Engineer | Frederick Chris C | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-06-09: 24
MBY00100 | 05 966/972 AU2020 | 92-L5 | 314 | 2 | 05 966/972 AU2020.Testbed2.MBY00100.12 | Dig Assist Development | Testbed2.MBY00100.12 | 966/972 AU20-25480 | Run (Tinker) | 2019-06-27 | 2019-07-11 | L5 IPS Engineer | Tinker Matt M | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2019-06-23: 16; 2019-06-30: 32; 2019-07-07: 32
MBY00100 | 05 966/972 AU2020 | 92-L5 | 314 | 2 | 05 966/972 AU2020.Testbed2.MBY00100.9 | Dig Assist Operator Eval | Testbed2.MBY00100.9 | 966/972 AU20-25490 | Run | 2019-07-12 | 2019-07-16 | L5 IPS Engineer | Tinker Matt M | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-07-07: 8; 2019-07-14: 16
XE300100 | 05 980 XE | 92-L5 | 314 | 2 | 05 980 XE.Proto.XE300100.21 | Dig Assist Development | Proto.XE300100.21 | 980XE-11350 | Run (Goli) | 2018-11-16 | 2018-12-03 | L5 IPS Engineer | Tinker Matt M | $0.00/h | 10 | 80 | 8/d | PPG | Remaining Units | 2018-11-11: 8; 2018-11-18: 24; 2018-11-25: 40; 2018-12-02: 8
XE300100 | 05 980 XE | 92-L5 | 314 | 2 | 05 980 XE.Proto.XE300100.20 | Dig Assist Operator Eval | Proto.XE300100.20 | 980XE-11360 | Run | 2018-12-10 | 2018-12-12 | L5 IPS Engineer | Tinker Matt M | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2018-12-09: 24
MK800100 | 05 980/982 AU2020 | 92-L5 | 314 | 2 | 05 980/982 AU2020.Testbed2.MK800100.21 | Dig Assist Operator Eval | Testbed2.MK800100.21 | 980/982 AU20-26440 | Run | 2019-01-07 | 2019-01-09 | L5 IPS Engineer | Tinker Matt M | $0.00/h | 3 | 24 | 8/d | PPG | Remaining Units | 2019-01-06: 24