## sheet1
| Activity ID | Start | Finish | STCW |  |  |  |  | Min | max
| 980GC Milestones | 2019-02-28 | 2022-09-08 |  | 2019-02-28 | 2022-09-08 |  |  | 2019-02-28 | 2022-09-08
GW | Launch | 2019-02-28 | 2019-02-28 |  |  |  |  | 2019-02-28
DR | DR 1/2 | 2019-07-27 | 2019-07-31 |  |  |  |  | 2022-09-08
GW | GW 1/2 | 2019-11-19 | 2019-11-21
GW | GW 3/4 | 2020-02-15 | 2020-02-16
QG | Quality Gate # 1 | 2020-02-05 | 2020-02-07
FR | PD Build | 2020-02-14 | 2020-03-20
FR | PD Ship to PPG | 2020-03-30 | 2020-06-23
FR | 100% Pilot Design Freeze | 2020-11-15 | 2020-11-17 |  |  | 1.714% | 6.25%
FR | 100% Pilot EDS Freeze | 2021-01-14 | 2021-01-16
GW | GW 5 | 2021-06-15 | 2021-06-17
FR | Pilot Build | 2021-06-07 | 2021-08-05
FR | FF | 2021-08-09 | 2022-01-16
FR | 100% Production DF Freeze | 2022-01-15 | 2022-01-15
FR | 100% Production EDS Freeze | 2022-03-01 | 2022-03-03
GW | GW 5.5 | 2022-05-18 | 2022-05-18
QG | Quality Gate # 2 | 2021-11-01 | 2021-11-01
GW | GW 6 | 2022-09-08 | 2022-09-08
FR | 1st Production | 2022-06-24 | 2022-06-24
| 980GC SW Milestones | 2020-02-03 | 2020-11-02
SW | Release # 1 | 2020-02-03 | 2020-02-03
SW | Release # 2 | 2020-06-01 | 2020-06-01
SW | Release # 3 | 2020-08-03 | 2020-08-03
SW | Trans SW | 2020-10-12 | 2020-10-12
SW | Release # 4 | 2020-11-02 | 2020-11-02
| 980GC TIC Report Milestones | 2020-12-24 | 2022-03-23
Safety and Regs-Pilot | Brake-ISO 3450 | 2020-12-24 | 2020-12-25
Safety and Regs-Pilot | Steering-ISO 5010 | 2021-01-20 | 2021-01-21
Safety and Regs-Pilot | Stg V EMC | 2021-05-16 | 2021-05-17
Safety and Regs-Pilot | Sound- Back-up Alarm, Horn-ISO 9566 | 2021-01-17 | 2021-01-18
Safety and Regs-Production | Brake-ISO 3450 Certification | 2021-11-29 | 2021-11-30
Safety and Regs-Production | Steering-ISO 5010 Certification | 2021-12-17 | 2021-12-18
Safety and Regs-Production | EMC Certification | 2022-02-21 | 2022-02-22
Safety and Regs-Production | Articulation Frame Certification | 2022-03-12 | 2022-03-13
Safety and Regs-Production | Sound- Back-up Alarm, Horn-ISO 9566 Certification | 2022-03-22 | 2022-03-23
| PPG 980GC TB (W7K00288) | 2019-05-13 | 2019-11-22
Machine Build | 980GC TB Machine Build (hyd pump, implement valve) | 2019-05-13 | 2019-05-24
Machine Check | Machine Checkout STP-64 | 2019-05-28 | 2019-05-30
Machine Build | Machine Update | 2019-10-01 | 2019-10-01
Opr Eval | Operator Eval # 2 | 2019-10-02 | 2019-10-02
Hydraulics | Hydraulic Development (Setup/Run/Teardown) | 2019-11-04 | 2019-11-22
| QPG 980GC LRC PD#1 (SN) | 2020-03-16 | 2021-03-02
Machine Build | PD Machine Build | 2020-03-16 | 2020-04-24
Machine Check | Machine Checkout STP-64 | 2020-04-27 | 2020-05-11
SW | Software Checkout #1 (STP 230) Ver 01; Telematics SW (Gen A6N1+PL243/PL083) | 2020-05-12 | 2020-05-22
NVH | Sound Testing (1st Pass screening) | 2020-05-25 | 2020-06-16
Performance2 | L5 Tuning and Performance Check | 2020-06-17 | 2020-07-01
Opr Eval | Operator Eval #1 | 2020-07-02 | 2020-07-06
Hydraulics | Hydraulic Test ( Steering Pump Perf)+ Fan calibration | 2020-07-07 | 2020-08-27
SW | Software Checkout #2 | 2020-08-28 | 2020-09-03
Opr Eval | Operator Eval #2 | 2020-09-04 | 2020-09-08
Cooling2 | LRC Water Flow Test & System (STP 151 & 155) | 2020-09-09 | 2020-09-22
Cooling3 | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration and Fan calibration | 2020-09-23 | 2020-09-30
Holiday | China National Holiday | 2020-10-01 | 2020-10-07
Cooling3 | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration and Fan calibration | 2020-10-08 | 2020-10-23
Issue | Issue resolution # 1 | 2020-10-26 | 2020-10-28
Engine | LRC STP 401 Engine Audit | 2020-10-29 | 2020-11-02
Safety and Regs | ISO 3450 Brake Feasibility | 2020-11-03 | 2020-11-24
Safety and Regs | ISO 5010 Steering Feasibility | 2020-11-25 | 2020-12-21
Elec | Electric Load Study (Alt Charging capacity) | 2020-12-22 | 2020-12-25
Endurance | 980GC Endurance 0-500 hrs+ Inspection (12 hr/day) | 2020-12-28 | 2021-02-11
Holiday | China New Year | 2021-02-11 | 2021-02-18
SW | Software Checkout #3 | 2021-02-19 | 2021-02-24
Inspection | Endurance Inspection | 2021-02-25 | 2021-03-02
| PPG 980GC Stg V HRC PD#2 (SN) | 2020-02-17 | 2021-10-07
Machine Build | PD Machine Build | 2020-02-17 | 2020-03-22
Machine Check | QPG Machine Check | 2020-03-23 | 2020-03-27
Machine Build | Ship Machine to PPG | 2020-03-29 | 2020-06-10
Machine Check | Machine Checkout STP-64 | 2020-06-11 | 2020-06-16
SW | SW Checkout # 1 | 2020-06-17 | 2020-06-24
Safety and Regs | Safety & Service Audit | 2020-06-25 | 2020-06-25
Elec | Harness routing Audit | 2020-06-26 | 2020-06-26
Performance1 | L5 Tuning and Performance Check #1 | 2020-06-25 | 2020-07-06
Engine | Engine and SW Check | 2020-07-07 | 2020-07-14
Performance5 | Engine Exhaust AFT controls | 2020-07-15 | 2020-07-17
HVAC | HVAC Charge Checkout | 2020-07-20 | 2020-07-23
NVH | Sound Screening | 2020-07-24 | 2020-07-27
Transmission | XMSN Tuning | 2020-07-28 | 2020-08-11
SW | Software Checkout #2 (STP 230) | 2020-08-12 | 2020-08-19
Issue | Issue resolution # 1 | 2020-08-20 | 2020-09-04
Performance2 | Rimpull and Response Test | 2020-09-07 | 2020-09-23
Cooling1 | STP-153 (Airflow Testing) | 2020-09-24 | 2020-10-01
Cooling2 | STP-151 & 155 (Water Flow & System Test) | 2020-10-02 | 2020-10-14
Cooling3 | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT + Fuel Sensor Calibration | 2020-10-15 | 2020-11-11 | Jan 14 2021 Pilot EDS Freeze
Engine | STP 401 HRC Engine Audit | 2020-11-12 | 2020-11-23
Holiday | US Thanksgiving | 2020-11-24 | 2020-12-01
NVH | Sound Testing (Plus Hyd & Exhaust Characterization) | 2020-12-08 | 2020-12-15
Holiday | US Christmas and New Year Day Holiday | 2020-12-18 | 2021-01-04
EIC2 | Dust Ejector Measurement | 2021-01-11 | 2021-01-14
EIC1 | Stage V Engine Install MER | 2021-01-05 | 2021-01-19
Performance3 | Stage 5 Engine TC-L Cold Room | 2021-01-20 | 2021-03-11
Issue | Issue resolution # 2 | 2021-03-12 | 2021-03-29
Safety and Regs | EN 13309 EMC Testing- Engg Test | 2021-03-30 | 2021-04-08
SW | Software Checkout #3 (STP 230)+ Endurance | 2021-04-09 | 2021-04-16
Performance1 | L5 Tuning with Operator # 1 | 2021-04-19 | 2021-04-26
Commercial | Machine D&A | 2021-05-20 | 2021-10-07
| PPG 980GC T3 LRC PD#3 (SN) | 2020-03-02 | 2021-05-31
Machine Build | PD Machine Build | 2020-03-02 | 2020-04-05
Machine Check | QPG Machine Check | 2020-04-06 | 2020-04-10
Machine Build | Ship Machine to PPG | 2020-04-12 | 2020-06-25
Machine Check | Machine Checkout STP-64 | 2020-06-26 | 2020-07-01
SW | SW Checkout # 1 | 2020-07-02 | 2020-07-09
Performance2 | L5 Tuning and Performance Operator Eval # 1 (Shift Performance) | 2020-07-02 | 2020-07-20
Engine | Engine and SW Check | 2020-07-21 | 2020-07-28
Issue | Issue resolution # 1 | 2020-07-29 | 2020-08-07
Transmission | XMSN Tuning | 2020-08-10 | 2020-08-21
Performance2 | Rimpull and Response Test | 2020-08-25 | 2020-09-03
Light Structures | Light Fab and Heavy Structure OMSA Hood & Cooling Pkg & MER- 200 channels | 2020-09-04 | 2020-11-05
Hydraulics | Hydraulic Test (Service Brake Modulation)+ Opr Eval | 2020-11-06 | 2020-11-20
Holiday | US Thanksgiving | 2020-11-23 | 2020-11-30
Hydraulics | Hydraulic Test (Service Brake Modulation)+ Opr Eval | 2020-12-01 | 2020-12-18
Holiday | US Christmas and New Year Day Holiday | 2020-12-22 | 2021-01-04
SW | Software Checkout #2 (STP 230)+ Endurance | 2021-01-05 | 2021-01-12
Performance6 | LRC Engine Altitude (Start in 2021) | 2021-04-23 | 2021-05-31
| PPG 980GC HRC Pilot #1 (SN) | 2021-06-07 | 2022-03-07
Machine Build | Pilot Machine Build | 2021-06-07 | 2021-08-05
Machine Build | Ship Machine to PPG | 2021-08-06 | 2021-10-05
Machine Check | Machine Checkout STP-64 | 2021-10-06 | 2021-10-11
SW | SW Checkout #1 | 2021-10-12 | 2021-10-19
NVH | Sound Testing (Issue Resolution Not meeting Rqmts) | 2021-10-20 | 2021-10-27
Performance | L5 Checkout and Performance Check + Oper eval | 2021-10-28 | 2021-11-09
SW | SW Checkout #2 | 2021-11-10 | 2021-11-15
Opr Eval | Operator Eval #2 | 2021-11-16 | 2021-11-19
Holiday | US Thanksgiving | 2021-11-22 | 2021-11-29
Light Structures | OMSA Light Fabs Hood # 2 | 2021-11-30 | 2021-12-14
Holiday | US Christmas and New Year Day Holiday | 2021-12-17 | 2022-01-03
Light Structures | OMSA Light Fabs Hood # 2 | 2022-01-04 | 2022-02-01
SW | Software Checkout #3 | 2022-02-02 | 2022-02-09
Safety and Regs | EN 13309 EMC Testing-HRC-CERT | 2022-02-10 | 2022-02-21
Performance5 | Engg Perf Productivity-Baseline | 2022-02-22 | 2022-03-07
| QPG 980GC LRC Pilot #2 (SN) | 2021-06-07 | 2022-08-23
Machine Build | Pilot Machine Build | 2021-06-07 | 2021-08-06
Machine Check | Machine Checkout STP-64 | 2021-08-09 | 2021-08-23
SW | Software Checkout | 2021-08-24 | 2021-09-03
Safety and Regs | ISO 3450 Brake- CERT | 2021-09-06 | 2021-09-30
Holiday | China National Holiday | 2021-10-01 | 2021-10-07
Safety and Regs | ISO 5010- HMU CERT | 2021-10-01 | 2021-10-18
Safety and Regs | EMC CERT | 2021-10-19 | 2021-11-04
Hydraulics | Hydraulic Signature Test- Documentation | 2021-11-05 | 2021-12-20
NVH | Sound Testing- ISO 9533, HAWB | 2021-12-21 | 2021-12-30
Safety and Regs | ISO 10570 Articulation Lock | 2021-12-31 | 2022-01-11
Safety and Regs | ISO 5006 (Virtual Audit) | 2022-01-12 | 2022-01-21
Holiday | China New Year | 2022-01-30 | 2022-02-07
Endurance1 | 980GC Endurance 0-500 hrs+ 250 hr Inspections | 2022-02-08 | 2022-04-13
Endurance2 | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | 2022-04-14 | 2022-06-17
Endurance3 | 980GC Endurance 1001-1500 hrs+ 250 hr inspections | 2022-06-20 | 2022-08-23
Formulas:
Start = MIN([Start, row below]:C20)
Start = [Finish, row above]+4
Finish = MAX([Finish, row below]:D19)
Finish = [Start]+4
Min = MIN([Start],C21,C27,C37,C43,C66,C98,C116,C132)
max = MAX([Finish],D21,D27,D37,D43,D66,D98,D116,D132)
Note on B104: Viresh B Shah: Trans Control Throttle; Opr Eval; Xsmn Shifting Quality-Opr Eval; Machine Stability chk-Opr Eval;Trans Neutralizer Functional Check

## calendar
Machine S/N | Phase | 2019-02-25 |  | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 |  | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 |  | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 |  |  | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 |  | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 |  | 2020-02-10 |  | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 |  | 2020-03-30 | 2020-04-06 |  | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 |  | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 |  | 2020-06-15 |  | 2020-06-22 |  |  | 2020-06-29 |  | 2020-07-06 |  | 2020-07-13 |  | 2020-07-20 |  |  | 2020-07-27 |  |  | 2020-08-03 | 2020-08-10 |  | 2020-08-17 |  | 2020-08-24 |  |  | 2020-08-31 |  | 2020-09-07 |  | 2020-09-14 | 2020-09-21 |  |  | 2020-09-28 |  |  | 2020-10-05 |  | 2020-10-12 |  | 2020-10-19 | 2020-10-26 |  | 2020-11-02 |  |  | 2020-11-09 |  |  | 2020-11-16 | 2020-11-23 |  |  | 2020-11-30 |  | 2020-12-07 |  | 2020-12-14 |  | 2020-12-21 |  |  | 2020-12-28 | 2021-01-04 |  | 2021-01-11 |  |  | 2021-01-18 |  | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 |  | 2021-02-22 |  | 2021-03-01 | 2021-03-08 |  | 2021-03-15 | 2021-03-22 | 2021-03-29 |  | 2021-04-05 |  | 2021-04-12 | 2021-04-19 |  | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-05-17 |  | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 |  | 2021-08-09 | 2021-08-16 | 2021-08-23 |  | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 |  | 2021-10-04 |  | 2021-10-11 |  | 2021-10-18 |  |  | 2021-10-25 |  | 2021-11-01 |  | 2021-11-08 |  | 2021-11-15 |  | 2021-11-22 | 2021-11-29 |  | 2021-12-06 | 2021-12-13 |  | 2021-12-20 |  | 2021-12-27 |  | 2022-01-03 |  | 2022-01-10 |  | 2022-01-17 | 2022-01-24 |  | 2022-01-31 |  | 2022-02-07 |  |  | 2022-02-14 | 2022-02-21 |  | 2022-02-28 |  | 2022-03-07 |  | 2022-03-14 | 2022-03-21 |  | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 |  | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 |  | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 |  | 2022-09-12
980GC Milestone | 980GC Milestone |  | Launch | [22 empty] | DR 1/2 | [19 empty] | GW 1/2 | [11 empty] | Quality Gate # 1 |  | PD Build | [7 empty] | PD Ship to PPG | [61 empty] | 100% Pilot Design Freeze | [17 empty] | 100% Pilot EDS Freeze | [30 empty] | Pilot Build | [9 empty] | FF | [50 empty] | 100% Production EDS Freeze | [14 empty] | GW 5.5 | [5 empty] | 1st Production | [11 empty] | GW 6
980GC SW Milestone | 980GC SW Milestone | [55 empty] | Release # 1 | [21 empty] | Release # 2 | [19 empty] | Release # 3 | [20 empty] | Trans SW |  |  |  |  | Release # 4
980GC TIC Report Milestone | 980GC TIC Report Milestone | [141 empty] | Brake-ISO 3450 | [5 empty] | Sound- Back-up Alarm, Horn-ISO 9566 |  | Steering-ISO 5010 | [22 empty] | Stg V EMC | [40 empty] | Brake-ISO 3450 Certification |  |  |  | Steering-ISO 5010 Certification | [17 empty] | EMC Certification |  |  |  |  | Articulation Frame Certification |  |  | Sound- Back-up Alarm, Horn-ISO 9566 Certification
W7K00288 | PPG 980GC TB | [12 empty] | 980GC TB Machine Build (hyd pump, implement valve) |  |  | Machine Checkout STP-64 | [19 empty] | Machine Update | Operator Eval # 2 |  |  |  |  | Hydraulic Development (Setup/Run/Teardown)
SN | QPG 980GC LRC PD#1 | [63 empty] | PD Machine Build | [7 empty] | Machine Checkout STP-64 |  |  | Software Checkout #1 (STP 230) Ver 01; Telematics SW (Gen A6N1+PL243/PL083) |  | Sound Testing (1st Pass screening) |  |  |  |  | L5 Tuning and Performance Check |  |  |  |  | Operator Eval #1 |  | Hydraulic Test ( Steering Pump Perf)+ Fan calibration | [15 empty] | Software Checkout #2 |  | Operator Eval #2 |  | LRC Water Flow Test & System (STP 151 & 155) |  |  | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration and Fan calibration |  |  | China National Holiday |  |  | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration and Fan calibration |  |  |  | Issue resolution # 1 | LRC STP 401 Engine Audit |  | ISO 3450 Brake Feasibility | [7 empty] | ISO 5010 Steering Feasibility | [7 empty] | Electric Load Study (Alt Charging capacity) |  | 980GC Endurance 0-500 hrs+ Inspection (12 hr/day) | [11 empty] | Software Checkout #3 |  | Endurance Inspection
SN | PPG 980GC Stg V HRC PD#2 | [59 empty] | PD Machine Build |  |  |  |  | QPG Machine Check | Ship Machine to PPG | [13 empty] | Machine Checkout STP-64 |  | SW Checkout # 1 |  | L5 Tuning and Performance Check #1 |  |  |  |  | Engine and SW Check |  | Engine Exhaust AFT controls | HVAC Charge Checkout |  | Sound Screening |  | XMSN Tuning |  |  |  | Software Checkout #2 (STP 230) |  | Issue resolution # 1 | [5 empty] | Rimpull and Response Test |  |  |  |  | STP-153 (Airflow Testing) |  |  | STP-151 & 155 (Water Flow & System Test) |  |  |  | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT + Fuel Sensor Calibration | [7 empty] | STP 401 HRC Engine Audit |  |  |  | US Thanksgiving |  |  |  |  | Sound Testing (Plus Hyd & Exhaust Characterization) |  | US Christmas and New Year Day Holiday | [5 empty] | Stage V Engine Install MER |  |  |  |  | Stage 5 Engine TC-L Cold Room | [9 empty] | Issue resolution # 2 |  |  |  | EN 13309 EMC Testing- Engg Test |  | Software Checkout #3 (STP 230)+ Endurance |  | L5 Tuning with Operator # 1 | [6 empty] | Machine D&A
SN | PPG 980GC T3 LRC PD#3 | [61 empty] | PD Machine Build | [5 empty] | QPG Machine Check | Ship Machine to PPG | [15 empty] | Machine Checkout STP-64 |  | L5 Tuning and Performance Operator Eval # 1 (Shift Performance) | [5 empty] | Engine and SW Check |  |  |  | Issue resolution # 1 |  | XMSN Tuning |  |  |  |  | Rimpull and Response Test |  |  | Light Fab and Heavy Structure OMSA Hood & Cooling Pkg & MER- 200 channels | [18 empty] | Hydraulic Test (Service Brake Modulation)+ Opr Eval |  |  |  |  | US Thanksgiving |  |  |  | Hydraulic Test (Service Brake Modulation)+ Opr Eval | [5 empty] | US Christmas and New Year Day Holiday |  |  |  | Software Checkout #2 (STP 230)+ Endurance | [23 empty] | LRC Engine Altitude (Start in 2021)
SN | PPG 980GC HRC Pilot #1 | [177 empty] | Pilot Machine Build | [8 empty] | Ship Machine to PPG | [11 empty] | Machine Checkout STP-64 |  | SW Checkout #1 |  |  | Sound Testing (Issue Resolution Not meeting Rqmts) |  | L5 Checkout and Performance Check + Oper eval |  |  |  | SW Checkout #2 |  | Operator Eval #2 | US Thanksgiving |  | OMSA Light Fabs Hood # 2 |  |  | US Christmas and New Year Day Holiday | [5 empty] | OMSA Light Fabs Hood # 2 | [6 empty] | Software Checkout #3 |  |  | EN 13309 EMC Testing-HRC-CERT |  |  | Engg Perf Productivity-Baseline
SN | QPG 980GC LRC Pilot #2 | [177 empty] | Pilot Machine Build | [9 empty] | Machine Checkout STP-64 |  |  | Software Checkout |  | ISO 3450 Brake- CERT |  |  |  | ISO 5010- HMU CERT | [5 empty] | EMC CERT |  |  |  |  | Hydraulic Signature Test- Documentation | [11 empty] | Sound Testing- ISO 9533, HAWB |  | ISO 10570 Articulation Lock |  |  |  | ISO 5006 (Virtual Audit) |  |  | China New Year |  |  |  | 980GC Endurance 0-500 hrs+ 250 hr Inspections | [14 empty] | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | [10 empty] | 980GC Endurance 1001-1500 hrs+ 250 hr inspections

## Pre GW 1 & 2
Machine S/N | Phase | 2019-02-25 |  | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 |  | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 |  | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 |  |  | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 |  | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 |  | 2020-02-03 |  | 2020-02-10 |  | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 |  | 2020-03-30 | 2020-04-06 |  | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 |  | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 |  | 2020-06-15 |  | 2020-06-22 |  |  | 2020-06-29 |  | 2020-07-06 |  | 2020-07-13 |  | 2020-07-20 |  |  | 2020-07-27 |  |  |  | 2020-08-03 | 2020-08-10 |  | 2020-08-17 |  | 2020-08-24 |  |  | 2020-08-31 |  | 2020-09-07 |  | 2020-09-14 | 2020-09-21 |  |  | 2020-09-28 |  |  | 2020-10-05 |  |  | 2020-10-12 |  | 2020-10-19 | 2020-10-26 |  |  | 2020-11-02 |  |  | 2020-11-09 |  |  | 2020-11-16 | 2020-11-23 |  |  | 2020-11-30 |  |  |  | 2020-12-07 |  |  | 2020-12-14 |  |  | 2020-12-21 |  | 2020-12-28 | 2021-01-04 |  | 2021-01-11 |  |  | 2021-01-18 |  | 2021-01-25 | 2021-02-01 | 2021-02-08 |  | 2021-02-15 |  | 2021-02-22 |  | 2021-03-01 | 2021-03-08 |  | 2021-03-15 | 2021-03-22 | 2021-03-29 |  | 2021-04-05 |  | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 |  | 2021-05-17 |  | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 |  | 2021-08-09 | 2021-08-16 | 2021-08-23 |  | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 |  | 2021-10-04 |  | 2021-10-11 |  | 2021-10-18 |  |  | 2021-10-25 |  | 2021-11-01 |  | 2021-11-08 |  | 2021-11-15 |  | 2021-11-22 | 2021-11-29 |  | 2021-12-06 | 2021-12-13 |  | 2021-12-20 |  | 2021-12-27 |  | 2022-01-03 |  | 2022-01-10 |  | 2022-01-17 | 2022-01-24 |  | 2022-01-31 |  | 2022-02-07 |  |  | 2022-02-14 | 2022-02-21 |  | 2022-02-28 |  | 2022-03-07 |  | 2022-03-14 | 2022-03-21 |  | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 |  | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 |  | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05
980GC Milestone | 980GC Milestone |  | Launch | [22 empty] | DR 1/2 | [19 empty] | GW 1/2 | [12 empty] | Quality Gate # 1 |  | PD Build | [7 empty] | PD Ship to PPG | [64 empty] | 100% Pilot Design Freeze | [20 empty] | 100% Pilot EDS Freeze | [30 empty] | Pilot Build | [9 empty] | FF | [50 empty] | 100% Production EDS Freeze | [14 empty] | GW 5.5 | [5 empty] | 1st Production | [11 empty] | GW 6
980GC SW Milestone | [56 empty] | Release # 1 | [22 empty] | Release # 2 | [19 empty] | Release # 3 | [21 empty] | Trans SW | [5 empty] | Release # 4
980GC TIC Report Milestone | [144 empty] | Brake-ISO 3450 | [9 empty] | Steering-ISO 5010 | Sound- Back-up Alarm, Horn-ISO 9566 | [24 empty] | Stg V EMC | [40 empty] | Brake-ISO 3450 Certification |  |  |  | Steering-ISO 5010 Certification | [17 empty] | EMC Certification |  |  |  |  | Articulation Frame Certification |  |  | Sound- Back-up Alarm, Horn-ISO 9566 Certification
W7K00288 | PPG 980GC TB | [12 empty] | 980GC TB Machine Build (hyd pump, implement valve) |  |  | Machine Checkout STP-64 | [19 empty] | Machine Update | Operator Eval # 2 |  |  |  |  | Hydraulic Development (Setup/Run/Teardown) | [98 empty] | Sound Testing (Plus Hyd & Exhaust Characterization)
SN | QPG 980GC LRC PD#1 | [64 empty] | PD Machine Build | [7 empty] | Machine Checkout STP-64 |  |  | Software Checkout #1 (STP 230) Ver 01; Telematics SW (Gen A6N1+PL243/PL083) |  | Sound Testing (1st Pass screening) |  |  |  |  | L5 Tuning and Performance Check |  |  |  |  | Operator Eval #1 |  | Hydraulic Test ( Steering Pump Perf)+ Fan calibration | [16 empty] | Software Checkout #2 |  | Operator Eval #2 |  | LRC Water Flow Test & System (STP 151 & 155) |  |  | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration and Fan calibration |  |  | China National Holiday |  |  | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration and Fan calibration |  |  |  |  | Issue resolution # 1 | LRC STP 401 Engine Audit |  |  | ISO 3450 Brake Feasibility | [7 empty] | ISO 5010 Steering Feasibility | [11 empty] | Electric Load Study (Alt Charging capacity) | 980GC Endurance 0-500 hrs+ Inspection (12 hr/day) | [10 empty] | China New Year |  | Software Checkout #3 |  | Endurance Inspection
SN | PPG 980GC Stg V HRC PD#2 | [60 empty] | PD Machine Build |  |  |  |  | QPG Machine Check | Ship Machine to PPG | [13 empty] | Machine Checkout STP-64 |  | SW Checkout # 1 |  | L5 Tuning and Performance Check #1 |  |  |  |  | Engine and SW Check |  | Engine Exhaust AFT controls | HVAC Charge Checkout |  | Sound Screening |  | XMSN Tuning |  |  |  |  | Software Checkout #2 (STP 230) |  | Issue resolution # 1 | [5 empty] | Rimpull and Response Test |  |  |  |  | STP-153 (Airflow Testing) |  |  | STP-151 & 155 (Water Flow & System Test) |  |  |  |  | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT + Fuel Sensor Calibration | [8 empty] | STP 401 HRC Engine Audit |  |  |  | US Thanksgiving |  |  |  | Dust Ejector Measurement |  |  | Sound Testing (Plus Hyd & Exhaust Characterization) |  |  | US Christmas and New Year Day Holiday | [5 empty] | Stage V Engine Install MER |  |  |  |  | Stage 5 Engine TC-L Cold Room | [10 empty] | Issue resolution # 2 |  |  |  | EN 13309 EMC Testing- Engg Test |  | Software Checkout #3 (STP 230)+ Endurance |  | L5 Tuning with Operator # 1 | [5 empty] | Machine D&A
SN | PPG 980GC T3 LRC PD#3 | [62 empty] | PD Machine Build | [5 empty] | QPG Machine Check | Ship Machine to PPG | [15 empty] | Machine Checkout STP-64 |  | L5 Tuning and Performance Operator Eval # 1 (Shift Performance) | [5 empty] | Engine and SW Check |  |  |  | Issue resolution # 1 |  |  | XMSN Tuning |  |  |  |  | Rimpull and Response Test |  |  | Light Fan and Heavy Structure OMSA Hood & Cooling Pkg & MER- 200 channels | [20 empty] | Hydraulic Test (Service Brake Modulation)+ Opr Eval |  |  |  |  | US Thanksgiving |  |  |  | Hydraulic Test (Service Brake Modulation)+ Opr Eval | [7 empty] | US Christmas and New Year Day Holiday |  |  |  |  | Software Checkout #2 (STP 230)+ Endurance | [23 empty] | Stage 5 Engine Altitude (Start in 2021)
SN | PPG 980GC HRC Pilot #1 | [184 empty] | Pilot Machine Build | [8 empty] | Ship Machine to PPG | [11 empty] | Machine Checkout STP-64 |  | SW Checkout #1 |  |  | Sound Testing (Issue Resolution Not meeting Rqmts) |  | L5 Checkout and Performance Check + Oper eval |  |  |  | SW Checkout #2 |  | Operator Eval #2 | US Thanksgiving |  | OMSA Light Fabs Hood # 2 |  |  | US Christmas and New Year Day Holiday | [5 empty] | OMSA Light Fabs Hood # 2 | [6 empty] | Software Checkout #3 |  |  | EN 13309 EMC Testing-HRC-CERT |  |  | Engg Perf Productivity-Baseline
SN | QPG 980GC LRC Pilot #2 | [184 empty] | Pilot Machine Build | [9 empty] | Machine Checkout STP-64 |  |  | Software Checkout |  | ISO 3450 Brake- CERT |  |  |  | ISO 5010- HMU CERT | [5 empty] | EMC CERT |  |  |  |  | Hydraulic Signature Test- Documentation | [11 empty] | Sound Testing- ISO 9533, HAWB |  | ISO 10570 Articulation Lock |  |  |  | ISO 5006 (Virtual Audit) |  |  | China New Year |  |  |  | 980GC Endurance 0-500 hrs+ 250 hr Inspections | [14 empty] | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | [10 empty] | 980GC Endurance 1001-1500 hrs+ 250 hr inspections
P i l
ot
Des i g
n
Freeze
P roduction
Des i g
n
Freeze

## DR 1 & 2 (old)
Machine S/N | Phase | 2019-02-25 |  | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 |  | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 |  | 2019-08-12 |  | 2019-08-19 | 2019-08-26 |  | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 |  | 2019-11-18 |  | 2019-11-25 |  | 2019-12-02 | 2019-12-09 | 2019-12-16 |  | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 |  | 2020-01-20 | 2020-01-27 |  | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 |  | 2020-03-30 | 2020-04-06 | 2020-04-13 |  | 2020-04-20 | 2020-04-27 |  | 2020-05-04 | 2020-05-11 |  |  | 2020-05-18 |  |  |  | 2020-05-25 |  | 2020-06-01 |  |  | 2020-06-08 |  |  |  | 2020-06-15 |  | 2020-06-22 |  | 2020-06-29 |  | 2020-07-06 |  | 2020-07-13 |  | 2020-07-20 |  |  | 2020-07-27 |  |  | 2020-08-03 | 2020-08-10 |  | 2020-08-17 |  | 2020-08-24 |  | 2020-08-31 |  | 2020-09-07 |  |  | 2020-09-14 |  | 2020-09-21 | 2020-09-28 | 2020-10-05 |  | 2020-10-12 |  | 2020-10-19 |  | 2020-10-26 |  |  | 2020-11-02 |  | 2020-11-09 |  | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 |  | 2021-01-11 |  | 2021-01-18 |  |  | 2021-01-25 |  |  |  | 2021-02-01 |  |  | 2021-02-08 |  |  | 2021-02-15 | 2021-02-22 |  |  | 2021-03-01 |  | 2021-03-08 |  | 2021-03-15 |  |  | 2021-03-22 |  | 2021-03-29 | 2021-04-05 | 2021-04-12 |  | 2021-04-19 |  |  | 2021-04-26 |  | 2021-05-03 |  | 2021-05-10 | 2021-05-17 | 2021-05-24 |  | 2021-05-31 | 2021-06-07 |  | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 |  | 2021-08-02 | 2021-08-09 | 2021-08-16 |  | 2021-08-23 | 2021-08-30 |  | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 |  | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10
980GC Milestone | 980GC Milestone |  | Launch | [22 empty] | DR 1/2 |  | DR 3, DD3 |  | GW 1/2 |  |  | 100% PD EDS Freeze | [15 empty] | Quality Gate # 1 | [8 empty] | GW 4 |  |  |  |  | PD Build | [7 empty] | PD Ship to PPG | [47 empty] | 100% Pilot EDS Freeze | [15 empty] | Pilot Build | [22 empty] | FF | [43 empty] | 100% Production EDS Freeze | [6 empty] | GW 5.5 | [9 empty] | Quality Gate # 2 | [9 empty] | GW 6 | 1st Production
980GC SW Milestone | 980GC SW Milestone | [59 empty] | Release # 1 | [26 empty] | Release # 2 | [21 empty] | Release # 3 | [17 empty] | Trans SW | [6 empty] | Release # 4
980GC TIC Report Milestone | 980GC TIC Report Milestone | [125 empty] | Brake-ISO 3450 report | [28 empty] | Steering-ISO 5010 report
W7K00288 | PPG 980GC TB | [12 empty] | 980GC TB Machine Build (hyd pump, implement valve) |  |  | Machine Checkout STP-64 | [22 empty] | Hydraulic Development (Setup/Run/Teardown) |  |  | Implement SW Checkout |  |  | Operator Eval
SN | QPG 980GC LRC PD#1 | [43 empty] | Software Checkout #3 |  | 980GC Endurance 0-500 hrs+ Inspection (12 hr/day) | [5 empty] | Endurance Inspection | [17 empty] | Machine Checkout STP-64 |  |  | Software Checkout #1 (STP 230) Ver 01; Telematics SW (Gen A6N1+PL243/PL083) |  |  | Sound Testing (1st Pass screening) |  |  | L5 Tuning and Performance Check |  |  |  |  | Operator Eval #1 | [8 empty] | Hydraulic Test ( Steering Pump Perf) | [9 empty] | Software Checkout #2 |  |  | Operator Eval #2 |  | LRC Water Flow Test & System (STP 151 & 155) | [5 empty] | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration | [6 empty] | Issue resolution | LRC STP 401 Engine Audit | ISO 3450 Brake Feasibility |  |  |  | ISO 5010 Steering Feasibility | [5 empty] | 980GC Endurance 0-500 hrs+ Inspection (12 hr/day)
SN | PPG 980GC Stg V HRC PD#2 | [61 empty] | Machine Build | [5 empty] | Ship Machine to PPG | [10 empty] | Machine Checkout STP-64 | SW Checkout # 1 |  |  | L5 Tuning and Performance Check #1 |  |  |  |  | Engine and SW Check |  |  | Engine Exhaust AFT controls | HVAC Charge Checkout |  |  | XMSN Tuning |  |  |  | Issue resolution # 1 | [7 empty] | Rimpull and Response Test |  |  |  |  | Software Checkout #2 (STP 230) |  | STP-153 (Airflow Testing) |  | STP-151 & 155 (Water Flow & System Test) |  |  |  | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT + Fuel Sensor Calibration | [5 empty] | STP 401 HRC Engine Audit |  |  | Dust Ejector Measurement |  | Stage V Engine Install MER |  |  |  |  | Stage 5 Engine TC-L Cold Room | [10 empty] | Issue resolution # 2 |  |  |  |  | Safety & Service Audit |  | Harness routing Audit | EN 13309 EMC Testing- Engg Test |  |  |  | Software Checkout #3 (STP 230)+ Endurance |  |  | L5 Tuning with Operator # 1
SN | PPG 980GC T3 LRC PD#3 | [61 empty] | Machine Build | [6 empty] | Ship Machine to PPG | [10 empty] | Machine Checkout STP-64 |  | L5 Tuning with Operator # 2 (Shift Performance) |  |  |  | SW Checkout # 1 |  |  | L5 Tuning and Performance Check #1 |  |  |  |  | Engine and SW Check |  |  | XMSN Tuning |  |  |  | Issue resolution # 1 |  |  |  | Rimpull and Response Test | [5 empty] | Light Fan and Heavy Structure OMSA Hood & Cooling Pkg & MER- 200 channels | [16 empty] | Hydraulic Test (Service Brake Modulation)+ Opr Eval | [9 empty] | Software Checkout #4 (STP 230)+ Endurance | [51 empty] | Stage 5 Engine Altitude (Start in 2021)
SN | PPG 980GC HRC Pilot #1 | [155 empty] | Machine Checkout STP-64 |  | SW Checkout #1 |  |  |  |  | Sound Testing (Issue Resolution Not meeting Rqmts) | L5 Checkout |  | Operator Eval #1 |  | SW Checkout #2 |  | Operator Eval #2 |  | OMSA Light Fabs Hood # 2 | [8 empty] | Software Checkout #3 |  | EN 13309 EMC Testing-HRC-CERT |  |  | Engg Perf Productivity-Baseline
SN | QPG 980GC LRC Pilot #2 | [148 empty] | Machine Checkout STP-64 |  | Software Checkout |  |  |  | ISO 5010- HMU CERT | [5 empty] | ISO 3450 Brake- CERT |  |  |  | EMC Testing | [7 empty] | Hydraulic Signature Test- Documentation | [5 empty] | Sound Testing- ISO 9533, HAWB |  |  | ISO 10570 Articulation Lock |  | ISO 5006 (Virtual Audit)
SN | PPG 980GC HRC Pilot #3 | [174 empty] | Machine Checkout STP-64 | Sound Testing-ISO 9533, ISO 6393-6396 | 980GC Endurance 0-500 hrs+ 250 hr Inspections | [15 empty] | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | [11 empty] | 980GC Endurance 1001-1500 hrs+ 250 hr inspections | [10 empty] | Endurance Inspection

## STCW option 2
Machine S/N | Phase | 2019-02-01 | 2019-02-08 |  | 2019-02-15 | 2019-02-22 |  | 2019-03-01 | 2019-03-08 | 2019-03-15 | 2019-03-22 |  | 2019-03-29 | 2019-04-05 | 2019-04-12 | 2019-04-19 | 2019-04-26 | 2019-05-03 | 2019-05-10 |  | 2019-05-17 | 2019-05-24 |  | 2019-05-31 | 2019-06-07 | 2019-06-14 | 2019-06-21 |  | 2019-06-28 | 2019-07-05 |  | 2019-07-12 |  | 2019-07-19 | 2019-07-26 | 2019-08-02 |  | 2019-08-09 |  | 2019-08-16 | 2019-08-23 | 2019-08-30 | 2019-09-06 |  | 2019-09-13 | 2019-09-20 | 2019-09-27 | 2019-10-04 | 2019-10-11 | 2019-10-18 | 2019-10-25 | 2019-11-01 | 2019-11-08 | 2019-11-15 | 2019-11-22 | 2019-11-29 |  | 2019-12-06 | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 |  | 2020-01-17 | 2020-01-24 | 2020-01-31 |  | 2020-02-07 |  | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 |  | 2020-04-03 | 2020-04-10 |  | 2020-04-17 |  | 2020-04-24 |  | 2020-05-01 |  | 2020-05-08 |  | 2020-05-15 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  | 2020-06-05 |  |  | 2020-06-12 |  |  |  | 2020-06-19 |  | 2020-06-26 |  |  | 2020-07-03 |  |  | 2020-07-10 |  | 2020-07-17 |  |  | 2020-07-24 |  |  | 2020-07-31 |  |  |  | 2020-08-07 |  | 2020-08-14 | 2020-08-21 |  |  | 2020-08-28 |  | 2020-09-04 |  | 2020-09-11 |  | 2020-09-18 |  |  |  | 2020-09-25 |  | 2020-10-02 |  |  | 2020-10-09 |  | 2020-10-16 | 2020-10-23 | 2020-10-30 |  | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-04 | 2020-12-11 | 2020-12-18 | 2020-12-25 | 2021-01-01 | 2021-01-08 | 2021-01-15 |  | 2021-01-22 |  | 2021-01-29 |  |  |  | 2021-02-05 |  | 2021-02-12 |  | 2021-02-19 |  |  | 2021-02-26 |  | 2021-03-05 |  | 2021-03-12 | 2021-03-19 |  |  | 2021-03-26 |  |  | 2021-04-02 |  |  | 2021-04-09 | 2021-04-16 | 2021-04-23 |  | 2021-04-30 | 2021-05-07 | 2021-05-14 | 2021-05-21 | 2021-05-28 |  | 2021-06-04 | 2021-06-11 | 2021-06-18 | 2021-06-25 | 2021-07-02 | 2021-07-09 | 2021-07-16 | 2021-07-23 | 2021-07-30 |  | 2021-08-06 | 2021-08-13 |  | 2021-08-20 | 2021-08-27 |  | 2021-09-03 | 2021-09-10 | 2021-09-17 | 2021-09-24 | 2021-10-01 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 2021-10-29 |  | 2021-11-05 | 2021-11-12 | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 |  | 2022-01-14
980GC Milestone | 980GC Milestone | [5 empty] | Launch | [25 empty] | DR 1/2 |  |  |  | DR 3, DD3 |  | GW 1/2 |  |  |  |  | 100% PD EDS Freeze | [12 empty] | Quality Gate # 1 | [6 empty] | GW 4 | [5 empty] | PD Build | [7 empty] | PD Ship to PPG | [32 empty] | 100% Pilot EDS Freeze | [41 empty] | Pilot Build | [17 empty] | FF | [41 empty] | 100% Production EDS Freeze | [5 empty] | GW 5.5 | [9 empty] | Quality Gate # 2 | [10 empty] | GW 6 |  | 1st Production
980GC SW Milestone | 980GC SW Milestone | [66 empty] | Release # 1 | [29 empty] | Release # 2 | [25 empty] | Release # 3 | [24 empty] | Trans SW |  |  |  | Release # 4
980GC TIC Report Milestone | 980GC TIC Report Milestone | [129 empty] | Steering-ISO 5010 | [36 empty] | Steering-ISO 5010
W7K00288 | PPG 980GC TB | [18 empty] | 980GC TB Machine Build (hyd pump, implement valve) |  |  | Machine Checkout STP-64 | Hydraulic Development (Setup/Run/Teardown) |  |  |  | Implement SW Checkout |  |  | Operator Eval
SN | QPG 980GC LRC PD#1 | [76 empty] | Machine Checkout STP-64 |  |  | Software Checkout #1 (STP 230) Ver 01; Telematics SW (Gen A6N1+PL243/PL083) |  | Sound Testing (1st Pass screening) |  | L5 Tuning and Performance Check |  | Rimpull Test |  |  |  | Operator Eval #1 |  | Hydraulic Test ( Steering Pump Perf) | [8 empty] | Software Checkout #2 |  | Operator Eval #2 |  | LRC Water Flow Test & System (STP 151 & 155) |  |  |  | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration | [9 empty] | Issue resolution | Safety Audit | LRC STP 401 Engine Audit |  |  | Electric Load Study (Alt Charging capacity) | ISO 5010 Steering Feasibility | [5 empty] | ISO 3450 Brake Feasibility |  |  |  | Software Checkout #3 |  | 980GC Endurance 0-500 hrs+ Inspection | [18 empty] | ISO 5006 (Virtual Audit)
SN | PPG 980GC Stg V HRC PD#2 |  |  | Machine Build | [7 empty] | Ship Machine to PPG | [76 empty] | Machine Checkout STP-64 |  | Operator Eval # 1 |  | SW Checkout # 1 |  |  | L5 Tuning and Performance Check #1 |  |  | Engine and SW Check |  | XMSN Tuning |  |  |  | Machine Endurance 100 hrs |  |  | Rimpull and Response Test |  |  |  |  | Issue resolution | Software Checkout #2 (STP 230) |  |  | L5 Tuning with Operator # 1 |  | Engine Exhaust AFT controls | Hydraulic Test (Service Brake Modulation)+ Opr Eval | [7 empty] | Light Fan and Heavy Structure OMSA Hood & Cooling Pkg & MER- 200 channels | [11 empty] | HRC Sound Testing (Plus Hydraulic+ exhaust characterization) |  | Issue resolution |  | Software Checkout #3 (STP 230) |  | Safety & Service Audit | Harness routing Audit | EN 13309 EMC Testing- Engg Test
SN | PPG 980GC Stg V HRC PD#3 | [88 empty] | Machine Checkout STP-64 |  | STP-153 (Airflow Testing) |  |  | STP-151 & 155 (Water Flow & System Test) |  |  |  | Dust Ejector Measurement |  | L5 Tuning with Operator # 2 (Shift Performance) |  |  |  | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT + Fuel Sensor Calibration | [10 empty] | STP 401 HRC Engine Audit |  | Stage 5 Engine TC-L Cold Room | [15 empty] | Software Checkout # 3 (STP 230)+ Endurance | [6 empty] | Engg Perf Productivity | [61 empty] | Stage 5 Engine Altitude
SN | PPG 980GC HRC Pilot #1 | [168 empty] | Machine Checkout STP-64 |  | SW Checkout #1 |  |  |  | Sound Testing (Issue Resolution Not meeting Rqmts) |  | L5 Checkout |  | Operator Eval #1 | SW Checkout #2 |  | Operator Eval #2 | OMSA Light Fabs Hood | [5 empty] | Software Checkout #3 |  |  | EN 13309 EMC Testing-HRC
SN | QPG 980GC LRC Pilot #2 | [163 empty] | Machine Checkout STP-64 | Software Checkout # 1 |  | ISO 5010- HMU CERT | [5 empty] | ISO 3450 Brake- CERT |  |  |  |  | EMC Testing | [6 empty] | Hydraulic Signature Test- Documentation | [8 empty] | Sound Testing- ISO 9533, HAWB | ISO 10570 Articulation Lock | ISO 5006 (Virtual Audit)
SN | QPG 980GC HRC Pilot #3 | [185 empty] | Machine Checkout STP-64 |  | Sound Testing-ISO 9533, ISO 6393-6396 |  |  | 980GC Endurance 0-500 hrs+ 250 hr Inspections | [12 empty] | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | [10 empty] | 980GC Endurance 1001-1500 hrs+ 250 hr inspections

## STCW Option 1
Machine S/N | Phase | 2019-02-01 | 2019-02-08 |  | 2019-02-15 | 2019-02-22 |  | 2019-03-01 | 2019-03-08 | 2019-03-15 | 2019-03-22 |  | 2019-03-29 | 2019-04-05 | 2019-04-12 | 2019-04-19 | 2019-04-26 | 2019-05-03 | 2019-05-10 |  | 2019-05-17 | 2019-05-24 |  | 2019-05-31 | 2019-06-07 | 2019-06-14 | 2019-06-21 | 2019-06-28 | 2019-07-05 | 2019-07-12 |  | 2019-07-19 | 2019-07-26 | 2019-08-02 |  | 2019-08-09 |  | 2019-08-16 | 2019-08-23 | 2019-08-30 | 2019-09-06 |  | 2019-09-13 | 2019-09-20 | 2019-09-27 |  | 2019-10-04 | 2019-10-11 |  | 2019-10-18 | 2019-10-25 | 2019-11-01 | 2019-11-08 | 2019-11-15 | 2019-11-22 | 2019-11-29 |  | 2019-12-06 | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 |  | 2020-01-17 | 2020-01-24 | 2020-01-31 |  | 2020-02-07 |  | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 |  | 2020-04-03 | 2020-04-10 |  | 2020-04-17 |  | 2020-04-24 |  | 2020-05-01 |  | 2020-05-08 |  | 2020-05-15 |  |  | 2020-05-22 |  | 2020-05-29 |  |  | 2020-06-05 |  | 2020-06-12 |  |  |  | 2020-06-19 | 2020-06-26 |  |  |  | 2020-07-03 |  |  | 2020-07-10 | 2020-07-17 | 2020-07-24 |  |  | 2020-07-31 |  | 2020-08-07 | 2020-08-14 |  | 2020-08-21 | 2020-08-28 | 2020-09-04 |  |  | 2020-09-11 |  | 2020-09-18 |  | 2020-09-25 |  | 2020-10-02 |  | 2020-10-09 |  |  | 2020-10-16 | 2020-10-23 |  | 2020-10-30 |  | 2020-11-06 | 2020-11-13 |  | 2020-11-20 |  | 2020-11-27 |  | 2020-12-04 | 2020-12-11 | 2020-12-18 | 2020-12-25 | 2021-01-01 | 2021-01-08 |  | 2021-01-15 |  |  | 2021-01-22 |  | 2021-01-29 |  |  | 2021-02-05 |  |  | 2021-02-12 | 2021-02-19 |  |  | 2021-02-26 |  | 2021-03-05 | 2021-03-12 | 2021-03-19 |  |  | 2021-03-26 |  | 2021-04-02 |  |  | 2021-04-09 |  | 2021-04-16 | 2021-04-23 |  | 2021-04-30 | 2021-05-07 | 2021-05-14 | 2021-05-21 | 2021-05-28 | 2021-06-04 |  | 2021-06-11 | 2021-06-18 | 2021-06-25 | 2021-07-02 | 2021-07-09 | 2021-07-16 | 2021-07-23 | 2021-07-30 |  | 2021-08-06 | 2021-08-13 |  | 2021-08-20 | 2021-08-27 |  | 2021-09-03 | 2021-09-10 | 2021-09-17 | 2021-09-24 | 2021-10-01 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 2021-10-29 |  | 2021-11-05 | 2021-11-12 | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 |  | 2022-01-14
980GC Milestone | 980GC Milestone | [5 empty] | Launch | [23 empty] | DR 1/2 |  |  |  | DR 3, DD3 |  | GW 1/2 |  |  |  |  | 100% PD EDS Freeze | [14 empty] | Quality Gate # 1 | [6 empty] | GW 4 | [5 empty] | PD Build | [7 empty] | PD Ship to PPG | [29 empty] | 100% Pilot EDS Freeze | [33 empty] | Pilot Build | [20 empty] | FF | [40 empty] | 100% Production EDS Freeze | [5 empty] | GW 5.5 | [9 empty] | Quality Gate # 2 | [10 empty] | GW 6 |  | 1st Production
980GC SW Milestone | 980GC SW Milestone | [66 empty] | Release # 1 | [27 empty] | Release # 2 | [20 empty] | Release # 3 | [17 empty] | Trans SW | [6 empty] | Release # 4
980GC TIC Report Milestone | 980GC TIC Report Milestone | [119 empty] | Steering-ISO 5010 | [39 empty] | Steering-ISO 5010
W7K00288 | PPG 980GC TB | [18 empty] | 980GC TB Machine Build (hyd pump, implement valve) |  |  | Machine Checkout STP-64 | [17 empty] | Hydraulic Development (Setup/Run/Teardown) |  |  |  |  | Implement SW Checkout |  |  | Operator Eval
SN | QPG 980GC LRC PD#1 | [76 empty] | Machine Checkout STP-64 |  |  | Software Checkout #1 (STP 230) Ver 01; Telematics SW (Gen A6N1+PL243/PL083) |  | Sound Testing (1st Pass screening) |  | L5 Tuning and Performance Check |  | Rimpull Test |  |  |  | Operator Eval #1 | Hydraulic Test ( Steering Pump Perf) | [6 empty] | Software Checkout #2 |  | Operator Eval #2 |  | LRC Water Flow Test & System (STP 151 & 155) |  |  | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration | [7 empty] | Safety Audit | LRC STP 401 Engine Audit | Electric Load Study (Alt Charging capacity) |  | ISO 5010 Steering Feasibility |  |  |  | ISO 3450 Brake Feasibility |  |  | Software Checkout #3 |  | 980GC Endurance 0-500 hrs+ Inspection | [17 empty] | ISO 5006 (Virtual Audit)
SN | PPG 980GC Stg V HRC PD#2 |  |  | Machine Build | [7 empty] | Ship Machine to PPG | [76 empty] | Machine Checkout STP-64 |  | Operator Eval | SW Checkout # 1 |  | L5 Tuning and Performance Check #1 |  |  | Rimpull and Response Test |  |  |  |  | Engine and SW Check |  | XMSN Tuning |  |  | Software Checkout #2 (STP 230) |  |  | L5 Tuning with Operator # 1 | Hydraulic Test (Service Brake Modulation)+ Opr Eval |  |  |  | Light Fan and Heavy Structure OMSA Hood & Cooling Pkg & MER- 120 channels | [8 empty] | HRC Sound Testing (Plus Hydraulic+ exhaust characterization) |  | Software Checkout #3 (STP 230) |  | Safety & Service Audit | Harness routing Audit | EN 13309 EMC Testing- Engg Test |  | STP-153 (Airflow Testing) |  | STP-151 & 155 (Water Flow & System Test) |  | Dust Ejector Measurement | L5 Tuning with Operator # 2 (Shift Performance) |  |  | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT + Fuel Sensor Calibration | [6 empty] | STP 401 HRC Engine Audit |  | Stage 5 Engine TC-L Cold Room | [6 empty] | Software Checkout #4 (STP 230)+ Endurance | [32 empty] | Engg Perf Productivity
SN | PPG 980GC HRC Pilot #1 | [156 empty] | Machine Checkout STP-64 |  | SW Checkout #1 |  |  |  | Sound Testing (Issue Resolution Not meeting Rqmts) |  | L5 Checkout |  |  | Operator Eval #1 | SW Checkout #2 |  |  | Operator Eval #2 | OMSA Light Fabs Hood | [8 empty] | Software Checkout #3 |  | Stage V EN 13309 EMC Testing-HRC
SN | QPG 980GC LRC Pilot #2 | [155 empty] | Machine Checkout STP-64 |  | Software Checkout |  | ISO 5010- HMU CERT | [5 empty] | ISO 3450 Brake- CERT |  |  |  | EMC Testing | [5 empty] | Hydraulic Signature Test- Documentation | [8 empty] | Sound Testing- ISO 9533, HAWB | ISO 10570 Articulation Lock | ISO 5006 (Virtual Audit)
SN | QPG 980GC HRC Pilot #3 | [176 empty] | Machine Checkout STP-64 |  | Sound Testing-ISO 9533, ISO 6393-6396 |  | 980GC Endurance 0-500 hrs+ 250 hr Inspections | [12 empty] | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | [11 empty] | 980GC Endurance 1001-1500 hrs+ 250 hr inspections

## STCW
| Activity ID | Start | Finish | STCW |  | Activity ID | Start | Finish | STCW
| 980GC Milestones | 2019-02-28 | 2022-01-10 |  |  | 980GC Milestones | 2019-02-28 | 2022-01-10
GW | Launch | 2019-02-28 | 2019-02-28 |  | GW | Launch | 2019-02-28 | 2019-02-28
DR | DR 1/2 | 2019-07-15 | 2019-07-15 |  | DR | DR 1/2 | 2019-07-15 | 2019-07-15
GW | GW 1/2 | 2019-08-15 | 2019-08-15 |  | GW | GW 1/2 | 2019-08-15 | 2019-08-15
DR | DR 3, DD3 | 2019-08-07 | 2019-08-07 |  | DR | DR 3, DD3 | 2019-08-07 | 2019-08-07
FR | 100% PD EDS Freeze | 2019-09-09 | 2019-09-09 |  | FR | 100% PD EDS Freeze | 2019-09-09 | 2019-09-09
QC | Quality Gate # 1 | 2019-12-01 | 2019-12-01 |  | QC | Quality Gate # 1 | 2019-12-01 | 2019-12-01
GW | GW 3 | 2020-01-15 | 2020-01-15 |  | GW | GW 3 | 2020-01-15 | 2020-01-15
GW | GW 4 | 2020-01-15 | 2020-01-15 |  | GW | GW 4 | 2020-01-15 | 2020-01-15
FR | PD Build | 2020-02-10 | 2020-03-15 |  | FR | PD Build | 2020-02-10 | 2020-03-15
FR | PD Ship to PPG | 2020-03-30 | 2020-05-11 |  | FR | PD Ship to PPG | 2020-03-30 | 2020-05-11
FR | 100% Pilot EDS Freeze | 2020-07-01 | 2020-07-01 |  | FR | 100% Pilot EDS Freeze | 2020-07-01 | 2020-07-01
GW | GW 5 | 2020-11-15 | 2020-11-15 |  | GW | GW 5 | 2020-11-15 | 2020-11-15
FR | Pilot Build | 2020-11-01 | 2021-01-15 |  | FR | Pilot Build | 2020-11-01 | 2021-01-15
FR | FF | 2021-02-01 | 2021-07-31 |  | FR | FF | 2021-02-01 | 2021-07-31
FR | 100% Production EDS Freeze | 2021-08-01 | 2021-08-01 |  | FR | 100% Production EDS Freeze | 2021-08-01 | 2021-08-01
GW | GW 5.5 | 2021-09-01 | 2021-09-01 |  | GW | GW 5.5 | 2021-09-01 | 2021-09-01
QG | Quality Gate # 2 | 2021-11-01 | 2021-11-01 |  | QG | Quality Gate # 2 | 2021-11-01 | 2021-11-01
GW | GW 6 | 2022-01-10 | 2022-01-10 |  | GW | GW 6 | 2022-01-10 | 2022-01-10
FR | 1st Production | 2022-01-15 | 2022-01-15 |  | FR | 1st Production | 2022-01-15 | 2022-01-15
| 980GC SW Milestones | 2020-02-01 | 2021-06-25 |  |  | 980GC SW Milestones | 2020-02-01 | 2021-06-25
SW | Release # 1 | 2020-02-01 | 2020-02-01 |  | SW | Release # 1 | 2020-02-01 | 2020-02-01
SW | Release # 2 | 2020-06-01 | 2020-06-01 |  | SW | Release # 2 | 2020-06-01 | 2020-06-01
SW | Release # 3 | 2020-08-01 | 2020-08-01 |  | SW | Release # 3 | 2020-08-01 | 2020-08-01
SW | Trans SW | 2020-10-10 | 2020-10-10 |  | SW | Trans SW | 2020-10-10 | 2020-10-10
SW | Release # 4 | 2020-11-01 | 2020-11-01 |  | SW | Release # 4 | 2020-11-01 | 2020-11-01
| 980GC TIC Report Milestones | 2020-08-20 | 2021-06-25 |  |  | 980GC TIC Report Milestones | 2020-08-25 | 2021-06-25
Safety and Regs-Pilot | Brake-ISO 3450 | 2020-09-04 | 2020-11-03 |  | Safety and Regs-Pilot | Brake-ISO 3450 | 2020-09-09 | 2020-11-08
Safety and Regs-Pilot | Steering-ISO 5010 | 2020-08-20 | 2020-10-19 |  | Safety and Regs-Pilot | Steering-ISO 5010 | 2020-08-25 | 2020-10-24
Safety and Regs-Pilot | EMC | 2020-09-26 | 2020-11-25 |  | Safety and Regs-Pilot | EMC | 2020-10-16 | 2020-12-15
Safety and Regs-Pilot | Sound- Back-up Alarm, Horn-ISO 9566 | 2020-09-08 | 2020-11-07 |  | Safety and Regs-Pilot | Sound- Back-up Alarm, Horn-ISO 9566 | 2020-09-23 | 2020-11-22
Safety and Regs-Production | Brake-ISO 3450 | 2021-02-24 | 2021-04-25 |  | Safety and Regs-Production | Brake-ISO 3450 | 2021-02-24 | 2021-04-25
Safety and Regs-Production | Steering-ISO 5010 | 2021-01-27 | 2021-03-28 |  | Safety and Regs-Production | Steering-ISO 5010 | 2021-01-27 | 2021-03-28
Safety and Regs-Production | EMC | 2021-02-25 | 2021-04-26 |  | Safety and Regs-Production | EMC | 2021-02-25 | 2021-04-26
Safety and Regs-Production | Articulation Frame | 2021-04-26 | 2021-06-25 |  | Safety and Regs-Production | Articulation Frame | 2021-04-26 | 2021-06-25
Safety and Regs-Production | Sound- Back-up Alarm, Horn-ISO 9566 | 2021-04-22 | 2021-06-21 |  | Safety and Regs-Production | Sound- Back-up Alarm, Horn-ISO 9566 | 2021-04-22 | 2021-06-21
| PPG 980GC TB (W7K00288) | 2019-05-13 | 2019-07-09 |  |  | PPG 980GC TB (W7K00288) | 2019-05-13 | 2019-07-09
Machine Build | 980GC TB Machine Build (hyd pump, implement valve) | 2019-05-13 | 2019-05-24 |  | Machine Build | 980GC TB Machine Build (hyd pump, implement valve) | 2019-05-13 | 2019-05-24
Machine Check | Machine Checkout STP-64 | 2019-05-28 | 2019-05-30 |  | Machine Check | Machine Checkout STP-64 | 2019-05-28 | 2019-05-30
Hydraulics | Hydraulic Development (Setup/Run/Teardown) | 2019-05-31 | 2019-06-20 |  | Hydraulics | Hydraulic Development (Setup/Run/Teardown) | 2019-05-31 | 2019-06-20
Hydraulics | Implement SW Checkout | 2019-06-23 | 2019-07-04 |  | Hydraulics | Implement SW Checkout | 2019-06-23 | 2019-07-04
Opr Eval | Operator Eval | 2019-07-07 | 2019-07-09 |  | Opr Eval | Operator Eval | 2019-07-07 | 2019-07-09
| QPG 980GC LRC PD#1 (SN) | 2020-03-30 | 2020-11-16 |  |  | QPG 980GC LRC PD#1 (SN) | 2020-03-30 | 2020-11-21
Machine Check | Machine Checkout STP-64 | 2020-03-30 | 2020-04-12 |  | Machine Check | Machine Checkout STP-64 | 2020-03-30 | 2020-04-12
SW | Software Checkout #1 (STP 230) Ver 01; Telematics SW (Gen A6N1+PL243/PL083) | 2020-04-13 | 2020-04-19 |  | SW | Software Checkout #1 (STP 230) Ver 01; Telematics SW (Gen A6N1+PL243/PL083) | 2020-04-13 | 2020-04-19
NVH | Sound Testing (1st Pass screening) | 2020-04-20 | 2020-04-24 |  | NVH | Sound Testing (1st Pass screening) | 2020-04-20 | 2020-04-24
Performance2 | L5 Tuning and Performance Check | 2020-04-25 | 2020-05-05 |  | Performance2 | L5 Tuning and Performance Check | 2020-04-25 | 2020-05-05
Performance2 | Rimpull Test | 2020-05-07 | 2020-05-15 |  | Performance2 | Rimpull Test | 2020-05-07 | 2020-05-15
Opr Eval | Operator Eval #1 | 2020-05-16 | 2020-05-19 |  | Opr Eval | Operator Eval #1 | 2020-05-16 | 2020-05-19
Hydraulics | Hydraulic Test ( Steering Pump Perf) | 2020-05-20 | 2020-06-07 |  | Hydraulics | Hydraulic Test ( Steering Pump Perf) | 2020-05-20 | 2020-06-07
SW | Software Checkout #2 | 2020-06-08 | 2020-06-13 |  | SW | Software Checkout #2 | 2020-06-08 | 2020-06-13
Opr Eval | Operator Eval #2 | 2020-06-14 | 2020-06-17 |  | Opr Eval | Operator Eval #2 | 2020-06-14 | 2020-06-17
Cooling2 | LRC Water Flow Test & System (STP 151 & 155) | 2020-06-18 | 2020-06-26 | Pilot EDS Freeze | Cooling2 | LRC Water Flow Test & System (STP 151 & 155) | 2020-06-18 | 2020-06-26 | Pilot EDS Freeze
Cooling3 | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration | 2020-06-27 | 2020-07-23 |  | Cooling3 | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT with Fuel Level Sensor calibration | 2020-06-27 | 2020-07-23
Safety and Regs | Safety Audit | 2020-07-24 | 2020-07-24 |  | Issue | Issue resolution | 2020-07-24 | 2020-07-28
Safety and Regs | Service Audit | 2020-07-25 | 2020-07-25 |  | Safety and Regs | Safety Audit | 2020-07-29 | 2020-07-29
Engine | LRC STP 401 Engine Audit | 2020-07-25 | 2020-07-27 |  | Safety and Regs | Service Audit | 2020-07-30 | 2020-07-30
Elec | Electric Load Study (Alt Charging capacity) | 2020-07-28 | 2020-07-31 |  | Engine | LRC STP 401 Engine Audit | 2020-07-30 | 2020-08-01
Safety and Regs | ISO 5010 Steering Feasibility | 2020-08-01 | 2020-08-20 |  | Elec | Electric Load Study (Alt Charging capacity) | 2020-08-02 | 2020-08-05
Safety and Regs | ISO 3450 Brake Feasibility | 2020-08-21 | 2020-09-04 |  | Safety and Regs | ISO 5010 Steering Feasibility | 2020-08-06 | 2020-08-25
SW | Software Checkout #3 | 2020-09-05 | 2020-09-10 |  | Safety and Regs | ISO 3450 Brake Feasibility | 2020-08-26 | 2020-09-09
Endurance | 980GC Endurance 0-500 hrs+ Inspection | 2020-09-11 | 2020-11-16 |  | SW | Software Checkout #3 | 2020-09-10 | 2020-09-15
Safety and Regs | ISO 5006 (Virtual Audit) | 2020-11-17 | 2020-11-22 |  | Endurance | 980GC Endurance 0-500 hrs+ Inspection | 2020-09-16 | 2020-11-21
| PPG 980GC Stg V HRC PD#2 (SN) | 2020-05-12 | 2021-07-02 |  | Safety and Regs | ISO 5006 (Virtual Audit) | 2020-11-22 | 2020-11-27
Machine Build | Machine Build | 2019-02-10 | 2019-03-22 |  |  | PPG 980GC Stg V HRC PD#2 (SN) | 2020-05-12 | 2021-07-02
Machine Build | Ship Machine to PPG | 2019-03-24 | 2019-05-08 |  | Machine Build | Machine Build | 2019-02-10 | 2019-03-22
Machine Check | Machine Checkout STP-64 | 2020-05-12 | 2020-05-15 |  | Machine Build | Ship Machine to PPG | 2019-03-24 | 2019-05-08
Opr Eval | Operator Eval | 2020-05-16 | 2020-05-19 |  | Machine Check | Machine Checkout STP-64 | 2020-05-12 | 2020-05-15
SW | SW Checkout # 1 | 2020-05-20 | 2020-05-25 |  | Opr Eval | Operator Eval | 2020-05-16 | 2020-05-19
Performance1 | L5 Tuning and Performance Check #1 | 2020-05-26 | 2020-06-02 |  | SW | SW Checkout # 1 | 2020-05-20 | 2020-05-25
Performance2 | Rimpull and Response Test | 2020-06-03 | 2020-06-15 |  | Performance1 | L5 Tuning and Performance Check #1 | 2020-05-26 | 2020-06-02
Engine | Engine and SW Check | 2020-06-16 | 2020-06-18 |  | Engine | Engine and SW Check | 2020-06-03 | 2020-06-05
Transmission | XMSN Tuning | 2020-06-19 | 2020-06-27 |  | Transmission | XMSN Tuning | 2020-06-06 | 2020-06-14
SW | Software Checkout #2 (STP 230) | 2020-06-28 | 2020-07-03 | Pilot EDS Freeze | Endurance | Machine Endurance 100 hrs | 2020-06-15 | 2020-06-20
Performance1 | L5 Tuning with Operator # 1 | 2020-07-04 | 2020-07-08 |  | Performance2 | Rimpull and Response Test | 2020-06-21 | 2020-07-03
Performance5 | Engine Exhaust AFT controls | 2020-07-09 | 2020-07-10 |  | Issue | Issue resolution | 2020-07-04 | 2020-07-08
Hydraulics | Hydraulic Test (Service Brake Modulation)+ Opr Eval | 2020-07-09 | 2020-07-24 |  | SW | Software Checkout #2 (STP 230) | 2020-07-09 | 2020-07-16 | Pilot EDS Freeze
Light Structures | Light Fan and Heavy Structure OMSA Hood & Cooling Pkg & MER- 120 channels | 2020-07-25 | 2020-09-03 | 200 channels | Performance1 | L5 Tuning with Operator # 1 | 2020-07-17 | 2020-07-21
NVH | HRC Sound Testing (Plus Hydraulic+ exhaust characterization) | 2020-09-04 | 2020-09-08 |  | Performance5 | Engine Exhaust AFT controls | 2020-07-22 | 2020-07-23
SW | Software Checkout #3 (STP 230) | 2020-09-09 | 2020-09-14 |  | Hydraulics | Hydraulic Test (Service Brake Modulation)+ Opr Eval | 2020-07-24 | 2020-08-08
Safety and Regs | Safety & Service Audit | 2020-09-15 | 2020-09-17 |  | Light Structures | Light Fan and Heavy Structure OMSA Hood & Cooling Pkg & MER- 120 channels | 2020-08-09 | 2020-09-18 | 200 channels
Elec | Harness routing Audit | 2020-09-18 | 2020-09-18 |  | NVH | HRC Sound Testing (Plus Hydraulic+ exhaust characterization) | 2020-09-19 | 2020-09-23
Safety and Regs | EN 13309 EMC Testing- Engg Test | 2020-09-19 | 2020-09-26 |  | Issue | Issue resolution | 2020-09-24 | 2020-09-28
Cooling1 | STP-153 (Airflow Testing) | 2020-09-27 | 2020-10-02 |  | SW | Software Checkout #3 (STP 230) | 2020-09-29 | 2020-10-04
Cooling2 | STP-151 & 155 (Water Flow & System Test) | 2020-10-03 | 2020-10-11 |  | Safety and Regs | Safety & Service Audit | 2020-10-05 | 2020-10-07
Cooling1 | Dust Ejector Measurement | 2020-10-12 | 2020-10-14 |  | Elec | Harness routing Audit | 2020-10-08 | 2020-10-08
Performance2 | L5 Tuning with Operator # 2 (Shift Performance) | 2020-10-15 | 2020-10-23 |  | Safety and Regs | EN 13309 EMC Testing- Engg Test | 2020-10-09 | 2020-10-16
Cooling3 | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT + Fuel Sensor Calibration | 2020-10-24 | 2020-11-23 |  |  | PPG 980GC Stg V HRC PD#3 (SN) | 2020-05-15 | 2021-07-02
Engine | STP 401 HRC Engine Audit | 2020-11-24 | 2020-11-27 |  | Machine Check | Machine Checkout STP-64 | 2020-05-15 | 2020-05-18
Performance3 | Stage 5 Engine TC-L Cold Room | 2020-11-28 | 2020-12-27 |  | Cooling1 | STP-153 (Airflow Testing) | 2020-05-19 | 2020-05-24
SW | Software Checkout #4 (STP 230)+ Endurance | 2021-01-10 | 2021-01-20 |  | Cooling2 | STP-151 & 155 (Water Flow & System Test) | 2020-05-25 | 2020-06-02
Performance4 | Engg Perf Productivity | 2021-04-30 | 2021-06-14 |  | Cooling1 | Dust Ejector Measurement | 2020-06-03 | 2020-06-05
Performance4 | Stage 5 Engine Altitude | 2021-05-30 | 2021-07-02 |  | Performance2 | L5 Tuning with Operator # 2 (Shift Performance) | 2020-06-06 | 2020-06-14
| PPG 980GC HRC Pilot #1 (SN) | 2021-01-18 | 2021-04-01 |  | Cooling3 | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT + Fuel Sensor Calibration | 2020-06-15 | 2020-07-15
Machine Check | Machine Checkout STP-64 | 2021-01-18 | 2021-01-21 |  | Engine | STP 401 HRC Engine Audit | 2020-07-16 | 2020-07-19
SW | SW Checkout #1 | 2021-01-22 | 2021-02-01 |  | Performance3 | Stage 5 Engine TC-L Cold Room | 2020-07-20 | 2020-08-18
NVH | Sound Testing (Issue Resolution Not meeting Rqmts) | 2021-02-02 | 2021-02-07 |  | SW | Software Checkout #4 (STP 230)+ Endurance | 2020-09-01 | 2020-09-11
Performance | L5 Checkout | 2021-02-08 | 2021-02-13 |  | Performance4 | Engg Perf Productivity | 2020-09-21 | 2020-11-05
Opr Eval | Operator Eval #1 | 2021-02-14 | 2021-02-17 |  | Performance6 | Stage 5 Engine Altitude | 2021-05-30 | 2021-07-02
SW | SW Checkout #2 | 2021-02-18 | 2021-02-23 |  |  | PPG 980GC HRC Pilot #1 (SN) | 2021-01-30 | 2021-04-13
Opr Eval | Operator Eval #2 | 2021-02-24 | 2021-02-27 |  | Machine Check | Machine Checkout STP-64 | 2021-01-30 | 2021-02-02
Light Structures | OMSA Light Fabs Hood | 2021-02-28 | 2021-03-18 |  | SW | SW Checkout #1 | 2021-02-03 | 2021-02-13
SW | Software Checkout #3 | 2021-03-19 | 2021-03-24 |  | NVH | Sound Testing (Issue Resolution Not meeting Rqmts) | 2021-02-14 | 2021-02-19
Safety and Regs | EN 13309 EMC Testing-HRC | 2021-03-25 | 2021-04-01 |  | Performance | L5 Checkout | 2021-02-20 | 2021-02-25
| QPG 980GC LRC Pilot #2 (SN) | 2021-01-15 | 2021-04-26 |  | Opr Eval | Operator Eval #1 | 2021-02-26 | 2021-03-01
Machine Check | Machine Checkout STP-64 | 2021-01-15 | 2021-01-20 |  | SW | SW Checkout #2 | 2021-03-02 | 2021-03-07
SW | Software Checkout | 2021-01-21 | 2021-01-26 |  | Opr Eval | Operator Eval #2 | 2021-03-08 | 2021-03-11
Safety and Regs | ISO 5010- HMU CERT | 2021-01-27 | 2021-02-09 |  | Light Structures | OMSA Light Fabs Hood | 2021-03-12 | 2021-03-30
Safety and Regs | ISO 3450 Brake- CERT | 2021-02-10 | 2021-02-24 |  | SW | Software Checkout #3 | 2021-03-31 | 2021-04-05
Safety and Regs | EMC Testing | 2021-02-25 | 2021-03-20 |  | Safety and Regs | EN 13309 EMC Testing-HRC | 2021-04-06 | 2021-04-13
Hydraulics | Hydraulic Signature Test- Documentation | 2021-03-21 | 2021-04-15 |  |  | QPG 980GC LRC Pilot #2 (SN) | 2021-01-15 | 2021-04-26
NVH | Sound Testing- ISO 9533, HAWB | 2021-04-16 | 2021-04-22 |  | Machine Check | Machine Checkout STP-64 | 2021-01-15 | 2021-01-20
Safety and Regs | ISO 10570 Articulation Lock | 2021-04-23 | 2021-04-26 |  | SW | Software Checkout | 2021-01-21 | 2021-01-26
Safety and Regs | ISO 5006 (Virtual Audit) | 2021-04-27 | 2021-05-02 |  | Safety and Regs | ISO 5010- HMU CERT | 2021-01-27 | 2021-02-09
| QPG 980GC HRC Pilot #3 (SN) | 2021-03-23 | 2021-10-22 |  | Safety and Regs | ISO 3450 Brake- CERT | 2021-02-10 | 2021-02-24
Machine Check | Machine Checkout STP-64 | 2021-03-23 | 2021-03-28 |  | Safety and Regs | EMC Testing | 2021-02-25 | 2021-03-20
NVH | Sound Testing-ISO 9533, ISO 6393-6396 | 2021-03-29 | 2021-04-04 |  | Hydraulics | Hydraulic Signature Test- Documentation | 2021-03-21 | 2021-04-15
Endurance | 980GC Endurance 0-500 hrs+ 250 hr Inspections | 2021-04-05 | 2021-06-10 |  | NVH | Sound Testing- ISO 9533, HAWB | 2021-04-16 | 2021-04-22
Endurance | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | 2021-06-11 | 2021-08-16 |  | Safety and Regs | ISO 10570 Articulation Lock | 2021-04-23 | 2021-04-26
Endurance | 980GC Endurance 1001-1500 hrs+ 250 hr inspections | 2021-08-17 | 2021-10-22 |  | Safety and Regs | ISO 5006 (Virtual Audit) | 2021-04-27 | 2021-05-02
[6 empty] | QPG 980GC HRC Pilot #3 (SN) | 2021-03-23 | 2021-10-22
[5 empty] | Machine Check | Machine Checkout STP-64 | 2021-03-23 | 2021-03-28
[5 empty] | NVH | Sound Testing-ISO 9533, ISO 6393-6396 | 2021-03-29 | 2021-04-04
[5 empty] | Endurance | 980GC Endurance 0-500 hrs+ 250 hr Inspections | 2021-04-05 | 2021-06-10
[5 empty] | Endurance | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | 2021-06-11 | 2021-08-16
[5 empty] | Endurance | 980GC Endurance 1001-1500 hrs+ 250 hr inspections | 2021-08-17 | 2021-10-22
Formulas:
Start = MIN([Start, row below]:C21)
Start = MIN([Start, row below]:L21)
Finish = MAX([Finish, row below]:D21)
Finish = MAX([Finish, row below]:M21)
Note on B89: Viresh B Shah: Trans Control Throttle; Opr Eval; Xsmn Shifting Quality-Opr Eval; Machine Stability chk-Opr Eval;Trans Neutralizer Functional Check
Note on K95: Viresh B Shah: Trans Control Throttle; Opr Eval; Xsmn Shifting Quality-Opr Eval; Machine Stability chk-Opr Eval;Trans Neutralizer Functional Check

## PMO- April 4 2019
Machine S/N | Phase | 2019-02-24 |  | 2019-03-03 | 2019-03-10 | 2019-03-17 | 2019-03-24 | 2019-03-31 | 2019-04-07 | 2019-04-14 | 2019-04-21 | 2019-04-28 | 2019-05-05 | 2019-05-12 |  | 2019-05-19 | 2019-05-26 |  |  | 2019-06-02 | 2019-06-09 | 2019-06-16 | 2019-06-23 | 2019-06-30 | 2019-07-07 | 2019-07-14 |  | 2019-07-21 | 2019-07-28 |  | 2019-08-04 |  | 2019-08-11 | 2019-08-18 | 2019-08-25 | 2019-09-01 | 2019-09-08 |  | 2019-09-15 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 2019-10-13 | 2019-10-20 | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 |  | 2020-01-19 | 2020-01-26 | 2020-02-02 | 2020-02-09 | 2020-02-16 | 2020-02-23 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22 | 2020-03-29 |  | 2020-04-05 | 2020-04-12 |  | 2020-04-19 |  | 2020-04-26 |  |  | 2020-05-03 |  |  |  | 2020-05-10 |  |  | 2020-05-17 |  | 2020-05-24 |  |  | 2020-05-31 |  |  | 2020-06-07 |  |  |  | 2020-06-14 | 2020-06-21 |  | 2020-06-28 |  | 2020-07-05 |  |  | 2020-07-12 |  | 2020-07-19 | 2020-07-26 |  |  |  | 2020-08-02 |  |  | 2020-08-09 |  | 2020-08-16 |  |  | 2020-08-23 |  | 2020-08-30 |  | 2020-09-06 | 2020-09-13 |  | 2020-09-20 |  | 2020-09-27 | 2020-10-04 | 2020-10-11 |  |  | 2020-10-18 | 2020-10-25 | 2020-11-01 | 2020-11-08 | 2020-11-15 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-20 | 2020-12-27 | 2021-01-03 | 2021-01-10 |  | 2021-01-17 |  |  |  | 2021-01-24 |  | 2021-01-31 |  |  | 2021-02-07 |  |  | 2021-02-14 |  | 2021-02-21 |  | 2021-02-28 | 2021-03-07 | 2021-03-14 |  | 2021-03-21 |  |  | 2021-03-28 |  | 2021-04-04 |  | 2021-04-11 |  | 2021-04-18 |  | 2021-04-25 | 2021-05-02 | 2021-05-09 | 2021-05-16 | 2021-05-23 | 2021-05-30 | 2021-06-06 |  | 2021-06-13 | 2021-06-20 | 2021-06-27 | 2021-07-04 | 2021-07-11 | 2021-07-18 | 2021-07-25 | 2021-08-01 | 2021-08-08 | 2021-08-15 |  | 2021-08-22 | 2021-08-29 | 2021-09-05 | 2021-09-12 | 2021-09-19 | 2021-09-26 | 2021-10-03 | 2021-10-10 | 2021-10-17 | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09
980GC Milestone | 980GC Milestone |  | Launch | [23 empty] | DR 1/2 |  |  | GW 1/2 |  | DR 3, DD3 | [5 empty] | 100% PD EDS Freeze | [18 empty] | GW 3 | [8 empty] | GW 4 | [34 empty] | 100% Production EDS Freeze | [21 empty] | 100% Pilot EDS Freeze | [8 empty] | GW 5 | [61 empty] | GW 5.5 | [24 empty] | GW 6
980GC SW Milestone | 980GC SW Milestone | [62 empty] | Release # 1 | [26 empty] | Release # 2 | [19 empty] | Release # 3 | [24 empty] | Release # 4
980GC TIC Report Milestone | 980GC TIC Report Milestone | [107 empty] | Sound- Back-up Alarm, Horn-ISO 9566 | [43 empty] | Steering-ISO 5010
W7K00288 | PPG 980GC TB | [13 empty] | 980GC TB Machine Build (hyd pump, implement valve) |  |  | Machine Checkout STP-64 | Hydraulic Development (Setup/Run/Teardown) |  |  |  | Implement SW Checkout |  | Operator Eval
SN | QPG 980GC LRC PD#1 | [67 empty] | Machine Checkout STP-64 |  |  | Software Checkout #1 |  | Sound Testing (1st Pass screening) |  | L5 Tuning and Performance Check | Operator Eval #1 |  |  | Hydraulic Test | [7 empty] | Software Checkout #2 |  | Operator Eval #2 |  | LRC Water Flow Test & System (STP 151 & 155) |  |  |  | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT | [6 empty] | LRC STP 401 Engine Audit | Software Checkout #3 |  | ISO 5010 Steering Feasibility | [6 empty] | ISO 3450 Brake Feasibility |  |  |  |  | 980GC Endurance 0-500 hrs+ Inspection
SN | PPG 980GC Stg V HRC PD#2 | [77 empty] | Machine Checkout STP-64 |  | Steering Bump Stop Eval |  | Operator Eval | SW Checkout # 1 |  | L5 Tuning and Performance Check #1 |  |  | Rimpull and Response Test |  |  |  |  | Engine and SW Check | XMSN Tuning |  |  | Software Checkout #3 | L5 Tuning with Operator |  | Light Fan and Heavy Structure OMSA Hood & Cooling Pkg & MER- 120 channels | [6 empty] | HRC Sound Testing |  | EMC Testing- Engg Test |  |  |  | STP-153 (Airflow Testing) |  | STP-151 & 155 (Water Flow/System Test) |  |  | Dust Ejector Measurement |  | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT |  |  |  |  | STP 401 HRC Engine Audit |  | Stage 5 Engine TC-L Cold Room |  |  |  |  | Stage 5 Engine Altitude
SN | PPG 980GC HRC Pilot #1 | [147 empty] | Machine Checkout STP-64 |  | SW Checkout #1 |  |  |  | Sound Testing | L5 Checkout |  |  | Operator Eval #1 |  | SW Checkout #2 | Operator Eval #2 | OMSA Light Fabs Hood |  |  |  | SW S13 Checkout #3 |  | EMC Testing-HRC
SN | QPG 980GC LRC Pilot #2 | [145 empty] | Machine Checkout STP-64 |  |  | Software Checkout |  |  | ISO 5010- HMU CERT |  |  |  |  | ISO 3450 Brake- CERT |  |  |  |  | EMC Testing |  |  |  |  | Hydraulic Signature Test- Documentation | [7 empty] | Sound Testing- ISO 9533, HAWB |  | Articulation Lock
SN | QPG 980GC HRC Pilot #3 | [168 empty] | Machine Checkout STP-64 |  | Sound Testing-ISO 9533, ISO 6393-6396 |  | 980GC Endurance 0-500 hrs+ 250 hr Inspections | [11 empty] | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | [10 empty] | 980GC Endurance 1001-1500 hrs+ 250 hr inspections

## PMO-March 6 2019
Machine S/N | Phase | 2019-02-20 | 2019-02-27 |  | 2019-03-06 | 2019-03-13 | 2019-03-20 | 2019-03-27 | 2019-04-03 | 2019-04-10 |  | 2019-04-17 | 2019-04-24 |  | 2019-05-01 |  | 2019-05-08 | 2019-05-15 | 2019-05-22 |  | 2019-05-29 | 2019-06-05 |  | 2019-06-12 |  |  |  | 2019-06-19 | 2019-06-26 | 2019-07-03 | 2019-07-10 |  | 2019-07-17 | 2019-07-24 | 2019-07-31 | 2019-08-07 | 2019-08-14 | 2019-08-21 | 2019-08-28 | 2019-09-04 |  | 2019-09-11 | 2019-09-18 | 2019-09-25 | 2019-10-02 | 2019-10-09 | 2019-10-16 | 2019-10-23 | 2019-10-30 | 2019-11-06 | 2019-11-13 | 2019-11-20 | 2019-11-27 | 2019-12-04 | 2019-12-11 | 2019-12-18 | 2019-12-25 | 2020-01-01 | 2020-01-08 | 2020-01-15 | 2020-01-22 | 2020-01-29 | 2020-02-05 | 2020-02-12 | 2020-02-19 | 2020-02-26 | 2020-03-04 | 2020-03-11 |  | 2020-03-18 | 2020-03-25 |  | 2020-04-01 | 2020-04-08 |  |  | 2020-04-15 |  |  | 2020-04-22 | 2020-04-29 | 2020-05-06 |  | 2020-05-13 |  |  | 2020-05-20 |  | 2020-05-27 | 2020-06-03 | 2020-06-10 |  |  | 2020-06-17 |  | 2020-06-24 | 2020-07-01 |  | 2020-07-08 |  |  | 2020-07-15 |  | 2020-07-22 |  |  | 2020-07-29 |  |  | 2020-08-05 | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-02 |  | 2020-09-09 |  | 2020-09-16 | 2020-09-23 | 2020-09-30 | 2020-10-07 | 2020-10-14 |  | 2020-10-21 | 2020-10-28 | 2020-11-04 | 2020-11-11 | 2020-11-18 | 2020-11-25 | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2020-12-23 | 2020-12-30 | 2021-01-06 | 2021-01-13 |  | 2021-01-20 |  | 2021-01-27 | 2021-02-03 | 2021-02-10 |  |  | 2021-02-17 | 2021-02-24 |  |  |  | 2021-03-03 |  | 2021-03-10 |  |  | 2021-03-17 |  |  | 2021-03-24 |  | 2021-03-31 |  |  | 2021-04-07 |  | 2021-04-14 |  |  | 2021-04-21 | 2021-04-28 | 2021-05-05 | 2021-05-12 | 2021-05-19 | 2021-05-26 | 2021-06-02 | 2021-06-09 |  | 2021-06-16 | 2021-06-23 | 2021-06-30 | 2021-07-07 | 2021-07-14 | 2021-07-21 | 2021-07-28 | 2021-08-04 | 2021-08-11 |  | 2021-08-18 | 2021-08-25 | 2021-09-01 | 2021-09-08 | 2021-09-15 | 2021-09-22 | 2021-09-29 | 2021-10-06 | 2021-10-13 | 2021-10-20 | 2021-10-27
980GC Milestone | 980GC Milestone |  |  | Launch | [21 empty] | DR 1/2 | [5 empty] | GW 1/2 |  |  |  | DR 3, DD3 |  |  |  |  | 100% EDS Freeze
W7K00288 | PPG 980GC TB | [9 empty] | 980GC TB Machine Build (hyd pump, implement valve) |  |  | Machine Checkout STP-64 |  | Hydraulic Development (Setup/Run/Teardown) |  |  |  | Implement SW Checkout |  |  | Fan/Brake System Eval |  | Operator Eval |  | OMSA Shake Test
SN | CQL 980GC LRC PD#1 | [67 empty] | Machine Checkout STP-64 |  |  | Software Checkout #1 |  |  | Sound Testing (1st Pass screening) | L5 Tuning and Performance Check |  | Operator Eval #1 | Hydraulic Test |  |  |  | Software Checkout #2 |  | Operator Eval #2 |  | LRC Water Flow Test | LRC STP 152 (Ambient Capability) & STP-154 (IMT) w/ UHT |  |  |  | LRC STP 401 Engine Audit | Software Checkout #3 |  | ISO 5010 Steering Feasibility | [5 empty] | ISO 3450 Brake Feasibility |  |  |  |  | 980GC Endurance 0-500 hrs+ Inspection
SN | PPG 980GC HRC PD#2 | [79 empty] | Machine Checkout STP-64 |  | Steering Bump Stop Eval | Operator Eval |  | SW Checkout # 1 |  | Engine and SW Check | [9 empty] | HRC Sound Testing |  | EMC Testing- Engg Test |  |  | STP-153 (Airflow Testing) |  | STP-151 & 155 (Water Flow/System Test) |  |  | Dust Ejector Measurement | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT | [5 empty] | STP 401 HRC Engine Audit |  | Stage 5 Engine TC-L Cold Room | [5 empty] | Stage 5 Engine Altitude
SN | PPG 980GC HRC Pilot #1 | [141 empty] | Machine Checkout STP-64 | SW Checkout #1 |  |  |  | Sound Testing | Operator Eval #1 |  | SW Checkout #2 |  | Operator Eval #2 | OMSA Light Fabs Hood | [6 empty] | SW S13 Checkout #3 |  |  | EMC Testing-HRC |  |  | Articulation Lock
SN | CQL 980GC LRC Pilot #2 | [135 empty] | Machine Checkout STP-64 |  | Software Checkout | ISO 5010- HMU CERT |  | ISO 3450 Brake- CERT |  |  |  |  | EMC Testing | [8 empty] | Hydraulic Signature Test- Documentation | [9 empty] | Sound Testing- ISO 9533, HAWB
SN | CQL 980GC HRC Pilot #3 | [155 empty] | Machine Checkout STP-64 |  | Sound Testing-ISO 9533, ISO 6393-6396 |  |  | 980GC Endurance 0-500 hrs+ 250 hr Inspections | [13 empty] | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | [9 empty] | 980GC Endurance 1001-1500 hrs+ 250 hr inspections

## PMO- Feb 28 2019
Machine S/N | Phase | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 |  | 2019-05-06 | 2019-05-13 | 2019-05-20 |  | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 |  | 2020-01-27 |  |  | 2020-02-03 |  | 2020-02-10 |  | 2020-02-17 |  | 2020-02-24 |  |  | 2020-03-02 |  |  | 2020-03-09 | 2020-03-16 |  |  | 2020-03-23 |  | 2020-03-30 |  | 2020-04-06 |  | 2020-04-13 |  |  |  | 2020-04-20 |  |  | 2020-04-27 | 2020-05-04 | 2020-05-11 |  | 2020-05-18 |  | 2020-05-25 |  |  | 2020-06-01 |  | 2020-06-08 |  | 2020-06-15 |  | 2020-06-22 | 2020-06-29 |  | 2020-07-06 |  | 2020-07-13 |  | 2020-07-20 |  | 2020-07-27 | 2020-08-03 | 2020-08-10 |  | 2020-08-17 |  | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 |  | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 |  | 2020-11-23 | 2020-11-30 |  | 2020-12-07 | 2020-12-14 |  | 2020-12-21 |  | 2020-12-28 | 2021-01-04 |  | 2021-01-11 |  |  | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 |  | 2021-04-05 | 2021-04-12 | 2021-04-19
W7K00288 | PPG 980GC TB |  |  | 980GC TB Machine Build (hyd pump, implement valve) |  | Machine Checkout STP-64 | Hydraulic Development (Setup/Run/Teardown) |  |  |  | OMSA Shake Test |  |  | Implement SW Checkout |  | Operator Eval
SN | CQL 980GC LRC PD#1 | [41 empty] | Machine Checkout STP-64 | [6 empty] | Software Checkout #1 |  |  |  | Sound Testing (1st Pass screening) |  | L5 Tuning and Performance Check | Operator Eval #1 |  | Hydraulic Test | [9 empty] | Software Checkout #2 |  | Operator Eval #2 | LRC Water Flow Test |  |  | LRC Cooling Test | [9 empty] | LRC STP 401 Engine Audit |  | OMSA Hood & MER |  |  |  |  | Software Checkout #3 |  | ISO 5010 | [7 empty] | ISO 3450 Brake Cert STP24 |  |  |  |  | 980GC Endurance 0-500 hrs+ Inspection
SN | PPG 980GC HRC PD#2 | [43 empty] | Machine Checkout STP-64 |  | Operator Eval |  | L5 Tuning and Performance Check #1 |  |  | Rimpull and Response Test | [5 empty] | SW Checkout |  |  | Engine and SW Check | XMSN Tuning |  |  | L5 Tuning with Operator | Sound Testing |  | EMC Testing- Engg Test |  | STP-153 (Airflow Testing) |  | STP-155 (Water Flow/System Test) |  |  |  | HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT | [7 empty] | STP 401 HRC Engine Audit |  |  |  | TC-L Cold Room | [8 empty] | ISO 5010 |  |  |  | ISO 3450 Brake Cert STP24 | [5 empty] | Altitude
SN | PPG 980GC HRC Pilot #1 | [122 empty] | Machine Checkout STP-64 |  |  | SW Checkout #1 |  |  | Sound Testing |  | Operator Eval #1 |  |  | SW Checkout #2 |  | Operator Eval #2 | OMSA Light Fabs Hood |  |  |  | SW S13 Checkout #3 | ISO 5010- EH CERT | [6 empty] | EMC Testing-HRC
SN | CQL 980GC LRC Pilot #2 | [65 empty] | Machine Checkout STP-64 | [7 empty] | Software Checkout |  |  | ISO 5010- HMU CERT |  |  |  |  | ISO 3450 Brake- CERT | [6 empty] | EMC Testing | [8 empty] | Hydraulic Signature Test- Documentation | [9 empty] | Sound Testing- ISO 9533, HAWB, ISO 6393-6396
SN | CQL 980GC HRC Pilot #3 | [65 empty] | Machine Checkout STP-64 | [6 empty] | Sound Testing-ISO 9533, ISO 6393-6396 |  |  |  |  | 980GC Endurance 0-500 hrs+ 250 hr Inspections | [23 empty] | 980GC Endurance 501-1000 hrs+ 250 hr Inspections | [15 empty] | 980GC Endurance 1001-1500 hrs+ 250 hr inspections

## 2Sheet2
980GC PMO
date | milestones
2020-02-01 | PD build
2020-07-01 | Pilot EDS freeze
2020-11-01 | Pilot build
2021-08-01 | Production EDS freeze
2022-01-01 | Production
Budget Summary - PPG's estimate
2019 | 130011
2020 | 379500
2021 | 527000
2022 | 50000 | Only Jan-Feb of 2022
Total | 1086511
PPG Testbed activities (2019)
date | activity | approximate cost | time
| Testbed build (hyd pump, implement valve) | 10398 | 2 weeks
| Budget Alignment | 61343
| Machine checkout (STP-064) | 6189 | 3 days
| Implement SW checkout | 8640 | 2 weeks
| Operator evaluation | 2877 | 3 days
| Shake OMSA | 0
| Hydraulic development | 38844 | 3 weeks
128291
PPG PD activities (1 PD) (2020) |  |  |  | CQL PD activities (1 PD) (2020)
date | activity | approximate cost | time | date | activity | QPG will have to provide cost | time
| Machine checkout (STP-064) | 5500 | 3 days |  | Machine checkout STP-064 | 6581 | 11 days
| Operator evaluation | 3000 | 3 days |  | SW checkout | 6136 | 10 days
| Sound test | 2000 | 5 days |  | Sound test | 2894 | 3 days
| XMSN tuning | 0 | 10 days |  | Operator evaluation | 3232 | 5 days
| EMC test | 0 | 5 days |  | Hydraulic test | 15720 | 3 weeks
| airflow | 5500 | 5 days |  | SW checkout | 6136 | 10 days
| waterflow | 5500 | 5 days |  | Operator evaluation | 3232 | 4 days
| Light structures OMSA (hood) | 45000 | Funke's team to QPG |  | Light structures OMSA (hood) | 29190 | 5 weeks
| cooling/UHT test | 50000 | 20 days |  | SW checkout | 6136 | 10 days
| STP401 | 10000 |  |  | ISO 5010 | 15946 | 4 weeks
| controls support | 20000 | 20 days |  | ISO 3450 | 26500 | 4 weeks
| budget alignment | 55000
| Rimpull response | 25000 |  |  | Endurance 500 hours | 54550 | 2.5 months
| Altitude response | 30000 |  |  | XMSN tuning | 22970 | 4weeks | 200
| L5 tuning | 5000 |  |  | cooling/UHT test | 34522 | 4weeks
| cold room at TC-L (2 weeks) | 100000 |  |  | Hydraulic retest | 21440 | 3weeks
| EMC | 5000 |  |  | STP401 | 9320 | 2week
| Pilot update | 10000
| Service publications (shipping cost) | 3000
| PPG 2020 budget including budget alignment | 379500 |  |  | CQL 2020 budget based on PPG rates | 264505
PPG Pilot activities (1 Pilot)(2021) |  |  |  | CQL Pilot activities (1 Pilot)(2021)
date | activity | approximate cost | time | date | activity | QPG will have to provide cost | time
| budget alignment | 55000 |  |  | Machine checkout (STP-064) | 6581 | 11days
| endurance (3000 hrs) | 330000 |  |  | SW checkout | 6136 | 10days
| Productivity | 75000 |  |  | Sound certification (LRC) | 2894 | 3days
| Cooling/UHT retest | 40000 |  |  | Operator evaluation | 3232 | 4days
| EMC | 0 |  |  | Hydraulic signature | 15720 | 4weeks
| L5 checkout | 5000 |  |  | SW checkout | 6136 | 10days
| Sound certification (EU) | 2000 |  |  | Operator evaluation | 3232 | 4days
| XMSN signature | 0 |  |  | Light structures OMSA retest (hood) | 49290 | 4weeks
| controls support | 20000 | 20 days |  | SW checkout | 6136 | 10days
| SW release after endurance (2022) | 15000 |  |  | ISO 5010 | 19240 | 3weeks
| 2 months support (2022) | 35000 |  |  | ISO 3450 | 28700 | 3weeks
[5 empty] | EMC test | 39113 | 10days
[5 empty] | Endurance (3000 hrs) | 305900 | 13months
[5 empty] | MLIT | 74995
| PPG 2021 budget including only budget alignment | 577000 |  |  | CQL 2021 budget based on PPG rates | 573360
Note on C26: Andy McCallister: Not confirmed/budgeted activity

## Raw data
Activity ID | Activity Name | Original Duration | Start | Finish | Budgeted Total Cost | Remaining Total Cost | PDGT GMD Channel Count | Primary Resource | GPM Location
980GC Validation Program |  | 1075 | 01-Mar-17 A | 2021-06-24 | 1070077.22 | 1032930.9 | 801
Project Management |  | 953 | 01-Mar-17 A | 2020-12-23 | 9195.44 | 6548.3 | 0
966GC-1070 | Project Management - 2017 | 208 | 01-Mar-17 A | 22-Dec-17 A | 2585.44 | 0 |  | guppyam.Guppy Amy M | PPG
980GC-105655 | Project Management - 2019 | 247 | 02-Jan-19 A | 2019-12-20 | 1905 | 1843.3 |  | guppyam.Guppy Amy M | PPG
980GC-108330 | Project Management - 2020 | 249 | 02-Jan-20* | 2020-12-23 | 4705 | 4705 |  | guppyam.Guppy Amy M | PPG
Budget Alignment |  | 930 | 03-Apr-17 A | 2020-12-23 | 143371.32 | 109775.78 | 0
966GC-1000 | PPG Engineer Support - 2017 | 185 | 03-Apr-17 A | 22-Dec-17 A | 8050 | 0 |  | rogerar2.Rogers Adam R | PPG
966GC-1010 | Budget Alignment 2017 - Machine Supervisor | 185 | 03-Apr-17 A | 22-Dec-17 A | 2760 | 0 |  | mccalad.McCallister Andy D | PPG
966GC-1020 | Budget Alignment 2017 - L6 Val Engr | 185 | 03-Apr-17 A | 22-Dec-17 A | 17250 | 0 |  | shahvb.Shah Viresh B | PPG
966GC-1040 | Budget Alignment 2017 - APPG | 165 | 01-May-17 A | 22-Dec-17 A | 0 | 0 |  |  | APPG
966GC-105905 | L6 Val Engr - Trip #1 to China | 5 | 25-Jun-18 A | 29-Jun-18 A | 3750 | 0 |  | shahvb.Shah Viresh B | Field
980GC-108205 | Budget Alignment - Machine Supervisor 2019 | 247 | 02-Jan-19 A | 2019-12-20 | 6104 | 5906.3 |  | mccalad.McCallister Andy D | PPG
980GC-108210 | Budget Alignment - L6 Val Engr 2019 | 247 | 02-Jan-19 A | 2019-12-20 | 23980 | 23203.32 |  | shahvb.Shah Viresh B | PPG
980GC-108215 | PPG Engineer Support - 2019 | 247 | 02-Jan-19 A | 2019-12-20 | 25044.65 | 24233.49 |  | layjd.Lay Joe D | PPG
980GC-110680 | L6 Val Engr - 2019 Trip #3 to China | 5 | 07-Oct-19* | 2019-10-11 | 8000 | 8000 |  | shahvb.Shah Viresh B | Field
980GC-108225 | Budget Alignment - L6 Val Engr 2020 | 249 | 02-Jan-20* | 2020-12-23 | 17031.8 | 17031.8 |  | shahvb.Shah Viresh B | PPG
980GC-108230 | PPG Engineer Support - 2020 | 249 | 02-Jan-20* | 2020-12-23 | 25247.44 | 25247.44 |  | layjd.Lay Joe D | PPG
980GC-108220 | Budget Alignment - Machine Supervisor 2020 | 249 | 02-Jan-20* | 2020-12-23 | 6153.42 | 6153.42 |  | mccalad.McCallister Andy D | PPG
Sound Work |  | 497 | 02-Jan-19 A | 2020-12-23 | 12039.64 | 11136 | 0
980GC-110685 | Sound Validation Engineer Support 980GC - 2019 | 247 | 02-Jan-19 A | 2019-12-20 | 2759.64 | 1856 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-110690 | Sound Validation Engineer Support 980GC - 2020 | 249 | 02-Jan-20* | 2020-12-23 | 9280 | 9280 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
Key Project Milestones |  | 785 | 20-Nov-17 A | 2021-04-16 | 0 | 0 | 0
966GC-105190 | GW 2/3 | 0 | 20-Nov-17 A |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
980XE-1000 | GW 4 | 0 | 19-Mar-18 A |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
966GC-1005 | GW 5 | 0 | 15-Jun-18 A |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
966GC-106950 | Machine Ready for Field (9/4/18) | 0 |  | 23-Jul-18 A | 0 | 0 |  | shahvb.Shah Viresh B | PPG
966GC-105160 | Receive 966GC Early Pilot | 0 | 25-Jul-18 A |  | 0 | 0 |  | rogerar2.Rogers Adam R | PPG
980GC-1016 | Pilot EDS Freeze | 0 | 13-Sep-19* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
980GC-1011 | PD Build | 0 | 14-Feb-20* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
980GC-108340 | Pilot Build | 0 | 14-Feb-20* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
980GC-108350 | Production EDS Freeze | 0 | 13-Nov-20* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
980GC-108360 | Production | 0 | 16-Apr-21* |  | 0 | 0 |  | shahvb.Shah Viresh B | PPG
Software Milestones |  | 110 | 20-Apr-18 A | 23-Jul-18 A | 0 | 0 | 0
966GC-105900 | Receive V01 SW | 0 | 20-Apr-18 A |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
966GC-105930 | Receive V03 SW | 0 | 25-May-18 A |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
966GC-105920 | Receive V02 SW | 0 | 29-May-18 A |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
966GC-105940 | Receive V04 SW | 0 | 23-Jul-18 A |  | 0 | 0 |  | egantr.Egan Thomas R | PPG
Testbed Phase |  | 149 | 2019-01-14 | 2019-08-13 | 116952.89 | 116952.89 | 68
PPG 980GC TB (W7K00288) |  | 149 | 2019-01-14 | 2019-08-13 | 116952.89 | 116952.89 | 68
LOE |  | 110 | 2019-03-11 | 2019-08-13 | 0 | 0 | 0
980GC-108240 | Start Testing 980GC Testbed | 0 | 2019-03-11 |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-108250 | LOE: 980GC Testbed | 52 | 2019-03-11 | 2019-05-21 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-108260 | Testing Complete 980GC Testbed | 0 |  | 2019-05-21 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-108270 | Reports Complete 980GC Testbed | 0 |  | 2019-08-13 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
OMSA Shake Test |  | 112 | 2019-01-14 | 2019-06-20 | 50004.89 | 50004.89 | 48
980GC-110700 | Planning & Procurement | 40 | 2019-01-14 | 2019-03-11 | 3148.89 | 3148.89 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110710 | SGL Strain Gage Lab - Instrument Parts | 3 | 2019-03-06 | 2019-03-08 | 3161 | 3161 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110770 | Setup - Shop Support Work | 3 | 11-Mar-19* | 2019-03-13 | 4972 | 4972 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-110720 | Instrument - Setup Bay | 3 | 2019-03-14 | 2019-03-18 | 9135 | 9135 | 48 | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110780 | Field Prep for OMSA | 1 | 2019-03-18 | 2019-03-18 | 8108 | 8108 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110730 | Run | 4 | 2019-03-19 | 2019-03-22 | 8632 | 8632 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110740 | Teardown | 1 | 2019-03-25 | 2019-03-25 | 1948 | 1948 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-110750 | Preliminary Analysis/Reporting | 3 | 2019-03-25 | 2019-03-27 | 2180 | 2180 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110760 | TIC Report | 60 | 2019-03-28 | 2019-06-20 | 8720 | 8720 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC TB Machine Build (hyd pump, implement valve) |  | 20 | 2019-03-12 | 2019-04-08 | 10398 | 10398 | 0
980GC-108430 | Plan | 10 | 2019-03-12 | 2019-03-25 | 1308 | 1308 |  | layjd.Lay Joe D | PPG
980GC-108440 | Setup | 10 | 2019-03-26 | 2019-04-08 | 9090 | 9090 |  | layjd.Lay Joe D | PPG
Machine Checkout STP-64 |  | 13 | 2019-03-26 | 2019-04-11 | 6189 | 6189 | 0
980GC-108280 | Plan | 10 | 2019-03-26 | 2019-04-08 | 1635 | 1635 |  | layjd.Lay Joe D | PPG
980GC-108290 | Run | 3 | 2019-04-09 | 2019-04-11 | 4554 | 4554 |  | layjd.Lay Joe D | PPG
Implement SW Checkout |  | 20 | 2019-03-29 | 2019-04-25 | 8640 | 8640 | 0
980GC-108310 | Plan | 10 | 2019-03-29 | 2019-04-11 | 2180 | 2180 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
980GC-108300 | Run | 10 | 2019-04-12 | 2019-04-25 | 6460 | 6460 |  | 01-88107-440.TSD881MGT - SEC07 RES440 MACHINE CONTROLS - Management Labor-Program-ABC | PPG
Operator Eval |  | 3 | 2019-04-26 | 2019-04-30 | 2877 | 2877 | 0
980GC-108320 | Run | 3 | 2019-04-26 | 2019-04-30 | 2877 | 2877 |  | layjd.Lay Joe D | PPG
Hydraulic Development |  | 83 | 2019-04-17 | 2019-08-13 | 38844 | 38844 | 20
980GC-108380 | Plan | 10 | 2019-04-17 | 2019-04-30 | 4360 | 4360 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
980GC-108390 | Setup | 5 | 2019-05-01 | 2019-05-07 | 7015 | 7015 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-108400 | Instrument | 3 | 2019-05-08 | 2019-05-10 | 4099 | 4099 | 20 | Instrument Tech.Instrumentation Setup Tech | PPG
980GC-108370 | Run | 5 | 2019-05-13 | 2019-05-17 | 9010 | 9010 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-108410 | Teardown | 2 | 2019-05-20 | 2019-05-21 | 1280 | 1280 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-108420 | TIC Report | 60 | 2019-05-20 | 2019-08-13 | 13080 | 13080 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
PD Phase |  | 220 | 2019-12-30 | 2020-11-10 | 457454.74 | 457454.74 | 530
CQL 980GC LRC PD#1 (SN) |  | 227 | 2019-12-30 | 2020-11-10 | 158918.27 | 158918.27 | 311
Machine Checkout STP-64 |  | 24 | 2019-12-30 | 2020-01-30 | 10073 | 10073 | 0
980GC-109270 | Planning | 10 | 2019-12-30 | 2020-01-10 | 700 | 700 |  | lus1.Lu Shuliang | QPG
980GC-109230 | Machine Preparation | 2 | 13-Jan-20* | 2020-01-14 | 960 | 960 |  | lus1.Lu Shuliang | QPG
980GC-109240 | Run | 10 | 2020-01-15 | 2020-01-28 | 7968 | 7968 |  | lus1.Lu Shuliang | QPG
980GC-109250 | Preliminary Report | 1 | 2020-01-29 | 2020-01-29 | 175 | 175 |  | lus1.Lu Shuliang | QPG
980GC-109260 | Teardown | 1 | 2020-01-30 | 2020-01-30 | 270 | 270 |  | lus1.Lu Shuliang | QPG
Software Checkout #1 |  | 40 | 2020-01-17 | 2020-03-12 | 6069 | 6069 | 0
980GC-109305 | Planning | 10 | 2020-01-17 | 2020-01-30 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109295 | Run | 10 | 2020-01-31 | 2020-02-13 | 5019 | 5019 |  | lus1.Lu Shuliang | QPG
980GC-109300 | Report - Data Archiving no TIC | 20 | 2020-02-14 | 2020-03-12 | 700 | 700 |  | lus1.Lu Shuliang | QPG
Sound Testing |  | 34 | 2020-01-31 | 2020-03-18 | 3753 | 3753 | 0
980GC-109275 | Plan | 10 | 2020-01-31 | 2020-02-13 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109280 | Setup | 1 | 2020-02-14 | 2020-02-14 | 340 | 340 |  | lus1.Lu Shuliang | QPG
980GC-109285 | Run | 3 | 2020-02-17 | 2020-02-19 | 2271 | 2271 |  | lus1.Lu Shuliang | QPG
980GC-109290 | Report | 20 | 2020-02-20 | 2020-03-18 | 792 | 792 |  | LinHW.Lin Hongwei | QPG
L5 Tuning and Performance Check |  | 7 | 2020-02-13 | 2020-02-21 | 1279.11 | 1279.11 | 0
980GC-110590 | Planning | 5 | 2020-02-13 | 2020-02-19 | 280 | 280 |  | lus1.Lu Shuliang | QPG
980GC-110600 | Run | 2 | 2020-02-20 | 2020-02-21 | 999.11 | 999.11 |  | lus1.Lu Shuliang | QPG
Operator Eval #1 |  | 3 | 2020-02-24 | 2020-02-26 | 1571.4 | 1571.4 | 0
980GC-109600 | Run | 3 | 2020-02-24 | 2020-02-26 | 1571.4 | 1571.4 |  | lus1.Lu Shuliang | QPG
Hydraulic Test |  | 62 | 2020-02-13 | 2020-05-08 | 11747.77 | 11747.77 | 32
980GC-109630 | Planning | 10 | 2020-02-13 | 2020-02-26 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-109605 | Machine Preparation | 5 | 2020-02-27 | 2020-03-04 | 3100 | 3100 |  | lus1.Lu Shuliang | QPG
980GC-109635 | Setup/Instrument | 5 | 2020-03-05 | 2020-03-11 | 3100 | 3100 | 32 | lus1.Lu Shuliang | QPG
980GC-109610 | Run | 5 | 2020-03-12 | 2020-03-18 | 2497.77 | 2497.77 |  | lus1.Lu Shuliang | QPG
980GC-109615 | Preliminary Report | 4 | 2020-03-19 | 2020-03-24 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-109620 | Teardown | 3 | 2020-03-25 | 2020-03-27 | 1230 | 1230 |  | lus1.Lu Shuliang | QPG
980GC-109625 | Report - Data Archiving no TIC | 30 | 2020-03-30 | 2020-05-08 | 700 | 700 |  | lus1.Lu Shuliang | QPG
Software Checkout #2 |  | 35 | 2020-03-16 | 2020-05-01 | 3559.5 | 3559.5 | 0
980GC-109320 | Planning | 10 | 2020-03-16 | 2020-03-27 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109310 | Run | 5 | 2020-03-30 | 2020-04-03 | 2509.5 | 2509.5 |  | lus1.Lu Shuliang | QPG
980GC-109315 | Report - Data Archiving no TIC | 20 | 2020-04-06 | 2020-05-01 | 700 | 700 |  | lus1.Lu Shuliang | QPG
Operator Eval #2 |  | 3 | 2020-04-06 | 2020-04-08 | 1571.4 | 1571.4 | 0
980GC-109675 | Run | 3 | 2020-04-06 | 2020-04-08 | 1571.4 | 1571.4 |  | lus1.Lu Shuliang | QPG
LRC Water Flow Test |  | 44 | 2020-03-26 | 2020-05-26 | 20523.4 | 20523.4 | 0
980GC-110510 | Planning | 10 | 2020-03-26 | 2020-04-08 | 9880 | 9880 |  | lus1.Lu Shuliang | QPG
980GC-110530 | Machine Preparation | 1 | 2020-04-09 | 2020-04-09 | 1408 | 1408 |  | lus1.Lu Shuliang | QPG
980GC-110490 | Run | 3 | 2020-04-10 | 2020-04-14 | 4355.4 | 4355.4 |  | lus1.Lu Shuliang | QPG
980GC-110500 | Report - Data Archiving no TIC | 30 | 2020-04-15 | 2020-05-26 | 4880 | 4880 |  | lus1.Lu Shuliang | QPG
LRC Cooling Test |  | 65 | 2020-04-01 | 2020-06-30 | 12108 | 12108 | 15
980GC-110470 | Planning | 10 | 2020-04-01 | 2020-04-14 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-110420 | Machine Preparation | 5 | 2020-04-15 | 2020-04-21 | 1350 | 1350 |  | lus1.Lu Shuliang | QPG
980GC-110480 | Setup/Instrument | 5 | 2020-04-22 | 2020-04-28 | 3100 | 3100 | 15 | lus1.Lu Shuliang | QPG
980GC-110430 | Run | 10 | 2020-04-29 | 2020-05-12 | 5238 | 5238 |  | lus1.Lu Shuliang | QPG
980GC-110440 | Preliminary Report | 2 | 2020-05-13 | 2020-05-14 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-110450 | Teardown | 3 | 2020-05-15 | 2020-05-19 | 810 | 810 |  | lus1.Lu Shuliang | QPG
980GC-110460 | Report - Data Archiving no TIC | 30 | 2020-05-20 | 2020-06-30 | 700 | 700 |  | lus1.Lu Shuliang | QPG
LRC STP 401 Engine Audit |  | 4 | 2020-05-20 | 2020-05-25 | 1587.6 | 1587.6 | 0
980GC-110570 | Machine Preparation | 2 | 2020-05-20 | 2020-05-21 | 540 | 540 |  | lus1.Lu Shuliang | QPG
980GC-110580 | Run | 2 | 2020-05-22 | 2020-05-25 | 1047.6 | 1047.6 |  | lus1.Lu Shuliang | QPG
OMSA Hood |  | 160 | 2020-02-04 | 2020-09-14 | 39724 | 39724 | 200
980GC-109530 | Plan | 80 | 2020-02-04 | 2020-05-25 | 14250 | 14250 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | QPG
980GC-109545 | Setup/Instument | 10 | 2020-05-26 | 2020-06-08 | 4800 | 4800 | 200 | lus1.Lu Shuliang | QPG
980GC-109540 | Run | 7 | 2020-05-29 | 2020-06-08 | 11144 | 11144 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | QPG
980GC-109690 | Teardown | 3 | 2020-06-09 | 2020-06-11 | 810 | 810 |  | lus1.Lu Shuliang | QPG
980GC-109550 | Analyze | 10 | 2020-06-09 | 2020-06-22 | 4360 | 4360 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-109535 | TIC Report | 60 | 2020-06-23 | 2020-09-14 | 4360 | 4360 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
Software Checkout #3 |  | 35 | 2020-05-29 | 2020-07-16 | 3559.5 | 3559.5 | 0
980GC-109570 | Planning | 10 | 2020-05-29 | 2020-06-11 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109560 | Run | 5 | 2020-06-12 | 2020-06-18 | 2509.5 | 2509.5 |  | lus1.Lu Shuliang | QPG
980GC-109565 | Report - Data Archiving no TIC | 20 | 2020-06-19 | 2020-07-16 | 700 | 700 |  | lus1.Lu Shuliang | QPG
ISO 5010 |  | 81 | 2020-06-05 | 2020-09-25 | 11028 | 11028 | 32
980GC-109210 | Planning | 10 | 2020-06-05 | 2020-06-18 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-109160 | Machine Preparation | 3 | 2020-06-19 | 2020-06-23 | 1440 | 1440 |  | lus1.Lu Shuliang | QPG
980GC-109220 | Setup/Instrument | 3 | 2020-06-24 | 2020-06-26 | 1230 | 1230 | 32 | lus1.Lu Shuliang | QPG
980GC-109170 | Run | 10 | 2020-06-29 | 2020-07-10 | 5238 | 5238 |  | lus1.Lu Shuliang | QPG
980GC-109180 | Preliminary Report | 2 | 2020-07-13 | 2020-07-14 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109190 | Teardown | 3 | 2020-07-15 | 2020-07-17 | 810 | 810 |  | lus1.Lu Shuliang | QPG
980GC-109200 | TiC Report | 50 | 2020-07-20 | 2020-09-25 | 1400 | 1400 |  | lus1.Lu Shuliang | QPG
ISO 3450 Brake Cert STP24 |  | 76 | 2020-07-06 | 2020-10-19 | 8452.8 | 8452.8 | 32
980GC-109140 | Planning | 10 | 2020-07-06 | 2020-07-17 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-109090 | Machine Preparation | 2 | 2020-07-20 | 2020-07-21 | 960 | 960 |  | lus1.Lu Shuliang | QPG
980GC-109150 | Setup/Instrument | 3 | 2020-07-22 | 2020-07-24 | 1230 | 1230 | 32 | lus1.Lu Shuliang | QPG
980GC-109100 | Run | 6 | 2020-07-27 | 2020-08-03 | 3142.8 | 3142.8 |  | lus1.Lu Shuliang | QPG
980GC-109110 | Preliminary Report | 2 | 2020-08-04 | 2020-08-05 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109120 | Teardown | 3 | 2020-08-06 | 2020-08-10 | 810 | 810 |  | lus1.Lu Shuliang | QPG
980GC-109130 | TIC Report | 50 | 2020-08-11 | 2020-10-19 | 1400 | 1400 |  | lus1.Lu Shuliang | QPG
980GC Endurance 0-500 hrs |  | 86 | 2020-07-14 | 2020-11-10 | 22310.8 | 22310.8 | 0
980GC-109585 | Plan | 20 | 2020-07-14 | 2020-08-10 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109580 | Endurance (0-250hr) | 32 | 2020-08-11 | 2020-09-23 | 10640.4 | 10640.4 |  | lus1.Lu Shuliang | QPG
980GC-109595 | 250hr Service/Inspect | 1 | 2020-09-24 | 2020-09-24 | 340 | 340 |  | lus1.Lu Shuliang | QPG
980GC-109590 | Endurance (251-500hr) | 32 | 2020-09-25 | 2020-11-09 | 10640.4 | 10640.4 |  | lus1.Lu Shuliang | QPG
980GC-109575 | 500hr Service/Inspect/Update | 1 | 2020-11-10 | 2020-11-10 | 340 | 340 |  | lus1.Lu Shuliang | QPG
PPG 980GC HRC PD#2 (SN) |  | 193 | 2020-01-03 | 2020-10-05 | 298536.47 | 298536.47 | 219
LOE |  | 182 | 2020-01-21 | 2020-10-05 | 0 | 0 | 0
966GC-1090 | Start Testing 980GC HRC PD #2 | 0 | 2020-01-21 |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-1100 | LOE: 980GC HRC PD #2 | 122 | 2020-01-21 | 2020-07-10 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-1110 | Testing Complete 980GC HRC PD #2 | 0 |  | 2020-07-10 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-1120 | Reports Complete 980GC HRC PD #2 | 0 |  | 2020-10-05 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
Machine Checkout STP-64 |  | 8 | 2020-01-13 | 2020-01-23 | 5371.5 | 5371.5 | 0
966GC-1210 | Plan | 5 | 2020-01-13 | 2020-01-17 | 817.5 | 817.5 |  | layjd.Lay Joe D | PPG
966GC-1230 | Run | 3 | 21-Jan-20* | 2020-01-23 | 4554 | 4554 |  | layjd.Lay Joe D | PPG
Operator Eval |  | 3 | 2020-01-24 | 2020-01-28 | 3204 | 3204 | 0
980GC-106400 | Run | 3 | 2020-01-24 | 2020-01-28 | 3204 | 3204 |  | layjd.Lay Joe D | PPG
L5 Tuning and Performance Check #1 |  | 12 | 2020-01-22 | 2020-02-06 | 4591 | 4591 | 0
980GC-110190 | Plan | 5 | 2020-01-22 | 2020-01-28 | 545 | 545 |  | layjd.Lay Joe D | PPG
980GC-110200 | Run | 7 | 2020-01-29 | 2020-02-06 | 4046 | 4046 |  | layjd.Lay Joe D | PPG
Rimpull and Response Test |  | 56 | 2020-01-03 | 2020-03-23 | 33683 | 33683 | 24
980GC-110240 | Plan | 20 | 2020-01-03 | 2020-01-31 | 4360 | 4360 |  | layjd.Lay Joe D | PPG
980GC-110290 | SGL Strain Gage Lab - Instrument Parts | 4 | 2020-02-03 | 2020-02-06 | 3924 | 3924 |  | layjd.Lay Joe D | PPG
980GC-110250 | Setup | 2 | 2020-02-07 | 2020-02-10 | 2996 | 2996 |  | layjd.Lay Joe D | PPG
980GC-110260 | Instrument | 2 | 2020-02-11 | 2020-02-12 | 4352 | 4352 | 24 | layjd.Lay Joe D | PPG
980GC-110230 | Run | 7 | 2020-02-13 | 2020-02-21 | 7833 | 7833 |  | layjd.Lay Joe D | PPG
980GC-110270 | Teardown | 1 | 2020-02-24 | 2020-02-24 | 1498 | 1498 |  | layjd.Lay Joe D | PPG
980GC-110280 | Analyze | 5 | 2020-02-25 | 2020-03-02 | 2180 | 2180 |  | layjd.Lay Joe D | PPG
980GC-110300 | Report | 15 | 2020-03-03 | 2020-03-23 | 6540 | 6540 |  | layjd.Lay Joe D | PPG
SW Checkout |  | 5 | 2020-02-25 | 2020-03-02 | 2180 | 2180 | 0
980GC-110180 | Run | 5 | 2020-02-25 | 2020-03-02 | 2180 | 2180 |  | egantr.Egan Thomas R | PPG
XMSN Tuning |  | 10 | 2020-03-03 | 2020-03-16 | 8700 | 8700 | 24
980GC-108710 | Setup | 2 | 2020-03-03 | 2020-03-04 | 2192 | 2192 |  | 01-97209-400.RES400 HAULING & OEM XSMN DEVELOPMENT - Management Labor-Program | PPG
980GC-108720 | Instrument | 2 | 2020-03-05 | 2020-03-06 | 4362 | 4362 | 24 | 01-97209-400.RES400 HAULING & OEM XSMN DEVELOPMENT - Management Labor-Program | PPG
980GC-108700 | Run | 5 | 2020-03-09 | 2020-03-13 | 1050 | 1050 |  | 01-97209-400.RES400 HAULING & OEM XSMN DEVELOPMENT - Management Labor-Program | PPG
980GC-108730 | Teardown | 1 | 2020-03-16 | 2020-03-16 | 1096 | 1096 |  | 01-97209-400.RES400 HAULING & OEM XSMN DEVELOPMENT - Management Labor-Program | PPG
L5 Tuning with Operator |  | 8 | 2020-03-10 | 2020-03-19 | 3959 | 3959 | 0
980GC-110210 | Plan | 5 | 2020-03-10 | 2020-03-16 | 545 | 545 |  | layjd.Lay Joe D | PPG
980GC-110220 | Run | 3 | 2020-03-17 | 2020-03-19 | 3414 | 3414 |  | layjd.Lay Joe D | PPG
Sound Testing |  | 32 | 2020-03-20 | 2020-05-04 | 10068 | 10068 | 0
980GC-108580 | Run | 2 | 2020-03-20 | 2020-03-23 | 8212 | 8212 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG.Sound.Bld
980GC-108590 | Report | 20 | 2020-04-07 | 2020-05-04 | 1856 | 1856 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
EMC Testing |  | 81 | 2020-01-13 | 2020-05-05 | 29724 | 29724 | 0
980GC-110310 | Plan | 50 | 2020-01-13 | 2020-03-23 | 5770 | 5770 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
980GC-110320 | Setup | 1 | 2020-03-24 | 2020-03-24 | 1076 | 1076 |  | layjd.Lay Joe D | PPG
980GC-110330 | Run | 5 | 2020-03-25 | 2020-03-31 | 13160 | 13160 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
980GC-110340 | Teardown | 1 | 2020-04-01 | 2020-04-01 | 1076 | 1076 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-110360 | Analysis | 4 | 2020-04-02 | 2020-04-07 | 3744 | 3744 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
980GC-110350 | Report | 20 | 2020-04-08 | 2020-05-05 | 4898 | 4898 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
STP-153 (Airflow Testing) |  | 20 | 2020-03-19 | 2020-04-15 | 10969 | 10969 | 0
980GC-108450 | Plan | 10 | 2020-03-19 | 2020-04-01 | 1160 | 1160 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108460 | Setup/Run | 4 | 2020-04-02 | 2020-04-07 | 8256 | 8256 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108600 | Teardown | 1 | 2020-04-08 | 2020-04-08 | 625 | 625 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108470 | Report (Class 1) | 6 | 2020-04-08 | 2020-04-15 | 928 | 928 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
STP-155 (Water Flow Test) |  | 20 | 2020-03-26 | 2020-04-22 | 8945 | 8945 | 0
980GC-108480 | Plan | 10 | 2020-03-26 | 2020-04-08 | 1160 | 1160 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108490 | Setup/Run | 4 | 2020-04-09 | 2020-04-14 | 6232 | 6232 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108610 | Teardown | 1 | 2020-04-15 | 2020-04-15 | 625 | 625 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108500 | Report (Class 1) | 6 | 2020-04-15 | 2020-04-22 | 928 | 928 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
HRC STP-152 (Ambient Capability) & STP-154 (IMT) w/ UHT |  | 110 | 2020-01-23 | 2020-06-25 | 92051.8 | 92051.8 | 112
980GC-108620 | Plan | 60 | 2020-01-23 | 2020-04-15 | 3375 | 3375 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108630 | Setup | 6 | 2020-04-16 | 2020-04-23 | 10716 | 10716 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108680 | Instrument | 6 | 2020-04-24 | 2020-05-01 | 25980 | 25980 | 112 | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108670 | Prep Field - MDC | 3 | 2020-04-29 | 2020-05-01 | 2029 | 2029 |  | Field_Prep1.Field Prep 1 | PPG
980GC-108640 | Run | 8 | 2020-05-04 | 2020-05-13 | 35468 | 35468 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108650 | Teardown | 2 | 2020-05-14 | 2020-05-15 | 2862 | 2862 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
980GC-108660 | Report (Class 3) | 30 | 2020-05-14 | 2020-06-25 | 11621.8 | 11621.8 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
STP 401 HRC Engine Audit |  | 37 | 2020-05-04 | 2020-06-24 | 19571 | 19571 | 32
980GC-110630 | Plan | 10 | 2020-05-04 | 2020-05-15 | 2180 | 2180 |  | layjd.Lay Joe D | PPG
980GC-110610 | Setup | 2 | 2020-05-18 | 2020-05-19 | 2152 | 2152 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-110640 | Instrument | 3 | 2020-05-20 | 2020-05-22 | 6141 | 6141 | 32 | Instrument Tech.Instrumentation Setup Tech | PPG
980GC-110650 | Run | 2 | 2020-05-26 | 2020-05-27 | 3444 | 3444 |  | 01-88180-242.TSD881HRY - SEC80 RES242 PPG TEST OPERATIONS - Vehicle Operator-ABC | PPG
980GC-110660 | Teardown | 1 | 2020-05-28 | 2020-05-28 | 1294 | 1294 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-110670 | Report | 20 | 2020-05-28 | 2020-06-24 | 4360 | 4360 |  | layjd.Lay Joe D | PPG
ISO 5010 |  | 28 | 2020-05-07 | 2020-06-16 | 26054.67 | 26054.67 | 16
980GC-110070 | Plan | 15 | 2020-05-07 | 2020-05-28 | 4905 | 4905 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
980GC-110080 | Setup | 2 | 2020-05-29 | 2020-06-01 | 4958 | 4958 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
980GC-110090 | Instrument | 3 | 2020-06-02 | 2020-06-04 | 3078 | 3078 | 16 | layjd.Lay Joe D | PPG
980GC-110060 | Run | 5 | 2020-06-05 | 2020-06-11 | 10511.67 | 10511.67 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
980GC-110100 | Teardown | 1 | 2020-06-12 | 2020-06-12 | 858 | 858 |  | layjd.Lay Joe D | PPG
980GC-110110 | Analyze | 2 | 2020-06-15 | 2020-06-16 | 1744 | 1744 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
ISO 3450 Brake Cert STP24 |  | 89 | 2020-06-01 | 2020-10-05 | 39464.5 | 39464.5 | 11
980GC-110150 | Plan | 10 | 2020-06-01 | 2020-06-12 | 2180 | 2180 |  | layjd.Lay Joe D | PPG
980GC-110120 | Setup | 4 | 2020-06-15 | 2020-06-18 | 4712 | 4712 |  | layjd.Lay Joe D | PPG
980GC-110130 | Instrument | 1 | 2020-06-19 | 2020-06-19 | 1992.5 | 1992.5 | 11 | layjd.Lay Joe D | PPG
980GC-110170 | Run | 12 | 2020-06-22 | 2020-07-08 | 24504 | 24504 |  | layjd.Lay Joe D | PPG
980GC-110140 | Teardown | 2 | 2020-07-09 | 2020-07-10 | 1716 | 1716 |  | layjd.Lay Joe D | PPG
980GC-110160 | TIC Report | 60 | 2020-07-13 | 2020-10-05 | 4360 | 4360 |  | layjd.Lay Joe D | PPG
Pilot Phase |  | 315 | 2020-03-23 | 2021-06-24 | 331063.19 | 331063.19 | 203
PPG 980GC HRC Pilot #1 (SN) |  | 176 | 2020-10-07 | 2021-06-24 | 200557.67 | 200557.67 | 75
LOE |  | 110 | 2020-12-01 | 2021-05-13 | 0 | 0 | 0
980GC-110380 | Start Testing 980GC HRC Pilot #1 | 0 | 2020-12-01 |  | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-110390 | LOE: 980GC HRC Pilot #1 | 86 | 2020-12-01 | 2021-04-09 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-110400 | Testing Complete 980GC HRC Pilot #1 | 0 |  | 2021-04-09 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
980GC-110410 | Reports Complete 980GC HRC Pilot #1 | 0 |  | 2021-05-13 | 0 | 0 |  | mccalad.McCallister Andy D | PPG
Machine Checkout STP-64 |  | 8 | 2020-11-20 | 2020-12-03 | 5371.5 | 5371.5 | 0
980GC-109700 | Plan | 5 | 2020-11-20 | 2020-11-30 | 817.5 | 817.5 |  | layjd.Lay Joe D | PPG
980GC-109710 | Run | 3 | 01-Dec-20* | 2020-12-03 | 4554 | 4554 |  | layjd.Lay Joe D | PPG
SW Checkout #1 |  | 10 | 2020-12-04 | 2020-12-17 | 4360 | 4360 | 0
980GC-109800 | Run | 10 | 2020-12-04 | 2020-12-17 | 4360 | 4360 |  | egantr.Egan Thomas R | PPG
Sound Testing |  | 32 | 2020-12-18 | 2021-02-11 | 10068 | 10068 | 0
980GC-109720 | Run | 2 | 2020-12-18 | 2020-12-21 | 8212 | 8212 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG.Sound.Bld
980GC-109730 | Report | 20 | 2021-01-14 | 2021-02-11 | 1856 | 1856 |  | 01-55700-400.TSD557MGT - SEC00 RES400 GLOBAL SOUND SOLUTIONS-NA - Management Labor-Program | PPG
Operator Eval #1 |  | 3 | 2020-12-22 | 2021-01-04 | 3204 | 3204 | 0
980GC-109950 | Run | 3 | 2020-12-22 | 2021-01-04 | 3204 | 3204 |  | layjd.Lay Joe D | PPG
SW Checkout #2 |  | 5 | 2021-01-05 | 2021-01-11 | 2180 | 2180 | 0
980GC-109810 | Run | 5 | 2021-01-05 | 2021-01-11 | 2180 | 2180 |  | egantr.Egan Thomas R | PPG
Operator Eval #2 |  | 3 | 2021-01-12 | 2021-01-14 | 3204 | 3204 | 0
980GC-109960 | Run | 3 | 2021-01-12 | 2021-01-14 | 3204 | 3204 |  | layjd.Lay Joe D | PPG
OMSA Light Fabs Hood |  | 141 | 2020-10-07 | 2021-05-05 | 68319.33 | 68319.33 | 48
980GC-109970 | Planning & Procurement | 60 | 2020-10-07 | 2021-01-11 | 4723.33 | 4723.33 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-109980 | SGL Strain Gage Lab - Instrument Parts | 3 | 2021-01-12 | 2021-01-14 | 3161 | 3161 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110040 | Setup - Shop Support Work | 3 | 2021-01-15 | 2021-01-20 | 4972 | 4972 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-109990 | Instrument - Setup Bay | 3 | 2021-01-21 | 2021-01-25 | 9135 | 9135 | 48 | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110050 | Field Prep for OMSA | 2 | 2021-01-22 | 2021-01-25 | 16216 | 16216 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110000 | Run | 8 | 2021-01-26 | 2021-02-04 | 17264 | 17264 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110010 | Teardown | 1 | 2021-02-05 | 2021-02-05 | 1948 | 1948 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-110020 | Preliminary Analysis/Reporting | 3 | 2021-02-05 | 2021-02-09 | 2180 | 2180 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
980GC-110030 | TIC Report | 61 | 2021-02-10 | 2021-05-05 | 8720 | 8720 |  | 01-88109-400.TSD881MGT - SEC09 RES400 STRUCTURES Validation - Management Labor-Program | PPG
SW Checkout #3 |  | 5 | 2021-02-08 | 2021-02-12 | 2180 | 2180 | 0
980GC-109820 | Run & Checkout S13 | 5 | 2021-02-08 | 2021-02-12 | 2180 | 2180 |  | egantr.Egan Thomas R | PPG
ISO 5010 |  | 33 | 2021-01-25 | 2021-03-10 | 36566.33 | 36566.33 | 16
980GC-109840 | Plan | 15 | 2021-01-25 | 2021-02-12 | 4905 | 4905 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
980GC-109850 | Setup | 2 | 2021-02-15 | 2021-02-16 | 4958 | 4958 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
980GC-109860 | Instrument | 3 | 2021-02-17 | 2021-02-19 | 3078 | 3078 | 16 | layjd.Lay Joe D | PPG
980GC-109830 | Run | 10 | 2021-02-22 | 2021-03-05 | 21023.33 | 21023.33 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
980GC-109870 | Teardown | 1 | 2021-03-08 | 2021-03-08 | 858 | 858 |  | layjd.Lay Joe D | PPG
980GC-109880 | Analyze | 2 | 2021-03-09 | 2021-03-10 | 1744 | 1744 |  | 01-88103-400.TSD881MGT - SEC03 RES400 HYDRAULICS DEVELOPMENT - Management Labor-Program | PPG
ISO 3450 Brake Cert STP24 |  | 87 | 2021-02-23 | 2021-06-24 | 35380.5 | 35380.5 | 11
980GC-109920 | Plan | 10 | 2021-02-23 | 2021-03-08 | 2180 | 2180 |  | layjd.Lay Joe D | PPG
980GC-109890 | Setup | 4 | 2021-03-09 | 2021-03-12 | 4712 | 4712 |  | layjd.Lay Joe D | PPG
980GC-109900 | Instrument | 1 | 2021-03-15 | 2021-03-15 | 1992.5 | 1992.5 | 11 | layjd.Lay Joe D | PPG
980GC-109940 | Run | 10 | 2021-03-16 | 2021-03-29 | 20420 | 20420 |  | layjd.Lay Joe D | PPG
980GC-109910 | Teardown | 2 | 2021-03-30 | 2021-03-31 | 1716 | 1716 |  | layjd.Lay Joe D | PPG
980GC-109930 | TIC Report | 60 | 2021-04-01 | 2021-06-24 | 4360 | 4360 |  | layjd.Lay Joe D | PPG
EMC Testing |  | 81 | 2021-01-21 | 2021-05-13 | 29724 | 29724 | 0
980GC-108510 | Plan | 50 | 2021-01-21 | 2021-03-31 | 5770 | 5770 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
980GC-108520 | Setup | 1 | 2021-04-01 | 2021-04-01 | 1076 | 1076 |  | layjd.Lay Joe D | PPG
980GC-108530 | Run | 5 | 2021-04-02 | 2021-04-08 | 13160 | 13160 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
980GC-108540 | Teardown | 1 | 2021-04-09 | 2021-04-09 | 1076 | 1076 |  | 01-88108-241.TSD881HRY - SEC08 RES241 OPERATIONS & FACILITIES - Mechanic-ABC | PPG
980GC-108690 | Analysis | 4 | 2021-04-12 | 2021-04-15 | 3744 | 3744 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
980GC-108550 | Report | 20 | 2021-04-16 | 2021-05-13 | 4898 | 4898 |  | 01-75304-400.E&E753MGT - SEC04 RES400 ROBUST ELECT HARDWARE DESIGN - Management Labor-Program | PPG
CQL 980GC LRC Pilot #2 (SN) |  | 136 | 2020-03-23 | 2020-09-29 | 54366.25 | 54366.25 | 128
Machine Checkout STP-64 |  | 16 | 2020-03-23 | 2020-04-14 | 3121.88 | 3121.88 | 0
980GC-109000 | Planning | 10 | 2020-03-23 | 2020-04-03 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-108960 | Machine Preparation | 1 | 06-Apr-20* | 2020-04-06 | 480 | 480 |  | lus1.Lu Shuliang | QPG
980GC-108970 | Run | 3 | 2020-04-07 | 2020-04-10 | 1636.88 | 1636.88 |  | lus1.Lu Shuliang | QPG
980GC-108980 | Preliminary Report | 1 | 2020-04-10 | 2020-04-13 | 175 | 175 |  | lus1.Lu Shuliang | QPG
980GC-108990 | Teardown | 1 | 2020-04-13 | 2020-04-14 | 270 | 270 |  | lus1.Lu Shuliang | QPG
Software Checkout |  | 35 | 2020-03-31 | 2020-05-19 | 3559.5 | 3559.5 | 0
980GC-109355 | Planning | 10 | 2020-03-31 | 2020-04-14 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109345 | Run | 5 | 2020-04-14 | 2020-04-21 | 2509.5 | 2509.5 |  | lus1.Lu Shuliang | QPG
980GC-109350 | Report - Data Archiving no TIC | 20 | 2020-04-21 | 2020-05-19 | 700 | 700 |  | lus1.Lu Shuliang | QPG
ISO 5010 |  | 75 | 2020-04-07 | 2020-07-21 | 7885.2 | 7885.2 | 32
980GC-108940 | Planning | 10 | 2020-04-07 | 2020-04-21 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-108890 | Machine Preparation | 3 | 2020-04-21 | 2020-04-24 | 1440 | 1440 |  | lus1.Lu Shuliang | QPG
980GC-108950 | Setup/Instrument | 3 | 2020-04-24 | 2020-04-29 | 1230 | 1230 | 32 | lus1.Lu Shuliang | QPG
980GC-108900 | Run | 4 | 2020-04-29 | 2020-05-05 | 2095.2 | 2095.2 |  | lus1.Lu Shuliang | QPG
980GC-108910 | Preliminary Report | 2 | 2020-05-05 | 2020-05-07 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-108920 | Teardown | 3 | 2020-05-07 | 2020-05-12 | 810 | 810 |  | lus1.Lu Shuliang | QPG
980GC-108930 | TiC Report | 50 | 2020-05-12 | 2020-07-21 | 1400 | 1400 |  | lus1.Lu Shuliang | QPG
ISO 3450 Brake Cert STP24 |  | 76 | 2020-04-28 | 2020-08-12 | 8452.8 | 8452.8 | 32
980GC-108870 | Planning | 10 | 2020-04-28 | 2020-05-12 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-108820 | Machine Preparation | 2 | 2020-05-12 | 2020-05-14 | 960 | 960 |  | lus1.Lu Shuliang | QPG
980GC-108880 | Setup/Instrument | 3 | 2020-05-14 | 2020-05-19 | 1230 | 1230 | 32 | lus1.Lu Shuliang | QPG
980GC-108830 | Run | 6 | 2020-05-19 | 2020-05-27 | 3142.8 | 3142.8 |  | lus1.Lu Shuliang | QPG
980GC-108840 | Preliminary Report | 2 | 2020-05-27 | 2020-05-29 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-108850 | Teardown | 3 | 2020-05-29 | 2020-06-03 | 810 | 810 |  | lus1.Lu Shuliang | QPG
980GC-108860 | TIC Report | 50 | 2020-06-03 | 2020-08-12 | 1400 | 1400 |  | lus1.Lu Shuliang | QPG
EMC Testing |  | 62 | 2020-05-20 | 2020-08-14 | 15500 | 15500 | 32
980GC-108810 | Planning | 10 | 2020-05-20 | 2020-06-03 | 5060 | 5060 |  | lus1.Lu Shuliang | QPG
980GC-108800 | Machine Preparation | 5 | 2020-06-03 | 2020-06-10 | 1700 | 1700 |  | lus1.Lu Shuliang | QPG
980GC-108780 | Ship to EMC Location | 3 | 2020-06-10 | 2020-06-15 | 1710 | 1710 |  | lus1.Lu Shuliang | QPG
980GC-108770 | Setup | 2 | 2020-06-15 | 2020-06-17 | 560 | 560 | 32 | lus1.Lu Shuliang | Field
980GC-108750 | Run | 5 | 2020-06-17 | 2020-06-24 | 1400 | 1400 |  | lus1.Lu Shuliang | Field
980GC-108740 | Retest | 7 | 2020-06-24 | 2020-07-03 | 1960 | 1960 |  | lus1.Lu Shuliang | Field
980GC-108790 | Ship to CQL | 3 | 2020-07-03 | 2020-07-08 | 1710 | 1710 |  | lus1.Lu Shuliang | Field
980GC-108760 | TIC Report | 30 | 2020-07-03 | 2020-08-14 | 1400 | 1400 |  | lus1.Lu Shuliang | QPG
Hydraulic Signature Test |  | 69 | 2020-06-24 | 2020-09-29 | 15846.88 | 15846.88 | 32
980GC-109665 | Planning | 10 | 2020-06-24 | 2020-07-08 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-109640 | Machine Preparation | 10 | 2020-07-08 | 2020-07-22 | 6200 | 6200 |  | lus1.Lu Shuliang | QPG
980GC-109670 | Setup/Instrument | 5 | 2020-07-22 | 2020-07-29 | 3100 | 3100 | 32 | lus1.Lu Shuliang | QPG
980GC-109645 | Run | 7 | 2020-07-29 | 2020-08-07 | 3496.88 | 3496.88 |  | lus1.Lu Shuliang | QPG
980GC-109650 | Preliminary Report | 4 | 2020-08-07 | 2020-08-13 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-109655 | Teardown | 3 | 2020-08-13 | 2020-08-18 | 1230 | 1230 |  | lus1.Lu Shuliang | QPG
980GC-109660 | Report - Data Archiving no TIC | 30 | 2020-08-18 | 2020-09-29 | 700 | 700 |  | lus1.Lu Shuliang | QPG
CQL 980GC HRC Pilot #3 (SN) |  | 220 | 2020-03-23 | 2021-01-25 | 76139.27 | 76139.27 | 0
Machine Checkout STP-64 |  | 16 | 2020-03-23 | 2020-04-14 | 3121.88 | 3121.88 | 0
980GC-109380 | Planning | 10 | 2020-03-23 | 2020-04-03 | 560 | 560 |  | lus1.Lu Shuliang | QPG
980GC-109360 | Machine Preparation | 1 | 06-Apr-20* | 2020-04-06 | 480 | 480 |  | lus1.Lu Shuliang | QPG
980GC-109365 | Run | 3 | 2020-04-07 | 2020-04-10 | 1636.88 | 1636.88 |  | lus1.Lu Shuliang | QPG
980GC-109370 | Preliminary Report | 1 | 2020-04-10 | 2020-04-13 | 175 | 175 |  | lus1.Lu Shuliang | QPG
980GC-109375 | Teardown | 1 | 2020-04-13 | 2020-04-14 | 270 | 270 |  | lus1.Lu Shuliang | QPG
Sound Testing |  | 36 | 2020-03-31 | 2020-05-20 | 6785 | 6785 | 0
980GC-109385 | Plan | 10 | 2020-03-31 | 2020-04-14 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109390 | Setup | 1 | 2020-04-14 | 2020-04-15 | 340 | 340 |  | lus1.Lu Shuliang | QPG
980GC-109395 | Run | 5 | 2020-04-15 | 2020-04-22 | 3785 | 3785 |  | LinHW.Lin Hongwei | QPG
980GC-109400 | Report | 20 | 2020-04-22 | 2020-05-20 | 2310 | 2310 |  | LinHW.Lin Hongwei | QPG
980GC Endurance 0-500 hrs |  | 86 | 2020-03-25 | 2020-07-23 | 22310.8 | 22310.8 | 0
980GC-109415 | Plan | 20 | 2020-03-25 | 2020-04-22 | 350 | 350 |  | lus1.Lu Shuliang | QPG
980GC-109410 | Endurance (0-250hr) | 32 | 2020-04-22 | 2020-06-05 | 10640.4 | 10640.4 |  | lus1.Lu Shuliang | QPG
980GC-109425 | 250hr Service/Inspect | 1 | 2020-06-05 | 2020-06-08 | 340 | 340 |  | lus1.Lu Shuliang | QPG
980GC-109420 | Endurance (251-500hr) | 32 | 2020-06-08 | 2020-07-22 | 10640.4 | 10640.4 |  | lus1.Lu Shuliang | QPG
980GC-109405 | 500hr Service/Inspect/Update | 1 | 2020-07-22 | 2020-07-23 | 340 | 340 |  | lus1.Lu Shuliang | QPG
980GC Endurance 501-1000 hrs |  | 66 | 2020-07-23 | 2020-10-23 | 21960.8 | 21960.8 | 0
980GC-109435 | Endurance (501-750hr) | 32 | 2020-07-23 | 2020-09-07 | 10640.4 | 10640.4 |  | lus1.Lu Shuliang | QPG
980GC-109445 | 750hr Service/Inspect | 1 | 2020-09-07 | 2020-09-08 | 340 | 340 |  | lus1.Lu Shuliang | QPG
980GC-109440 | Endurance (751-1000hr) | 32 | 2020-09-08 | 2020-10-22 | 10640.4 | 10640.4 |  | lus1.Lu Shuliang | QPG
980GC-109430 | 1000hr Service/Inspect/Update | 1 | 2020-10-22 | 2020-10-23 | 340 | 340 |  | lus1.Lu Shuliang | QPG
980GC Endurance 1001-1500 hrs |  | 66 | 2020-10-23 | 2021-01-25 | 21960.8 | 21960.8 | 0
980GC-109455 | Endurance (1001-1250hr) | 32 | 2020-10-23 | 2020-12-08 | 10640.4 | 10640.4 |  | lus1.Lu Shuliang | QPG
980GC-109465 | 1250hr Service/Inspect | 1 | 2020-12-08 | 2020-12-09 | 340 | 340 |  | lus1.Lu Shuliang | QPG
980GC-109460 | Endurance (1251-1500hr) | 32 | 2020-12-09 | 2021-01-22 | 10640.4 | 10640.4 |  | lus1.Lu Shuliang | QPG
980GC-109450 | 1500hr Service/Inspect/Update | 1 | 2021-01-22 | 2021-01-25 | 340 | 340 |  | lus1.Lu Shuliang | QPG