## Sheet1
| Activity Name | Start | Finish
| Key Project Milestones | 2020-03-03 | 2022-03-05
GW | Quality Gate 3 | 2020-03-03 | 2020-03-05
GW | GW 3 | 2020-04-22 | 2020-04-23
DF | Pilot Design Freeze | 2020-07-12 | 2020-07-13
GW | Machine Ready for Field (Regs) | 2020-08-14 | 2020-08-15
DF | Pilot EDS Freeze | 2020-09-03 | 2020-09-05
GW | GW 4 | 2020-09-18 | 2020-09-19
Iron | Stg V Hood Iron arrives at PPG | 2020-09-28 | 2020-09-30
Iron | Ship DL Axle Arrives China Supplier | 2020-10-15 | 2020-10-17
GW | GW 5 | 2020-11-14 | 2020-11-16
DF | Production DF | 2021-10-01 | 2021-10-03
Iron | LPT (Axle) Design Freeze | 2021-10-15 | 2021-10-17
GW | GW 5.5 | 2021-10-20 | 2021-10-21
DF | Production EDS Freeze | 2021-12-01 | 2021-12-03
GW | GW 6 | 2022-03-02 | 2022-03-05
| Key Validation reviews | 2020-03-03 | 2020-11-02
VR | Validation Review 3 | 2020-03-03 | 2020-03-05
VR | Validation Review 4 | 2020-08-15 | 2020-08-15
VR | Validation Review 5 | 2020-11-02 | 2020-11-02
| Software Milestones | 2020-01-20 | 2021-01-27
SW | V01 SW Content Freeze | 2020-01-20 | 2020-01-21
SW | Receive V01 SW | 2020-03-16 | 2020-03-17
SW | V02 SW Content Freeze | 2020-06-23 | 2020-06-24
SW | Receive V02 SW | 2020-08-10 | 2020-08-11
SW | V03 SW Content Freeze | 2020-09-23 | 2020-09-24
SW | Receive V03 SW | 2020-11-11 | 2020-11-12
SW | V04 SW Content Freeze | 2020-12-15 | 2020-12-16
SW | Receive V04 SW (Pilot) | 2021-01-26 | 2021-01-27
| TIC Report Milestones | 2020-03-30 | 2021-10-05
Pilot | SYC Report-Pilot | 2020-03-30 | 2020-03-31
Pilot | ISO 3450 Brake Feasibility (Pilot) | 2020-07-03 | 2020-07-04
Pilot | EMC-Pilot- Pilot | 2020-08-13 | 2020-08-14
Pilot | ISO 9533 Horn, Back-up Alarm EN474 HAWB- Pilot | 2020-08-16 | 2020-08-17
Pilot | ISO 5010 Steering Feasibility (Pilot) | 2020-08-24 | 2020-08-25
Production | ISO 3450 Brake CERT | 2021-04-25 | 2021-04-27
Production | ISO 5010 Steering CERT | 2021-05-16 | 2021-05-17
Production | ISO 10570-Articulation Lock CERT | 2021-05-25 | 2021-05-26
Production | ISO 9533 Horn, Back-up Alarm HAWB CERT | 2021-08-22 | 2021-08-23
Production | Stg V EMC CERT | 2021-10-04 | 2021-10-05
| Tech Center ShakeTable | 2019-11-20 | 2020-12-13
Shake Table | Hood arrives at Tech Center, Peoria (Version 1) | 2019-11-20 | 2019-12-15
Shake Table | Stage V Shake Table # 1 (Version 1) | 2020-01-06 | 2020-02-28
Shake Table | Shake Table set-up (Version 2) | 2020-08-10 | 2020-09-04
Shake Table | Static Runs | 2020-09-05 | 2020-09-08
Shake Table | OMSA Drive File (Post Machine OMSA) (Version 2 hood) | 2020-09-20 | 2020-09-21
Shake Table | Set-up, Shakeout and Dynamic Runs | 2020-09-24 | 2020-10-18
Shake Table | Durability | 2020-10-19 | 2020-11-22
Shake Table | Teardown & Preliminary Report | 2020-11-23 | 2020-12-13
| Tech Center G LPT Axle | 2020-05-15 | 2021-03-01
Axle | Test Cycle Dev | 2020-05-15 | 2020-07-30
Axle | Lab set-up and Debug | 2020-08-13 | 2020-10-29
Axle | 0-500 hrs+ Inspection | 2020-11-02 | 2021-01-14
Axle | 501-1000 hrs + Inspection | 2021-01-15 | 2021-03-01
| 966GC T3 TB #3 (SGW00208) | 2020-05-11 | 2021-07-24
Tech | CPM + Collision Avoidance | 2020-05-11 | 2020-09-08
Machine Update | Machine Update | 2020-10-16 | 2020-10-21
Structures | Limited Slip Differential Driveline Signature- Prototype Iron | 2020-10-22 | 2020-11-23
Holiday | US Thanksgiving | 2020-11-24 | 2020-11-30
Structures | Driveline Signature-cont'd | 2020-12-01 | 2020-12-13
Endurance | 100 hr Endurance ( With Prototype LSD iron) | 2020-12-14 | 2020-12-22
Machine Build | Machine Update for UPT and LPT LCP Parts | 2021-02-20 | 2021-03-04
Machine Check | Machine Checkout STP-64/Opr Eval | 2021-03-07 | 2021-03-11
Endurance | Endurance 0-250 hrs+ Service/Inspect | 2021-03-12 | 2021-03-26
Endurance | Endurance 251-500 hrs+ Service/Inspect | 2021-03-27 | 2021-04-10
Endurance | Endurance 501-750 hrs+ Service/Inspect | 2021-04-11 | 2021-04-25
Endurance | Endurance 751-1000 hrs+ Service/Inspect | 2021-04-26 | 2021-05-10
Endurance | Endurance 1001-1250 hrs+ Service/Inspect | 2021-05-11 | 2021-05-25
Endurance | Endurance 1251-1500 hrs+ Service/Inspect | 2021-05-26 | 2021-06-09
Endurance | Endurance 1501-1750 hrs+ Service/Inspect | 2021-06-10 | 2021-06-24
Endurance | Endurance 1750-2000 hrs+ Service/Inspect | 2021-06-25 | 2021-07-09
Inspection | Full Inspection | 2021-07-10 | 2021-07-24
| 966GC T3 TB #4 (SGW00203) | 2020-02-05 | 2020-06-02
Safety | SYC Type Certification- Report 30 days after completion of Evaluation | 2020-02-05 | 2020-02-12
Hydraulics | AOC Fit-up and Perf Checkout | 2020-04-23 | 2020-06-02
| 966GC Stage V TB #1 (SG700101) | 2020-01-06 | 2021-05-25
Machine Build | Ship Machine Aurora MDC | 2020-01-06 | 2020-01-08
Machine Build | Machine Build | 2020-01-13 | 2020-03-02
Issue | Build Issue resolution | 2020-03-03 | 2020-03-10
Machine Ship | Ship Machine PPG | 2020-03-12 | 2020-03-16
Machine Check | Machine Checkout STP-64 | 2020-03-23 | 2020-03-27
SW | Ver 01 SW (STP 230/289) (Steering, L5, XSMN) | 2020-04-27 | 2020-05-13
Performance | L5 Performance Check (Include Thermal Mgmt Valve) | 2020-05-14 | 2020-05-25
NVH | Sound Development (Machine, Cab Sound) | 2020-05-26 | 2020-06-02
Engine/EIC | C9.3B Stage V Engine Performance | 2020-06-04 | 2020-06-05
Transmission | Trans Tuning | 2020-06-08 | 2020-06-12
Performance | L5 Tuning # 1 | 2020-06-15 | 2020-06-18
Performance | Rimpull/Response | 2020-06-19 | 2020-07-08
Issue | Issue Resolution # 1 | 2020-07-10 | 2020-07-20
HVAC | HVAC Perf Checkout | 2020-07-21 | 2020-07-23
Cooling | Water Flow and Water System | 2020-07-24 | 2020-08-04
Cooling | Stg V Ambient Capability and UHT | 2020-08-05 | 2020-09-29
SW | Ver 02 SW (STP 230/289) (Steering, L5, XSMN) | 2020-09-30 | 2020-10-01
Machine Build | Machine Update | 2020-10-02 | 2020-10-07
Structures | Light Structures (Stg V Hood-Version 2) OMSA | 2020-10-08 | 2020-11-30
Holiday | US Thanksgiving | 2020-12-01 | 2020-12-07
Structures | Light Structures (Stg V Hood-Version 2) OMSA- Teardown | 2020-12-08 | 2020-12-14
SW | Ver 03 SW (STP 230/289) (L5, XSMN, Engine) | 2020-12-15 | 2020-12-16
Engine/EIC | STP 401 Engine Install Audit | 2020-12-17 | 2020-12-18
Engine/EIC | DEF and Fuel Tank Calibration | 2020-12-21 | 2020-12-22
Holiday | US Christmas and New Year Holiday | 2020-12-23 | 2021-01-04
Engine/EIC | Thermal Mgmt | 2021-01-05 | 2021-01-06
Engine/EIC | Thermal Mgmt endurance-300 hrs | 2021-01-07 | 2021-01-21
Issue | Issue Resolution # 2 | 2021-01-22 | 2021-01-29
Performance | L5 Tuning and Performance Check # 2 | 2021-02-01 | 2021-02-08
SW | Ver 04 SW (STP 230/289) (Steering, L5, XSMN, Engine) BOB | 2021-02-09 | 2021-02-25
Engine/EIC | Dust Ejector Measurement | 2021-03-02 | 2021-03-05
Structures | Limited Slip Differential Driveline Signature- Prod Iron | 2021-03-11 | 2021-04-29
Issue | Issue Resolution # 3 | 2021-05-06 | 2021-05-25
| QPG 966GC CNR4 TB#2 (SG800101) | 2019-12-01 | 2021-07-01
Machine Build | Machine Build + Issue Resolution | 2019-12-01 | 2019-12-29
Holiday | China New Year | 2020-01-24 | 2020-01-31
Performance | L5 Checkout | 2020-02-12 | 2020-02-25
Machine Check | Machine Checkout STP-64 | 2020-02-26 | 2020-03-10
NVH | Sound Test screening | 2020-03-11 | 2020-03-12
Transmission | Trans checkout (Lead by CRDC UPT team) | 2020-03-19 | 2020-04-01
NVH | Sound Test (including cab glass) ISO 9533, HAWB | 2020-04-02 | 2020-04-15
SW | Stg V Ver 01 SW (STP 230) | 2020-04-16 | 2020-04-21
Issue | Issue Resolution # 1 | 2020-04-22 | 2020-04-29
Engine/EIC | Engine Installation Audit | 2020-04-30 | 2020-05-13
Audit | Safety/Serviceability audit | 2020-05-14 | 2020-05-14
Safety | ISO 3450 Brake Feasibility | 2020-05-15 | 2020-06-05
Safety | ISO 5010 Steering Feasibility (Include Secondary Steering) | 2020-06-08 | 2020-06-29
Safety | EMC Feasibility | 2020-06-30 | 2020-07-21
SW | Stg V Ver 02 SW (STP 230) | 2020-10-02 | 2020-10-05
SW | Stage V Ver 03 SW (STP 230) | 2021-01-01 | 2021-01-04
Machine Build | UPT and LPT LCP (NPI Workshop)- Machine Build | 2021-01-11 | 2021-01-20
Machine Check | STP 64/Opr Eval | 2021-01-21 | 2021-01-26
Endurance | 0-250 hrs | 2021-01-27 | 2021-03-01
Inspection | Endurance Inspection | 2021-03-02 | 2021-03-05
Endurance | 251-500 hrs | 2021-03-08 | 2021-04-08
Inspection | Endurance Inspection | 2021-04-09 | 2021-04-14
Endurance | 501-750 hrs | 2021-04-15 | 2021-05-18
Inspection | Endurance Inspection | 2021-05-19 | 2021-05-24
Endurance | 751-1000 hrs | 2021-05-25 | 2021-06-25
Inspection | Endurance Inspection | 2021-06-28 | 2021-07-01
| PPG 966GC Stage V Pilot #1 (SN) | 2021-02-01 | 2022-01-03
Machine Build | Machine Build | 2021-02-01 | 2021-02-10
Holiday | China New Year | 2021-02-11 | 2021-02-18
Machine Build | Machine Build | 2021-02-19 | 2021-03-05
Machine Build | Machine Ship | 2021-03-10 | 2021-04-29
Machine Check | Machine Checkout STP-64 | 2021-05-25 | 2021-05-31
SW | SW Checkout # Pilot V01 | 2021-06-01 | 2021-06-02
Engine/EIC | C9.3B Stage V Engine Performance | 2021-06-03 | 2021-06-04
Performance | L5 Performance Check | 2021-06-07 | 2021-06-10
Endurance | Machine Endurance- 100 hrs | 2021-06-11 | 2021-06-17
NVH | Stg V Alarm, FWD Horn, HAWB CERT | 2021-06-18 | 2021-06-21
Endurance | Endurance 0-250 hrs+ Service/Inspect | 2021-08-06 | 2021-08-20
Endurance | Endurance 251-500 hrs+ Service/Inspect | 2021-08-21 | 2021-09-04
Endurance | Endurance 501-750 hrs+ Service/Inspect | 2021-09-05 | 2021-09-19
Endurance | Endurance 751-1000 hrs+ Service/Inspect | 2021-09-20 | 2021-10-04
Endurance | Endurance 1001-1250 hrs+ Service/Inspect | 2021-10-05 | 2021-10-19
Endurance | Endurance 1251-1500 hrs+ Service/Inspect | 2021-10-20 | 2021-11-03
Endurance | Endurance 1501-1750 hrs+ Service/Inspect | 2021-11-04 | 2021-11-18
Endurance | Endurance 1750-2000 hrs+ Service/Inspect | 2021-11-19 | 2021-12-03
Inspection | Full Inspection | 2021-12-04 | 2021-12-19
Performance | Productivity | 2021-12-20 | 2022-01-03
| QPG 966GC CNR4/ Stg V Pilot #2 (SN) | 2021-02-01 | 2022-01-26
Machine Build | Machine Build | 2021-02-01 | 2021-02-10
Machine Check | China New Year | 2021-02-11 | 2021-02-18
Machine Build | Machine Build | 2021-02-19 | 2021-03-05
Machine Check | Machine Checkout STP-64 | 2021-03-25 | 2021-04-12
Audit | Safety/Serviceability audit | 2021-04-13 | 2021-04-15
SW | SW Checkout # 1 | 2021-04-16 | 2021-04-27
Safety | MLIT Practice & Witness | 2021-04-28 | 2021-06-02
NVH | Sound Test | 2021-06-03 | 2021-06-08
Safety | ISO 3450- Brake CERT | 2021-06-09 | 2021-06-30
Safety | ISO 5010- Steering CERT | 2021-07-01 | 2021-07-20
Safety | ISO 10570-Articulation Lock CERT | 2021-07-21 | 2021-07-29
Safety | Stage V EMC Test CERT | 2021-07-30 | 2021-08-05
Endurance | 0-250 hrs | 2021-08-06 | 2021-09-08
Inspection | Endurance Inspection | 2021-09-09 | 2021-09-14
Endurance | 251-500 hrs | 2021-09-15 | 2021-10-18
Inspection | Endurance Inspection | 2021-10-19 | 2021-10-22
Endurance | 501-750 hrs | 2021-10-25 | 2021-11-25
Inspection | Endurance Inspection | 2021-11-26 | 2021-12-01
Endurance | 751-1000 hrs | 2021-12-02 | 2022-01-04
Inspection | Endurance Inspection | 2022-01-05 | 2022-01-26
| QPG 966GC Pre-Production | 2022-06-01 | 2022-06-14
Safety | MLIT Witness | 2022-06-01 | 2022-06-14
Formulas:
Start = MIN([Start, row below]:C16)
Start = [Finish, row above]+2
Finish = MAX([Finish, row below]:D16)
Finish = [Start]+2