## Sheet1
| Activity ID | Start | Finish
| 966GC Early Pilot PPG (SGW00201) | 2018-07-18 | 2019-08-31
Machine | Machine Checkout STP-64 | 2018-07-18 | 2018-08-07
SW | SW Checkout - S01 | 2018-08-08 | 2018-08-14
Sound | Sound Development | 2018-08-15 | 2018-08-15
SW | L5 Peformance SW Check | 2018-08-16 | 2018-08-22
Engine | Engine Performance Checkout | 2018-08-23 | 2018-08-29
Engine | ET55 Turbo Surge | 2018-08-30 | 2018-08-30
Transmission | Trans Functional Checkout | 2018-08-31 | 2018-09-10
Transmission | Trans Manual Clutch Fill Calibration | 2018-09-11 | 2018-09-13
Transmission | Auto Cal Checkout | 2018-09-14 | 2018-09-17
Performance | L5 Tuning #1 | 2018-09-18 | 2018-09-26
Performance | Rimpull/Response | 2018-09-27 | 2018-10-22
Cooling | STP-153 (Airflow Testing) | 2018-10-23 | 2018-10-31
Hydraulics | Fan Signature Test - Fan Calibration | 2018-11-01 | 2018-11-20
Transmission | UPT ETCA Steady State Performance Analysis | 2018-11-21 | 2018-11-29
Transmission | Shift Development - 12c | 2019-02-21 | 2019-03-06
Performance | L5 Tuning #2 | 2019-02-07 | 2019-03-06
Performance | SCL Verification Operator Eval | 2019-03-07 | 2019-03-08
Transmission | Full CSD TP-6 Powershift Signature Test - 12c | 2019-02-11 | 2019-04-01
Structures | 966GC-105665 | 2019-01-04 | 2019-01-25
SW | SW Checkout S02.1/STP 289 | 2019-04-02 | 2019-04-08
Hydraulics | Fan Signature Test - Reversing Fan | 2019-04-09 | 2019-04-25
SW | SW Checkout S03/STP 289 | 2019-04-26 | 2019-05-02
Machine | Operator Eval | 2019-05-03 | 2019-05-07
Engine | Cold Room Test | 2019-05-08 | 2019-06-25
Heavy Structures | OMSA Heavy Fab Test | 2019-06-26 | 2019-07-31
Performance | Altitude Performance | 2019-08-01 | 2019-08-31
| APPG 966GC Early Pilot (SGW00202) | 2018-04-27 | 2019-07-15
Machine | Machine Check in | 2018-05-07 | 2018-05-07
Machine | STP 064 Machine Checkout | 2018-05-08 | 2018-05-11
SW | SW Check Out (STP 289) | 2018-05-21 | 2018-05-23
Performance | L5 SW Checkout Lite | 2018-05-24 | 2018-05-24
Sound | Sound Screening | 2018-05-25 | 2018-05-25
Transmission | Transmission Tuning Autocal | 2018-05-28 | 2018-05-31
snFactrcfeatunctia | Transmission Functional & Feature Checkout | 2018-06-01 | 2018-06-04
Transmission | Transmission Autocal Development | 2018-06-05 | 2018-06-12
Transmission | Mini CSTDP Powershift Signature Test | 2018-06-13 | 2018-06-26
Safety and Regs | Brake Cert L5 Tires and Str | 2018-07-19 | 2018-07-18
Safety and Regs | Sound Screen/ Vibration Check | 2018-07-20 | 2018-07-26
Safety and Regs | Safety Audit | 2018-07-27 | 2018-07-27
Safety and Regs | EMC | 2018-07-30 | 2018-07-31
Machine | Operator Evaluation Endurance Readiness Survey | 2018-08-01 | 2018-08-02
SW | SW Check Out - SW 2.1 | 2018-08-02 | 2018-08-06
Performance | L5 SW Checkout | 2018-08-07 | 2018-08-08
Cooling | Waterflow/Water System | 2018-08-09 | 2018-08-22
Performance | Engine/Machine Performance Test | 2018-08-23 | 2018-08-30
Hydraulics | Fan Signature test | 2018-08-31 | 2018-09-06
SW | SW Check Out #2 | 2018-09-07 | 2018-09-11
Cooling | Cooling /UHT Checkout | 2018-09-12 | 2018-10-29
Light Structures | Light Fab OMSA/MER | 2018-10-30 | 2018-11-30
Light Structures | Fan ET57 Test | 2018-12-03 | 2018-12-13
Hydraulics | HYD Signature | 2018-12-14 | 2019-01-11
SW | SW Check Out #3 | 2019-01-14 | 2019-01-17
Sound | Sound Development /HAWB | 2019-01-15 | 2019-01-29
Machine | Electronic Load Study | 2019-01-31 | 2019-02-11
SW | SW Check Out #4 | 2019-02-12 | 2019-02-12
Light Structures | Light Fab OMSA/MER #2 | 2019-02-13 | 2019-03-07
Performance | Productivity and Fuel Consumption 2 machine | 2019-03-08 | 2019-03-26
Heavy Structures | Driveline Signature #2 | 2019-05-06 | 2019-06-12
| APPG 966GC Endurance Pilot #1 (SGW00203) | 2018-07-26 | 2019-01-02
Machine | Pilot #1 Machine Check in | 2018-08-01 | 2018-08-01
Machine | Pilot #1 STP 064 Machine Checkout | 2018-08-02 | 2018-08-07
Machine | Pilot #1 Endurance 0-250h | 2018-08-08 | 2018-08-27
Machine | 966GC-10730 | 2018-08-08 | 2018-08-23
Inspection 1 | 966GC-10810 | 2018-08-24 | 2018-08-27
Machine | Pilot #1 Endurance 250-500h | 2018-08-28 | 2018-09-14
Machine | 966GC-10840 | 2018-08-28 | 2018-09-12
Inspection 1 | 966GC-10900 | 2018-09-13 | 2018-09-14
Machine | Pilot #1 Endurance 500-750h | 2018-09-17 | 2018-10-11
Machine | 966GC-11050 | 2018-09-17 | 2018-10-09
Inspection 1 | 966GC-11120 | 2018-10-10 | 2018-10-11
Machine | Pilot #1 Endurance 750-1000h | 2018-10-12 | 2018-10-31
Machine | 966GC-11160 | 2018-10-12 | 2018-10-29
Inspection 1 | 966GC-11230 | 2018-10-30 | 2018-10-31
Machine | Pilot #1 Endurance 1000-1250h | 2018-11-01 | 2018-11-20
Machine | 966GC-11280 | 2018-11-01 | 2018-11-16
Inspection 1 | 966GC-11370 | 2018-11-19 | 2018-11-20
Machine | Pilot #1 STP 064 Machine Checkout #2 | 2018-11-21 | 2018-11-26
Inspection 1 | Pilot #1 Final Inspection | 2018-11-27 | 2018-12-17
| APPG 966GC Endurance Pilot #2 (SGW00207) | 2018-07-26 | 2018-10-18
Machine | Pilot #2 Machine Check in | 2018-08-01 | 2018-08-01
Machine | Pilot #2 STP 064 Machine Checkout | 2018-08-02 | 2018-08-07
Machine | Pilot #2 Endurance 0-250h | 2018-08-08 | 2018-08-27
Machine | 966GC-10740 | 2018-08-08 | 2018-08-23
Inspection 2 | 966GC-10820 | 2018-08-24 | 2018-08-27
Machine | Pilot #2 Endurance 250-500h | 2018-08-28 | 2018-09-14
Machine | 966GC-10850 | 2018-08-28 | 2018-09-12
Inspection 2 | 966GC-10910 | 2018-09-13 | 2018-09-14
Machine | Pilot #2 Endurance 500-750h | 2018-09-17 | 2018-10-11
Machine | 966GC-10930 | 2018-09-17 | 2018-10-09
Inspection 2 | 966GC-11030 | 2018-10-10 | 2018-10-11
Machine | Pilot #2 STP 064 Machine Checkout#2 | 2018-10-12 | 2018-10-17
Formulas:
Start = [Start, row below]

## calendar
Machine S/N | Phase | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 |  | 2018-05-14 | 2018-05-21 |  |  | 2018-05-28 |  | 2018-06-04 |  | 2018-06-11 |  | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 |  |  | 2018-07-23 |  | 2018-07-30 |  |  | 2018-08-06 |  |  |  | 2018-08-13 |  |  | 2018-08-20 |  |  | 2018-08-27 |  |  |  | 2018-09-03 |  | 2018-09-10 |  |  |  |  | 2018-09-17 |  | 2018-09-24 |  | 2018-10-01 | 2018-10-08 |  |  | 2018-10-15 | 2018-10-22 |  | 2018-10-29 |  |  | 2018-11-05 | 2018-11-12 | 2018-11-19 |  | 2018-11-26 |  | 2018-12-03 | 2018-12-10 |  | 2018-12-17 | 2018-12-24 | 2018-12-31 |  | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 |  | 2019-02-04 |  | 2019-02-11 |  |  | 2019-02-18 | 2019-02-25 | 2019-03-04 |  | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 |  | 2019-04-08 |  | 2019-04-15 | 2019-04-22 |  | 2019-04-29 |  | 2019-05-06 |  | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 |  | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 |  | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30
SGW00201 | 966GC Early Pilot PPG | [35 empty] | Machine Checkout STP-64 | [8 empty] | SW Checkout - S01 |  |  | Sound Development | L5 Peformance SW Check |  | Engine Performance Checkout |  |  |  | ET55 Turbo Surge | Trans Functional Checkout |  |  |  | Trans Manual Clutch Fill Calibration |  |  | Auto Cal Checkout |  | L5 Tuning #1 |  | Rimpull/Response | [6 empty] | STP-153 (Airflow Testing) |  |  | Fan Signature Test - Fan Calibration |  |  |  | UPT ETCA Steady State Performance Analysis | [8 empty] | 966GC-105665 | [6 empty] | L5 Tuning #2 | [11 empty] | SW Checkout S02.1/STP 289 |  | Fan Signature Test - Reversing Fan |  |  | SW Checkout S03/STP 289 |  | Operator Eval |  | Cold Room Test | [7 empty] | OMSA Heavy Fab Test | [5 empty] | Altitude Performance
SGW00202 | APPG 966GC Early Pilot | [18 empty] | Machine Check in | STP 064 Machine Checkout |  | SW Check Out (STP 289) | L5 SW Checkout Lite | Sound Screening | Transmission Tuning Autocal | Transmission Functional & Feature Checkout |  | Transmission Autocal Development |  | Mini CSTDP Powershift Signature Test | [5 empty] | Brake Cert L5 Tires and Str | Sound Screen/ Vibration Check |  | Safety Audit | EMC | Operator Evaluation Endurance Readiness Survey |  |  | L5 SW Checkout |  | Waterflow/Water System |  |  |  |  | Engine/Machine Performance Test |  |  |  |  | Fan Signature test |  | SW Check Out #2 |  |  | Cooling /UHT Checkout | [14 empty] | Light Fab OMSA/MER | [7 empty] | Fan ET57 Test |  | HYD Signature | [5 empty] | SW Check Out #3 |  |  | Electronic Load Study |  |  |  | SW Check Out #4 | Light Fab OMSA/MER #2 |  |  |  | Productivity and Fuel Consumption 2 machine | [12 empty] | Driveline Signature #2
SGW00203 | APPG 966GC Endurance Pilot #1 | [40 empty] | Pilot #1 Machine Check in | Pilot #1 STP 064 Machine Checkout
Pilot #1 Endurance 0-250 | Pilot #1 Endurance 0-250 | [44 empty] | 966GC-10730 | [6 empty] | 966GC-10810
Pilot #1 Endurance 250-500 | Pilot #1 Endurance 250-500 | [53 empty] | 966GC-10840 | [7 empty] | 966GC-10900
Pilot #1 Endurance 500-750 | Pilot #1 Endurance 500-750 | [63 empty] | 966GC-11050 | [5 empty] | 966GC-11120
Pilot #1 Endurance 750-1000 | Pilot #1 Endurance 750-1000 | [70 empty] | 966GC-11160 |  |  |  |  | 966GC-11230
Pilot #1 Endurance 1000-1250 | Pilot #1 Endurance 1000-1250 | [76 empty] | 966GC-11280 |  |  | 966GC-11370 | Pilot #1 STP 064 Machine Checkout #2 |  | Pilot #1 Final Inspection
SGW00207 | APPG 966GC Endurance Pilot #2 | [40 empty] | Pilot #2 Machine Check in | Pilot #2 STP 064 Machine Checkout
Pilot #2 Endurance 0-250 | Pilot #2 Endurance 0-250 | [44 empty] | 966GC-10740 | [6 empty] | 966GC-10820
Pilot #2 Endurance 250-500 | Pilot #2 Endurance 250-500 | [53 empty] | 966GC-10850 | [7 empty] | 966GC-10910
Pilot #2 Endurance 500-750 | Pilot #2 Endurance 500-750 | [63 empty] | 966GC-10930 | [5 empty] | 966GC-11030 | Pilot #2 STP 064 Machine Checkout#2

## format
|  |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | Apr 2 2018 | [6 empty] | Apr 9 2018 | [6 empty] | Apr 16 2018 | [6 empty] | #VALUE! | [6 empty] | Apr 16 2020 | [6 empty] | Apr 16 2021 | [6 empty] | Apr 16 2022 | [6 empty] | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T | W | Th | F | Sa | Su |  | M | T
966GC Early Pilot PPG (SGW00201) |  |  | 2018-01-01 | 2018-01-02 | 2018-01-03 | 2018-01-04 | 2018-01-05 | 2018-01-06 | 2018-01-07 | -------- | 2018-01-08 | 2018-01-09 | 2018-01-10 | 2018-01-11 | 2018-01-12 | 2018-01-13 | 2018-01-14 | -------- | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-19 | 2018-01-20 | 2018-01-21 | -------- | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-27 | 2018-01-28 | -------- | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-03 | 2018-02-04 | -------- | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-10 | 2018-02-11 | -------- | 2018-02-12 | 2018-02-13 | 2018-02-14 | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-18 | -------- | 2018-02-19 | 2018-02-20 | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-25 | -------- | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-03 | 2018-03-04 | -------- | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-10 | 2018-03-11 | -------- | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-17 | 2018-03-18 | -------- | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-25 | -------- | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30 | 2018-03-31 | 2018-04-01 | -------- | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | -------- | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | -------- | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | -------- | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | -------- | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | -------- | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | -------- | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | -------- | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | -------- | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2018-06-03 | -------- | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-08 | 2018-06-09 | 2018-06-10 | -------- | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-16 | 2018-06-17 | -------- | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | -------- | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-06-30 | 2018-07-01 | -------- | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-07 | 2018-07-08 | -------- | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-14 | 2018-07-15 | -------- | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | -------- | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-29 | -------- | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-04 | 2018-08-05 | -------- | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-11 | 2018-08-12 | -------- | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-18 | 2018-08-19 | -------- | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-25 | 2018-08-26 | -------- | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2018-09-01 | 2018-09-02 | -------- | 2018-09-03 | 2018-09-04 | 2018-09-05 | 2018-09-06 | 2018-09-07 | 2018-09-08 | 2018-09-09 | -------- | 2018-09-10 | 2018-09-11 | 2018-09-12 | 2018-09-13 | 2018-09-14 | 2018-09-15 | 2018-09-16 | -------- | 2018-09-17 | 2018-09-18 | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | -------- | 2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | -------- | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | -------- | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | -------- | 2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-18 | 2018-10-19 | 2018-10-20 | 2018-10-21 | -------- | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27 | 2018-10-28 | -------- | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | -------- | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | -------- | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | -------- | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | -------- | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-01 | 2018-12-02 | -------- | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08 | 2018-12-09 | -------- | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-15 | 2018-12-16 | -------- | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-22 | 2018-12-23 | -------- | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29 | 2018-12-30 | -------- | 2018-12-31 | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06 | -------- | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | -------- | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20 | -------- | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27 | -------- | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31 | 2019-02-01 | 2019-02-02 | 2019-02-03 | -------- | 2019-02-04 | 2019-02-05 | 2019-02-06 | 2019-02-07 | 2019-02-08 | 2019-02-09 | 2019-02-10 | -------- | 2019-02-11 | 2019-02-12 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-16 | 2019-02-17 | -------- | 2019-02-18 | 2019-02-19 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-23 | 2019-02-24 | -------- | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02 | 2019-03-03 | -------- | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-09 | 2019-03-10 | -------- | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | -------- | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 | -------- | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | -------- | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | -------- | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | -------- | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | -------- | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | -------- | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | -------- | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | -------- | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | -------- | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | -------- | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | -------- | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09 | -------- | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-15 | 2019-06-16 | -------- | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | -------- | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30 | -------- | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | -------- | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | -------- | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21 | -------- | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | -------- | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | -------- | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | -------- | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | -------- | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | -------- | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | 2019-09-01 | -------- | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | -------- | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | -------- | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | -------- | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | -------- | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | -------- | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | -------- | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | -------- | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | -------- | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-03 | -------- | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | -------- | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | -------- | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24 | -------- | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | -------- | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | -------- | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | -------- | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | -------- | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | -------- | 2019-12-30 | 2019-12-31
| Machine | Machine Checkout STP-64 | [226 empty] | Start | [22 empty] | End
| SW | SW Checkout - S01 | [250 empty] | Start | [6 empty] | End
| Sound | Sound Development | [258 empty] | End
| SW | L5 Peformance SW Check | [259 empty] | Start | [6 empty] | End
| Engine | Engine Performance Checkout | [267 empty] | Start | [6 empty] | End
| Engine | ET55 Turbo Surge | [275 empty] | End
| Transmission | Trans Functional Checkout | [276 empty] | Start | [11 empty] | End
| Transmission | Trans Manual Clutch Fill Calibration | [289 empty] | Start |  | End
| Transmission | Auto Cal Checkout | [292 empty] | Start |  |  |  | End
| Performance | L5 Tuning #1 | [297 empty] | Start | [8 empty] | End
| Performance | Rimpull/Response | [307 empty] | Start | [28 empty] | End
| Cooling | STP-153 (Airflow Testing) | [337 empty] | Start | [8 empty] | End
| Hydraulics | Fan Signature Test - Fan Calibration | [347 empty] | Start | [21 empty] | End
| Transmission | UPT ETCA Steady State Performance Analysis | [370 empty] | Start | [8 empty] | End
| Transmission | Shift Development - 12c | [475 empty] | Start | [14 empty] | End
| Performance | L5 Tuning #2 | [459 empty] | Start | [30 empty] | End
| Performance | SCL Verification Operator Eval | [491 empty] | Start | End
| Transmission | Full CSD TP-6 Powershift Signature Test - 12c | [464 empty] | Start | [55 empty] | End
| Structures | 966GC-105665 | [420 empty] | Start | [23 empty] | End
| SW | SW Checkout S02.1/STP 289 | [521 empty] | Start | [6 empty] | End
| Hydraulics | Fan Signature Test - Reversing Fan | [529 empty] | Start | [17 empty] | End
| SW | SW Checkout S03/STP 289 | [548 empty] | Start | [6 empty] | End
| Machine | Operator Eval | [556 empty] | Start |  |  |  |  | End
| Engine | Cold Room Test | [562 empty] | Start | [54 empty] | End
| Heavy Structures | OMSA Heavy Fab Test | [618 empty] | Start | [39 empty] | End
| Performance | Altitude Performance | [659 empty] | Start | [33 empty] | End
APPG 966GC Early Pilot (SGW00202)
| Machine | Machine Check in | [144 empty] | End
| Machine | STP 064 Machine Checkout | [145 empty] | Start |  |  | End
| SW | SW Check Out (STP 289) | [160 empty] | Start |  | End
| Performance | L5 SW Checkout Lite | [163 empty] | End
| Sound | Sound Screening | [164 empty] | End
| Transmission | Transmission Tuning Autocal | [168 empty] | Start |  |  | End
| Transmission | Transmission Functional & Feature Checkout | [172 empty] | Start |  |  |  | End
| Transmission | Transmission Autocal Development | [177 empty] | Start | [7 empty] | End
| Transmission | Mini CSTDP Powershift Signature Test | [186 empty] | Start | [14 empty] | End
| Safety and Regs | Brake Cert L5 Tires and Str | [226 empty] | End | Start
| Safety and Regs | Sound Screen/ Vibration Check | [228 empty] | Start | [6 empty] | End
| Safety and Regs | Safety Audit | [236 empty] | End
| Safety and Regs | EMC | [240 empty] | Start | End
| Machine | Operator Evaluation Endurance Readiness Survey | [242 empty] | Start | End
| SW | SW Check Out - SW 2.1 | [243 empty] | Start |  |  |  |  | End
| Performance | L5 SW Checkout | [249 empty] | Start | End
| Cooling | Waterflow/Water System | [251 empty] | Start | [14 empty] | End
| Performance | Engine/Machine Performance Test | [267 empty] | Start | [7 empty] | End
| Hydraulics | Fan Signature test | [276 empty] | Start | [6 empty] | End
| SW | SW Check Out #2 | [284 empty] | Start |  |  |  |  | End
| Cooling | Cooling /UHT Checkout | [290 empty] | Start | [53 empty] | End
| Light Structures | Light Fab OMSA/MER | [345 empty] | Start | [34 empty] | End
| Light Structures | Fan ET57 Test | [384 empty] | Start | [10 empty] | End
| Hydraulics | HYD Signature | [396 empty] | Start | [31 empty] | End
| SW | SW Check Out #3 | [432 empty] | Start |  |  | End
| Sound | Sound Development /HAWB | [433 empty] | Start | [15 empty] | End
| Machine | Electronic Load Study | [451 empty] | Start | [12 empty] | End
| SW | SW Check Out #4 | [465 empty] | End
| Light Structures | Light Fab OMSA/MER #2 | [466 empty] | Start | [24 empty] | End
| Performance | Productivity and Fuel Consumption 2 machine | [492 empty] | Start | [20 empty] | End
| Heavy Structures | Driveline Signature #2 | [560 empty] | Start | [41 empty] | End
APPG 966GC Endurance Pilot #1 (SGW00203)
| Machine | Pilot #1 Machine Check in | [242 empty] | End
| Machine | Pilot #1 STP 064 Machine Checkout | [243 empty] | Start | [5 empty] | End
|  | Pilot #1 Endurance 0-250h | [250 empty] | Start | [21 empty] | End
| Machine | 966GC-10730 | [250 empty] | Start | [16 empty] | End
| Inspection 1 | 966GC-10810 | [268 empty] | Start |  |  |  | End
|  | Pilot #1 Endurance 250-500h | [273 empty] | Start | [18 empty] | End
| Machine | 966GC-10840 | [273 empty] | Start | [16 empty] | End
| Inspection 1 | 966GC-10900 | [291 empty] | Start | End
|  | Pilot #1 Endurance 500-750h | [296 empty] | Start | [26 empty] | End
| Machine | 966GC-11050 | [296 empty] | Start | [24 empty] | End
| Inspection 1 | 966GC-11120 | [322 empty] | Start | End
|  | Pilot #1 Endurance 750-1000h | [324 empty] | Start | [21 empty] | End
| Machine | 966GC-11160 | [324 empty] | Start | [19 empty] | End
| Inspection 1 | 966GC-11230 | [345 empty] | Start | End
|  | Pilot #1 Endurance 1000-1250h | [347 empty] | Start | [21 empty] | End
| Machine | 966GC-11280 | [347 empty] | Start | [16 empty] | End
| Inspection 1 | 966GC-11370 | [368 empty] | Start | End
| Machine | Pilot #1 STP 064 Machine Checkout #2 | [370 empty] | Start | [5 empty] | End
| Inspection 1 | Pilot #1 Final Inspection | [377 empty] | Start | [22 empty] | End
APPG 966GC Endurance Pilot #2 (SGW00207)
| Machine | Pilot #2 Machine Check in | [242 empty] | End
| Machine | Pilot #2 STP 064 Machine Checkout | [243 empty] | Start | [5 empty] | End
|  | Pilot #2 Endurance 0-250h | [250 empty] | Start | [21 empty] | End
| Machine | 966GC-10740 | [250 empty] | Start | [16 empty] | End
| Inspection 2 | 966GC-10820 | [268 empty] | Start |  |  |  | End
|  | Pilot #2 Endurance 250-500h | [273 empty] | Start | [18 empty] | End
| Machine | 966GC-10850 | [273 empty] | Start | [16 empty] | End
| Inspection 2 | 966GC-10910 | [291 empty] | Start | End
|  | Pilot #2 Endurance 500-750h | [296 empty] | Start | [26 empty] | End
| Machine | 966GC-10930 | [296 empty] | Start | [24 empty] | End
| Inspection 2 | 966GC-11030 | [322 empty] | Start | End
| Machine | Pilot #2 STP 064 Machine Checkout#2 | [324 empty] | Start | [5 empty] | End