## Jan 7 2020
966GC Stg V and CNR4 Machine S/N | Phase | 2019-04-01 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 |  | 2019-11-25 | 2019-12-02 |  | 2019-12-09 |  |  | 2019-12-16 | 2019-12-23 | 2019-12-30 |  | 2020-01-06 |  | 2020-01-13 |  |  | 2020-01-20 |  |  | 2020-01-27 |  |  | 2020-02-03 | 2020-02-10 |  | 2020-02-17 |  | 2020-02-24 | 2020-03-02 |  |  | 2020-03-09 |  |  | 2020-03-16 | 2020-03-23 |  | 2020-03-30 |  | 2020-04-06 | 2020-04-13 |  |  | 2020-04-20 |  |  |  | 2020-04-27 |  |  | 2020-05-04 | 2020-05-11 | 2020-05-18 |  | 2020-05-25 |  | 2020-06-01 |  | 2020-06-08 |  |  | 2020-06-15 | 2020-06-22 | 2020-06-29 |  |  | 2020-07-06 |  | 2020-07-13 |  |  | 2020-07-20 |  | 2020-07-27 |  |  |  | 2020-08-03 |  | 2020-08-10 |  | 2020-08-17 |  |  |  | 2020-08-24 |  | 2020-08-31 |  | 2020-09-07 | 2020-09-14 |  | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 |  |  |  | 2020-11-02 | 2020-11-09 |  | 2020-11-16 | 2020-11-23 | 2020-11-30 |  |  | 2020-12-07 |  |  | 2020-12-14 |  | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 |  | 2021-01-25 |  |  | 2021-02-01 | 2021-02-08 |  |  | 2021-02-15 |  |  | 2021-02-22 | 2021-03-01 | 2021-03-08 |  |  |  | 2021-03-15 | 2021-03-22 |  | 2021-03-29 |  | 2021-04-05 | 2021-04-12 | 2021-04-19 |  | 2021-04-26 |  | 2021-05-03 |  | 2021-05-10 |  | 2021-05-17 | 2021-05-24 |  |  |  | 2021-05-31 |  |  | 2021-06-07 |  | 2021-06-14 |  |  | 2021-06-21 |  | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 |  | 2021-08-02 |  |  | 2021-08-09 |  |  | 2021-08-16 |  | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 |  | 2021-09-20 | 2021-09-27 |  | 2021-10-04 |  | 2021-10-11 |  |  | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 |  | 2021-11-29 |  | 2021-12-06 |  | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 |  | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 |  | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 |  | 2022-06-06
Key Project Milestone | Key Project Milestone |  | GW 1/2 | [35 empty] | Quality Gate 3 | [15 empty] | GW 3/4 | [22 empty] | Pilot Design Freeze |  |  |  |  | Machine Ready for Field | [15 empty] | Pilot EDS Freeze | [9 empty] | Endurance Complete | [23 empty] | GW 5 |  |  |  | Ship DL Axle from China Supplier | [65 empty] | LPT (Axle) Design Freeze | [8 empty] | Production EDS Freeze |  | GW 5.5 | [21 empty] | GW 6
Key Validation review | Key Validation review | [37 empty] | Validation Review 3 | [46 empty] | Validation Review 4 | [24 empty] | Validation Review 5
Software Milestone | Software Milestone | [24 empty] | V01 SW Content Freeze | [17 empty] | Receive V01 SW | [28 empty] | V02 SW Content Freeze | [15 empty] | Receive V02 SW | [13 empty] | V03 SW Content Freeze | [9 empty] | Receive V03 SW | [8 empty] | V04 SW Content Freeze | [7 empty] | Receive V04 SW (Pilot)
TIC Report Milestone | TIC Report Milestone | [78 empty] | EMC-Pilot- Pilot | ISO 9533 Horn, Back-up Alarm EN474 HAWB- Pilot | [13 empty] | ISO 5010 Steering Feasibility (Pilot) | [59 empty] | ISO 3450 Brake CERT | [5 empty] | ISO 5010 Steering CERT |  | ISO 10570-Articulation Lock CERT | [26 empty] | ISO 9533 Horn, Back-up Alarm HAWB CERT | [11 empty] | Stg V EMC CERT
SGW00208 | 966GC T3 TB #3 | [12 empty] | Shift Dev |  |  | HVAC Perf Checkout |  |  |  | Water system/ With Prod Rad Fixes |  |  |  | L5 Tuning |  |  |  | Operator Eval |  | Endurance-250 hrs |  |  |  | Final Inspection | [41 empty] | Machine Update for OMSA # 2 | [9 empty] | Light Structures (Stg V Hood) OMSA #2 (Likely Path)
Tech Center ShakeTable | Tech Center ShakeTable | [9 empty] | Hood arrives at Tech Center, Peoria | [9 empty] | Stage V Shake Table # 1 | [76 empty] | Stage V Shake Table # 2 with OMSA Drive File (Post Machine OMSA)
SG700101 | 966GC Stage V TB #1 | [17 empty] | Holiday Break |  | Ship Machine Aurora MDC |  | Machine Build (Teardown and start build Jan 26) | [14 empty] | Build Issue resolution | Ship Machine PPG |  | Machine Checkout STP-64 |  | Ver 01 SW (STP 230/289) (Steering, L5, XSMN) |  |  |  | Sound Development (Machine, Cab Sound) |  | L5 Performance Check (Include Thermal Mgmt Valve) |  |  | C9.3B Stage V Engine Performance | Trans Perf Checkout |  |  |  | L5 Tuning # 1 |  | Operator Eval | Rimpull/Response |  |  |  | HVAC Perf Checkout |  | Issue Resolution # 1 |  | Safety/Serviceability audit |  | Water Flow and Water System |  |  | Stg V Ambient Capability and UHT (Include AOC Channels) | [17 empty] | Ver 02 SW (STP 230/289) (Steering, L5, XSMN) |  | Dust Ejector Measurement |  |  | STP 401 Engine Install Audit | DEF and Fuel Tank Calibration |  |  |  |  | Issue Resolution # 2 |  | Dealer Service Training | L5 Tuning and Performance Check # 2 | [8 empty] | Ver 03 SW (STP 230/289) (Steering, L5, XSMN, Engine) BOB |  |  |  | Thermal Mgmt | Thermal Mgmt endurance |  |  |  |  | Endurance 0-500 hrs+ Service/Inspect (Cold Ambient) | [7 empty] | Ver 04 SW (STP 230/289) (Steering, L5, XSMN, Engine) | [6 empty] | Issue Resolution # 3 | [11 empty] | Limited Slip Differential Development Driveline Signature | [14 empty] | Stage V Engine Cold Room (TC-L)
S8W00101 | QPG 966GC CNR4 TB#2 | [14 empty] | Machine Build + Issue Resolution | [11 empty] | China New Year |  |  |  | Machine Checkout STP-64 (Hydraulic Checkout) |  |  |  |  | CNR4 SW Checkout-250 hrs |  |  | Sound Test (including cab glass) ISO 9533, HAWB |  |  | Engine Installation Audit |  |  |  | Stg V Ver 01 SW (STP 230) |  | Upper Powertrain Checkout( Shift Perf,Chk Pressure on all clutchs, CTS, HSDS,TSC1 Comm) |  | Hydraulic checkout |  | L5 Checkout |  |  | CNR4 SW Endurance- 250 hrs (Assess AOC Thermal Capability) | [9 empty] | Endurance Inspection |  |  |  |  | EMC Feasibility |  |  |  | L5 Checkout- Stg V | Safety/Serviceability audit | ISO 3450 Brake Feasibility (Optional) | [7 empty] | ISO 5010 Steering Feasibility (Include Secondary Steering) | [6 empty] | Stg V Ver 02 SW (STP 230) |  | Endurance 250-750 hrs | [15 empty] | Endurance Inspection | [10 empty] | Stage V Ver 04 SW (STP 230)
SN | PPG 966GC Stage V Pilot #1 | [131 empty] | Machine Build |  |  | China New Year |  |  | Machine Build | [6 empty] | Machine Ship | [17 empty] | Machine Checkout STP-64 |  |  |  | SW Checkout # Pilot V01 | C9.3B Stage V Engine Performance | L5 Performance Check | Machine Endurance- 100 hrs |  |  | Light Structures (Stg V Hood) OMSA # 3 | [9 empty] | Stg V Alarm, FWD Horn, HAWB CERT | Stage V EMC Test |  |  | Endurance 0-250 hrs+ Service/Inspect |  |  |  | Endurance 251-500 hrs+ Service/Inspect |  |  | Productivity
SN | QPG 966GC CNR4/ Stg V Pilot #2 | [131 empty] | Machine Build |  |  | China New Year |  |  |  | Machine Checkout STP-64 |  |  |  | Safety/Serviceability audit | SW Checkout # 1 |  |  |  | MLIT Practice | [7 empty] | Sound Test |  | ISO 3450- Brake CERT | [5 empty] | ISO 5010- Steering CERT | [7 empty] | ISO 10570-Articulation Lock CERT |  |  | Endurance 0-250 hrs | [5 empty] | Service/Inspect |  |  |  |  | Endurance 251-500 hrs (Axle Inspection) | [10 empty] | China National Day |  | Service/Inspect |  |  |  |  | Endurance 501-750 hrs |  |  |  |  | Service/Inspect |  |  |  |  | Endurance 750-1000 hrs |  |  |  |  | Service/Inspect
QPG 966GC Pre-Production | QPG 966GC Pre-Production | [240 empty] | MLIT Witness
Pilot EDS Freeze
PRODUCTION EDS Freeze