## Sheet1
| Activity Name | Start | Finish
Key Project Milestones
GW | GW 1/2 | 2019-10-01
QG | Quality Gate 3 | 2020-03-03
GW | GW 3/4 | 2020-04-01
GW | Machine Ready for Field
DF | Pilot EDS Freeze | 2020-09-03
GW | Endurance Complete
DF | Production EDS Freeze | 2021-12-01
GW | GW 5 | 2021-02-01
GW | GW 5.5 | 2021-12-10
GW | GW 6 | 2022-05-01
Key Validation reviews
VR | Validation Review 3
VR | Validation Review 4 | 2020-08-01
VR | Validation Review 5 | 2020-11-02
Software Milestones
SW | Receive V01 SW | 2019-11-22
SW | V02 SW Content Freeze | 2019-12-15
SW | Receive V02 SW | 2020-02-21
SW | V03 SW Content Freeze | 2020-03-01
SW | Receive V03 SW | 2020-04-24
SW | V04 SW Content Freeze | 2020-05-11
SW | Receive V04 SW (Pilot) | 2020-06-19
SW | V05 SW Content Freeze | 2020-06-28
SW | Receive V04 SW (Pilot) | 2020-07-24
TIC Report Milestones
Pilot | EMC-Pilot- Pilot
Pilot | ISO 9533 Horn, Back-up Alarm EN474 HAWB- Pilot
Pilot | ISO 5010 Steering Feasibility (Pilot) | 2020-08-24
Pilot | ISO 3450 Brake Feasibility (Pilot) | 2020-08-26
Production | Stg V EMC CERT
Production | ISO 3450 Brake CERT | 2021-04-25
Production | ISO 5010 Steering CERT | 2021-05-16
Production | ISO 9533 Horn, Back-up Alarm HAWB CERT | 2021-08-22
Production | ISO 10570-Articulation Lock CERT | 2021-05-25
Tech Center ShakeTable
Parts | Hood arrives at Tech Center, Peoria | 2019-11-20 | 2019-12-15
Shake Table | Stage V Shake Table # 1 | 2020-01-06 | 2020-01-31
Machine Build | Machine Update for OMSA # 2 | 2020-08-10
Shake Table | Stage V Shake Table # 2 with OMSA Drive File (Post Machine OMSA) | 2020-09-01
966GC T3 TB #3 (SGW00208)
Transmission | Shift Dev | 2019-12-05
HVAC | HVAC Perf Checkout
Cooling2 | Water system/ With Prod Rad Fixes | 2020-01-06
Performance | L5 Tuning
Opr Eval | Operator Eval
Endurance | Endurance-250 hrs
Inspection | Final Inspection
Machine Build | Machine Update
Light Structures | Light Structures (Stg V Hood) OMSA #1 (Contingency)
Machine Build | Machine Update
Light Structures | Light Structures (Stg V Hood) OMSA #2 (Likely Path) | 2020-08-03
966GC Stage V TB #1 (SGW00201)
Machine Ship | Ship Machine Aurora MDC | 2020-01-06
Machine Build | Machine Build (Teardown and start build Jan 26)
Machine Build | Build Issue resolution
Machine Ship | Ship Machine PPG
Machine Check | Machine Checkout STP-64
SW | Ver 01 SW (STP 230/289) (Steering, L5, XSMN)
NVH | Sound Development (Machine, Cab Sound)
Performance | L5 Performance Check (Include Thermal Mgmt Valve)
Engine | C9.3B Stage V Engine Performance
Transmission | Trans Tuning
Performance | L5 Tuning # 1
Performance | Operator Eval
Performance | Rimpull/Response
HVAC | HVAC Perf Checkout
Issue | Issue Resolution # 1
SW | Ver 02 SW (STP 230/289) (Steering, L5, XSMN)
Audit | Safety/Serviceability audit
Cooling 2 | Water Flow and Water System
Cooling 3 | Stg V Ambient Capability and UHT (Include AOC Channels)
EIC | Dust Ejector Measurement
Engine | STP 401 Engine Install Audit
Engine | DEF and Fuel Tank Calibration
SW | Ver 03 SW (STP 230/289) (L5, XSMN, Engine)
Structures2 | Limited Slip Differential Development Driveline Signature
Issue | Issue Resolution # 2
Product Support | Dealer Service Training
Performance | L5 Tuning and Performance Check # 2
SW | Ver 04 SW (STP 230/289) (Steering, L5, XSMN, Engine) BOB
Engine | Thermal Mgmt
SW | Ver 05 SW (STP 230/289) (L5, XSMN)
Engine | Thermal Mgmt endurance
Endurance#1 | Endurance 0-500 hrs+ Service/Inspect (Cold Ambient)
Issue | Issue Resolution # 3
Performance | Stage V Engine Cold Room (TC-L)
QPG 966GC CNR4 TB#2 (SGW00202)
Machine Build | Machine Build + Issue Resolution | 2019-12-15
Holiday | China New Year | 2020-01-24
Machine Check | Machine Checkout STP-64
SW | CNR4 SW Checkout-250 hrs
Endurance #2 | Sound Test (including cab glass) ISO 9533, HAWB
EIC | Engine Installation Audit
Issue | Issue Resolution # 1
Hydraulics#1 | Hydraulic checkout
Performance | L5 Checkout
Endurance#1 | CNR4 SW Endurance- 250 hrs
Inspection | Endurance Inspection
Safety | EMC Feasibility
SW | Stg V Ver 02 SW (STP 230)
Performance | L5 Checkout- Stg V
Audit | Safety/Serviceability audit
Safety | ISO 3450 Brake Feasibility (Optional)
Safety | ISO 5010 Steering Feasibility (Include Secondary Steering)
SW | Stg V Ver 03 SW (STP 230)
Endurance # 1 | Endurance 250-750 hrs
Inspection | Endurance Inspection
SW | Stage V Ver 04 SW (STP 230)
PPG 966GC Stage V Pilot #1 (SN)
Machine Build | Machine Build | 2021-02-01
Holiday | China New Year | 2021-02-11
Machine Build | Machine Build
Machine Ship | Machine Ship
Machine Check | Machine Checkout STP-64
SW | SW Checkout # Pilot V01
Engine | C9.3B Stage V Engine Performance
Performance | L5 Performance Check
Endurance #1 | Machine Endurance- 100 hrs
Light Structures | Light Structures (Stg V Hood) OMSA # 3
NVH | Stg V Alarm, FWD Horn, HAWB CERT
Safety | Stage V EMC Test
Endurance #1 | Endurance 0-250 hrs+ Service/Inspect
Endurance #2 | Endurance 251-500 hrs+ Service/Inspect
Performance | Productivity
QPG 966GC CNR4/ Stg V Pilot #2 (SN)
Machine Build | Machine Build | 2021-02-01
Machine Check | China New Year | 2021-02-11
Machine Ship | Machine Checkout STP-64
Audit | Safety/Serviceability audit
SW | SW Checkout # 1
Safety | MLIT Practice
Safety | MLIT Witness (Is witness test 12 weeks after MLIT practice?)
NVH | Sound Test
Safety | ISO 3450- Brake CERT
Safety | ISO 5010- Steering CERT
Safety | ISO 10570-Articulation Lock CERT
Endurance #1 | Endurance 0-250 hrs
Service | Service/Inspect
Endurance #2 | Endurance 251-500 hrs
Holiday | China National Day | 2021-10-01
Service | Service/Inspect
Endurance #3 | Endurance 501-750 hrs
Service | Service/Inspect
Endurance #4 | Endurance 750-1000 hrs
Service | Service/Inspect
Formulas:
Finish = WORKDAY([Start],8)
Finish = WORKDAY([Start], 5)
Start = WORKDAY([Finish, row above],1)

## Calendar
Machine S/N | Phase | 8/1/2019 | 8/8/2019 | 8/15/2019 | 8/22/2019 | 8/29/2019 | 9/5/2019 | 9/12/2019 | 9/19/2019 | 9/26/2019 |  | 10/3/2019 | 10/10/2019 | 10/17/2019 | 10/24/2019 | 10/31/2019 | 11/7/2019 | 11/14/2019 |  | 11/21/2019 |  | 11/28/2019 | 12/5/2019 | 12/12/2019 |  |  | 12/19/2019 | 12/26/2019 | 1/2/2020 |  | 1/9/2020 |  |  | 1/16/2020 | 1/23/2020 |  |  | 1/30/2020 |  | 2/6/2020 |  | 2/13/2020 |  | 2/20/2020 |  |  | 2/27/2020 |  |  |  | 3/5/2020 | 3/12/2020 | 3/19/2020 | 3/26/2020 |  |  | 4/2/2020 |  | 4/9/2020 |  | 4/16/2020 |  | 4/23/2020 |  |  | 4/30/2020 |  |  | 5/7/2020 |  | 5/14/2020 |  | 5/21/2020 |  |  | 5/28/2020 | 6/4/2020 |  |  | 6/11/2020 |  | 6/18/2020 |  | 6/25/2020 |  |  | 7/2/2020 |  |  | 7/9/2020 | 7/16/2020 |  |  |  | 7/23/2020 |  |  | 7/30/2020 |  |  | 8/6/2020 |  | 8/13/2020 |  |  | 8/20/2020 |  |  |  | 8/27/2020 |  |  |  | 9/3/2020 | 9/10/2020 | 9/17/2020 | 9/24/2020 | 10/1/2020 | 10/8/2020 | 10/15/2020 | 10/22/2020 | 10/29/2020 |  |  |  | 11/5/2020 | 11/12/2020 | 11/19/2020 | 11/26/2020 |  | 12/3/2020 |  | 12/10/2020 |  |  | 12/17/2020 | 12/24/2020 |  | 12/31/2020 | 1/7/2021 | 1/14/2021 | 1/21/2021 | 1/28/2021 |  |  | 2/4/2021 | 2/11/2021 | 2/18/2021 |  |  | 2/25/2021 |  | 3/4/2021 | 3/11/2021 |  |  | 3/18/2021 |  | 3/25/2021 | 4/1/2021 | 4/8/2021 | 4/15/2021 | 4/22/2021 |  | 4/29/2021 | 5/6/2021 | 5/13/2021 |  |  | 5/20/2021 |  |  | 5/27/2021 |  | 6/3/2021 |  |  | 6/10/2021 |  | 6/17/2021 |  | 6/24/2021 |  | 7/1/2021 | 7/8/2021 |  | 7/15/2021 | 7/22/2021 | 7/29/2021 | 8/5/2021 |  |  | 8/12/2021 |  | 8/19/2021 |  | 8/26/2021 |  |  | 9/2/2021 | 9/9/2021 |  | 9/16/2021 | 9/23/2021 | 9/30/2021 |  | 10/7/2021 |  | 10/14/2021 | 10/21/2021 |  | 10/28/2021 | 11/4/2021 | 11/11/2021 | 11/18/2021 | 11/25/2021 |  |  | 12/2/2021 | 12/9/2021 |  |  | 12/16/2021 | 12/23/2021 | 12/30/2021 | 1/6/2022 | 1/13/2022 |  | 1/20/2022 | 1/27/2022 | 2/3/2022 | 2/10/2022 | 2/17/2022 | 2/24/2022 | 3/3/2022 | 3/10/2022 | 3/17/2022 | 3/24/2022 | 3/31/2022 | 4/7/2022 | 4/14/2022 | 4/21/2022 | 4/28/2022
Key Project Milestone | Key Project Milestone | [9 empty] | GW 1/2 | [37 empty] | Quality Gate 3 | [6 empty] | GW 3/4 | [36 empty] | Machine Ready for Field | [20 empty] | Pilot EDS Freeze | [7 empty] | Endurance Complete | [21 empty] | GW 5 | [73 empty] | Production EDS Freeze |  |  | GW 5.5 | [22 empty] | GW 6
Key Validation review | Key Validation review | [47 empty] | Validation Review 3 | [49 empty] | Validation Review 4 | [24 empty] | Validation Review 5
Software Milestone | Software Milestone | [19 empty] | Receive V01 SW |  |  |  | V02 SW Content Freeze | [19 empty] | Receive V02 SW |  |  | V03 SW Content Freeze | [15 empty] | Receive V03 SW | [5 empty] | V04 SW Content Freeze | [12 empty] | Receive V04 SW (Pilot) |  | V05 SW Content Freeze | [10 empty] | Receive V04 SW (Pilot)
TIC Report Milestone | TIC Report Milestone | [90 empty] | EMC-Pilot- Pilot |  | ISO 9533 Horn, Back-up Alarm EN474 HAWB- Pilot | [12 empty] | ISO 5010 Steering Feasibility (Pilot) |  | ISO 3450 Brake Feasibility (Pilot) | [54 empty] | ISO 3450 Brake CERT |  |  |  | ISO 5010 Steering CERT |  |  | ISO 10570-Articulation Lock CERT | [24 empty] | ISO 9533 Horn, Back-up Alarm HAWB CERT | [12 empty] | Stg V EMC CERT
Tech Center ShakeTabl | Tech Center ShakeTabl | [17 empty] | Hood arrives at Tech Center, Peoria | [10 empty] | Stage V Shake Table # 1 | [71 empty] | Machine Update for OMSA # 2 | [9 empty] | Stage V Shake Table # 2 with OMSA Drive File (Post Machine OMSA)
SGW00208 | 966GC T3 TB #3 | [21 empty] | Shift Dev |  |  | HVAC Perf Checkout |  |  |  | Water system/ With Prod Rad Fixes |  |  | L5 Tuning |  |  |  | Operator Eval | Endurance-250 hrs |  |  | Final Inspection |  | Machine Update | [7 empty] | Light Structures (Stg V Hood) OMSA #1 (Contingency) | [39 empty] | Machine Update | [8 empty] | Light Structures (Stg V Hood) OMSA #2 (Likely Path)
SGW00201 | 966GC Stage V TB #1 | [28 empty] | Ship Machine Aurora MDC |  | Machine Build (Teardown and start build Jan 26) | [13 empty] | Build Issue resolution |  |  | Ship Machine PPG |  | Machine Checkout STP-64 | Ver 01 SW (STP 230/289) (Steering, L5, XSMN) |  |  | Sound Development (Machine, Cab Sound) |  |  | L5 Performance Check (Include Thermal Mgmt Valve) |  |  | C9.3B Stage V Engine Performance | Trans Tuning |  |  | L5 Tuning # 1 |  | Operator Eval | Rimpull/Response | [5 empty] | HVAC Perf Checkout | Issue Resolution # 1 |  |  | Ver 02 SW (STP 230/289) (Steering, L5, XSMN) | Safety/Serviceability audit |  | Water Flow and Water System |  |  | Stg V Ambient Capability and UHT (Include AOC Channels) | [20 empty] | Dust Ejector Measurement |  |  | STP 401 Engine Install Audit |  | DEF and Fuel Tank Calibration | Ver 03 SW (STP 230/289) (L5, XSMN, Engine) |  | Limited Slip Differential Development Driveline Signature | [7 empty] | Issue Resolution # 2 |  |  | Dealer Service Training | L5 Tuning and Performance Check # 2 |  | Ver 04 SW (STP 230/289) (Steering, L5, XSMN, Engine) BOB |  |  | Thermal Mgmt |  | Ver 05 SW (STP 230/289) (L5, XSMN) |  |  | Thermal Mgmt endurance |  |  | Endurance 0-500 hrs+ Service/Inspect (Cold Ambient) | [6 empty] | Issue Resolution # 3 | [6 empty] | Stage V Engine Cold Room (TC-L)
SGW00202 | QPG 966GC CNR4 TB#2 | [23 empty] | Machine Build + Issue Resolution | [10 empty] | China New Year |  |  | Machine Checkout STP-64 |  |  |  |  | CNR4 SW Checkout-250 hrs | [5 empty] | Sound Test (including cab glass) ISO 9533, HAWB |  | Engine Installation Audit |  |  | Issue Resolution # 1 |  |  | Hydraulic checkout |  | L5 Checkout | CNR4 SW Endurance- 250 hrs | [10 empty] | Endurance Inspection | [5 empty] | EMC Feasibility | [5 empty] | Stg V Ver 02 SW (STP 230) |  | L5 Checkout- Stg V |  | Safety/Serviceability audit | ISO 3450 Brake Feasibility (Optional) | [7 empty] | ISO 5010 Steering Feasibility (Include Secondary Steering) | [6 empty] | Stg V Ver 03 SW (STP 230) |  | Endurance 250-750 hrs | [16 empty] | Endurance Inspection | [10 empty] | Stage V Ver 04 SW (STP 230)
SN | PPG 966GC Stage V Pilot #1 | [142 empty] | Machine Build |  |  | China New Year |  | Machine Build | [6 empty] | Machine Ship | [15 empty] | Machine Checkout STP-64 |  | SW Checkout # Pilot V01 |  | C9.3B Stage V Engine Performance | L5 Performance Check |  | Machine Endurance- 100 hrs |  | Light Structures (Stg V Hood) OMSA # 3 | [8 empty] | Stg V Alarm, FWD Horn, HAWB CERT | Stage V EMC Test |  |  | Endurance 0-250 hrs+ Service/Inspect |  |  |  |  | Endurance 251-500 hrs+ Service/Inspect |  |  | Productivity
SN | QPG 966GC CNR4/ Stg V Pilot #2 | [142 empty] | Machine Build |  |  | China New Year |  |  | Machine Checkout STP-64 |  |  |  | Safety/Serviceability audit | SW Checkout # 1 |  |  | MLIT Practice | [6 empty] | MLIT Witness (Is witness test 12 weeks after MLIT practice?) |  | Sound Test |  | ISO 3450- Brake CERT | [8 empty] | ISO 5010- Steering CERT |  |  |  |  | ISO 10570-Articulation Lock CERT |  |  | Endurance 0-250 hrs | [5 empty] | Service/Inspect | [5 empty] | Endurance 251-500 hrs | [7 empty] | China National Day |  | Service/Inspect |  |  | Endurance 501-750 hrs | [5 empty] | Service/Inspect |  |  |  |  | Endurance 750-1000 hrs | [5 empty] | Service/Inspect